## Dashboard
Web Page Total Bugs | Open Bugs | Closed Bugs | Dev completed | To test | Questions | Suggestions | Rejected | High Open Bugs | Medium Open Bugs | Low Open Bugs | Nominal | Readiness | Blank | Web Page Dev Assigned Nominal High And Medium Bugs Open Bugs and Questions | Bogdan | Gowthami | Mihaita | Ionut | Gary C | Oz | Bogdan E
108 | 51 | 17 | 27 | 1 | 2 | 8 | 2 | 8 | 11 | 32 | 69 | 20 | 0 |  | 13 | 2 | 0 | 1 | 2 | 0 | 3
PIM Total Bugs | Open Bugs | Closed Bugs | Dev completed | To test | Questions | Suggestions | Rejected | High Open Bugs | Medium Open Bugs | Low Open Bugs | Nominal | Readiness | Blank | PIM Dev Assigned | Arvind | Maciej | Cristian | Piotr | Gowthami | N/A2 | N/A3
79 | 61 | 12 | 0 | 1 | 3 | 2 | 0 | 11 | 37 | 13 | 17 | 5 | 57 |  | 3 | 1 | 2 | 2 | 0 | 0 | 0
OMS Total Bugs | Open Bugs | Closed Bugs | Dev completed | To test | Questions | Suggestions | Rejected | High Open Bugs | Medium Open Bugs | Low Open Bugs | Nominal | Readiness | Blank | OMS Dev Assigned | N/A | N/A1 | N/A2 | N/A3 | N/A4 | N/A5 | N/A6
7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6 | 12 | 7 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Web Page Bug List
SABRE 2.0 - Web Page BUG LIST
BUG ID | BUG Description | Page | Nominal / Readiness | Status | Priority | Raised By / Tester | Dev. owner | Progress | Comments | Date discovered | Date closed
1 | Product Listing Page filter, if you search by "Best sellers" you get the following error: Internal Server Error It seems there was a problem with that request java.lang.NullPointerException | Product Listing Page | Readiness | Rejected | Low | Stefan | Bogdan |  | Best sellers option was removed | 2016-11-03
2 | Product Listing Page, "View by" grid buttons does not modify the grid. | Product Listing Page | Nominal | Open | Medium | Stefan | Bogdan E |  | Designs being worked on by Bogdan E | 2016-11-03
3 | Product Listing Page, Filters "Lower price" and "Highest price", Results per page, are randomizing results everytime each filter is clicked | Product Listing Page | Nominal | Closed | Medium | Stefan | Gowthami |  |  | 2016-11-03
4 | Checkout flow, once you complete all the required fields and even if you let them blank when you click to proceed to checkout, you get the following error : Internal Server Error It seems there was a problem with that request Can not deserialize instance of java.lang.String out of START_ARRAY token at [Source: java.io.ByteArrayInputStream@6f709a07; line: 1, column: 33] (through reference chain: com.brandpath.core.business.transfer.Consumer["properties"]) | Checkout | Nominal | Closed | High | Stefan | Gowthami / Emil |  | Bogdan: Validation required on fields Update 14/3/2016 Stefan : we don't get the same error anymore, but we still get an error Internal Server Error It seems there was a problem with that request Later update 14/03/2016 Geani: Internal Server Error It seems there was a problem with that request java.lang.NullPointerException NOTE: On local it works 16/03/2016 Geani Issue fixed 17/03/2016 Geani: Issue is back, Internal Server Error It seems there was a problem with that request 17/03/2016 Geani Issue fixed 18/03/2016 Geani : issue is back again | 2016-11-03 | 18/03/2016 Geani
5 | Product Listing Page (Variations & colours), if you click on "Size" or "Color" of anyof the devices listed, the changes appear only to the first device in the list. please check ( screenshot 1 ) for details | Product Listing Page | Readiness | Closed | Low | Stefan | Bogdan |  |  | 2016-11-03 | Stefan: 16/3/2016
6 | Product Listing Page, when you click on "Offers available" the "Close" button of the new window is not displayed correctly ( screenshot 2 ) | Product Listing Page | Readiness | Dev Completed | Low | Stefan | Ionut | Dev Completed | Stefan : tested on 1280x1024 resolution | 2016-11-03 | Ionut: 21/3/2016
7 | Product Listing Page , go to second page, the focus goes to Footer | Product Listing Page | Readiness | Closed | Low | Stefan | Bogdan |  | Bogdan: Needs instructions how it should behave | 2016-11-03 | Geani 15/03/2016
8 | Home Page, In the Header section of the homepage, the "Product" "Apps" "Support" "Business" "Shop" "My Samsung" submenus are not redirecting to proper sections of the website. | Home page | Readiness | Open | Low | Stefan | Bogdan |  | Redirect links to be added | 2016-11-03
9 | Product Listing Page, Left panel filters don't work | Product Listing Page | Nominal | Open | Medium | Stefan | Gary C |  | Business decision | 2016-11-03
10 | Product Listing Page, TV & AV , Shop by TV Feature, if you select four features and try to select the fifth, all the features are flickering on mouseover | Product Listing Page | Readiness | Dev Completed | Low | Stefan | DragosS |  |  | 2016-11-03
11 | Search button is not clickable | All | Readiness | Closed | Low | Stefan | Ionut |  | Search functionality need to be added. The cursor is now highlighting a click action | 2016-11-03 | Stefan: 16/3/2016
12 | Product Listing Page, this error happens sometimes when you add multiple products on basket Internal Server Error It seems there was a problem with that request Object is NULL ! | Product Listing Page | Nominal | Open | Medium | Stefan | Emil / Gowthami |  | Needs more testing as this issue is random (occured twice at 13 prodcuts diffrent products and at 10 diffrent prodcuts, note that some products had around 10 quantity) | 2016-11-03
13 | Product Details Page, No Arefs/quick links/anchor points. As per design | Product Details Page | Nominal | Closed | Medium | Gary / Stefan | Bogdan |  | Mihaita - 15th March | 2016-11-03 | Stefan: 16/3/2016
14 | Delay in page initialisation / loading Note: On IE 11 the time is around 30seconds - 1 minute | Home page | Nominal | Open | High |  | Bogdan |  | Issue related to dev packaging | 2016-11-03
15 | Add to basket indicator / lightbox | Product Listing Page / Product Details Page | Readiness | Closed |  |  | Bogdan |  | A visual cue has been added on the cart icon | 2016-11-03 | Stefan: 15/3/2016
16 | Item count isn't working / gets removed | Basket | Nominal | Closed | [5 empty] | 2016-11-03 | 14/3/2016
17 | All pages - Black header has no background colour in Internet Explorer 11 (screenshot 3) | All | Readiness | Open | Low | Ionut | Bogdan |  |  | 2016-11-03
18 | Home Page - Subscribe button not working | Home page | Readiness | Open | Low | Ionut |  |  | Service required | 14/3/2016
19 | Mini basket shoud have a scroll bar and fixed size. Adding more than 10 products will display a long list | Mini basket | Readiness | Suggestion | Low | Geani | Bogdan |  |  | 14/3/2016
20 | Clear basket button should be added to mini basket | Basket / Mini basket | Readiness | Suggestion | Low | Geani | Bogdan |  |  | 14/3/2016
21 | Basket page - If the basket is empty the user can still proceed to ckecout and paymant page | Basket / Mini basket | Readiness | Closed |  | Geani | Bogdan |  |  | 14/3/2016 | 14/3/2016
22 | Home page - Find more/Shop now buttons don't work | Home page | Nominal | Open | Low | Geani | Bogdan |  |  | 14/3/2016
23 | Home page - Pressing "More" from Samsung Galaxy S6" mouse over refreshes the page | Home page | Nominal | Open | Low | Geani | Bogdan |  |  | 14/3/2016
24 | Product listing - Add to basket / details from "Offers available" redirect to home page | Product Listing Page | Nominal | Open | Low | Geani | Bogdan |  |  | 14/3/2016
25 | Product listing - Pressing "Quick view" and "Full details" redirects to home page with a white overlay blocking everything. Note: Pressing back the overlay remains active | Product Listing Page | Nominal | Closed | High | Geani | Bogdan |  |  | 14/3/2016 | Geani 15/03/2016
26 | Pressing "Go to basket" form mini basket doesn't close mini basket | Mini basket | Nominal | Closed | Medium | Geani | Bogdan |  |  | 14/3/2016 | Geani 15/03/2016
27 | IE 11 - Home page - On Shop Smart with Samsung section icons are not aligned with the copy. (screenshot 4) | Home page | Nominal | Closed |  | Ionut | Mihaita |  |  | 14/3/2016 | Stefan: 15/3/2016
28 | Checkout - After adding all Billing Details and pressing Checkout, then clicking back "Checkout" button becomes unavailable | Checkout | Nominal | Closed | Medium | Geani | Oz |  | Oz to clarify behaviour OZ: Yes correct we should not allow customers to go back once they have entered the checkout. | 14/3/2016
29 | Basket page - Adding voucher doesn't work | Basket | Readiness | Open | Low | Geani | Bogdan |  |  | 14/3/2016
30 | IE 11 - Product Listing Page - Sort by filters dropdown has 2 arrows ( screenshot 5 ) | Product Listing Page | Nominal | Closed | Low | Stefan | Bogdan |  |  | 14/3/2016 | 16/03/2016 Geani
31 | Product listing - Pressing "Quick view" and "Full details" or "Add to basket" redirects to home page | Product Listing Page | Nominal | Open | Low | Geani | Bogdan |  |  | 15/3/2016
32 | Shopping basket - If you click any of the "Express Delivery (1 - 2 days)" "Smart TV installation service: Free Standing (2 - 4 days)" "Home appliances installation service: Wet Connection (2 - 4 days)" at checkout page you see "Express Delivery (1 - 2 Days)" always. | Checkout | Readiness | Open | Low | Stefan | Bogdan |  |  | 15/3/2016
33 | Thank you page - Address and company display wrong result Example Company: geani test adress Address: geani test addition address NOTE: There is no company firled on checkout form | Checkout | Nominal | Closed | Medium | Geani | Oz |  | We currently don't have a company field (address line 1 is being displayed there) OZ: Agree company field is not required as we aren't catering for enterprise customers. | 16/3/2016
34 | If mini basket is too long (e.g. 19 products) "Checkout" and "Proceed to Basket" buttons can't be reached. See BUG ID 19 | Mini basket | Readiness | Dev Completed | High | Geani | Mihaita |  | 16/3/2016 Geani: Please see suggestion ID 19 | 16/3/2016
35 | Mini basket closes when translating from white header to black header | Mini basket | Readiness | Suggestion | Low | Geani | Bogdan |  | That was intended functionality | 16/3/2016
36 | While in basket a product can be added with maximum quantity of 10. But if spamming add to basket button from product listing the quantity can reach higher values ( i managed 33) | Basket | Nominal | Open | Medium | Geani | Bogdan |  | Does the quantity 10 limitation apply to Sabre? If so, it will also be added on the listing / pdp Oz: We should add 20 as on current website | 17/3/2016
37 | Hard coded colour & memory variations. Data is there but not yet rendered. Will be part of nominal flow. | Product Listing Page | Nominal | Open | High | Simon T | Bogdan | ??? | Added by Simon T | 16/3
38 | Add to basket - MASSIVE lightbox required when customer adds to basket. Or similar | Basket | Nominal | Dev Completed | High | Simon T | Mihaita | 100% | Added by Simon T | 16/3
39 | Basket – grey is wrong colour. Need white | Basket | Nominal | Open | Medium | Simon T | Bogdan E |  | Added by Simon T | 16/3
40 | Basket alignment, decimal points, and consistency | Basket | Nominal | Dev Completed | Medium | Simon T | Bogdan | 100% | Added by Simon T | 16/3
41 | Proceed to checkout button should be duplicated at top of page as well as bottom | Checkout | Nominal | Dev Completed | Low | Oz | Mihaita |  | The user must select the payment method and agree to t&c before checkout | 17/3
42 | Remove button in basket is misaligned | Basket | Nominal | Open | High | Oz | Bogdan |  | Please clarify (screenshot) | 17/3
43 | No VAT calculations | Checkout | Nominal | Dev Completed | High | Oz | Bogdan & Dragos | 100% | See Bug ID 78 (PIM Bug List) | 17/3
44 | 1000 seperate is missing on amounts | Checkout | Nominal | Dev Completed | High | Oz | Bogdan & Dragos | 100% | Prices will be in this format 1,000.00 | 17/3
45 | "Same as shipping address" checkbox should be moved down the list after the "Phone field" | Checkout | Nominal | Dev Completed | High | Oz | Mihaita |  |  | 17/3
46 | £0 should be displayed as FREE | Checkout | Nominal | Dev Completed | High | Oz | Bogdan & Dragos | 100% | This covers also 0.00 | 17/3
47 | Product count is displayed on VAT field | Checkout | Nominal | Dev Completed | High | Oz | DragosS | 100% |  | 17/3
48 | Specific validation required (e.g. email, phone) | Checkout | Nominal | Dev Completed | High | Oz | Ionut |  | See Bogdan for details | 17/3
49 | Confirm email address field | Checkout | Nominal | Dev Completed | High | Oz | Mihaita |  |  | 17/3
50 | If the order takes too long to complete, internal server error will occur or redirect to the home page. Session time out time is too small. | All | Nominal | Open | High | Oz | Bogdan |  | Server Side Issue. Needs more testing for session expiry. | 17/3
51 | Write a review should be clickable. | Product Listing Page | Readiness | Open | Low | Oz | Bogdan |  |  | 17/3
52 | Star rate doesn't work | Product Listing Page | Readiness | Open | Low | Geani | Bogdan |  |  | 17/3
53 | Add "You save" calculation price | Product Listing Page | Nominal | Dev Completed | High | Oz | DragosS |  |  | 17/3
54 | Add SKU code on details page | Product Details Page | Nominal | Dev Completed | High | Oz | Mihaita | 100% |  | 17/3
55 | Will black banner (samsung Bespoke at this momment) automatically change? | Home page | Nominal | Open | Low | Geani | Bogdan |  | Oz: It should after implementation | 18/03/2016
56 | Price range finder is randomizing variants everytime filter is clicked | Product Listing Page | Nominal | Open | Medium | Geani | Gowthami |  | Similar to the sorting issue | 18/03/2016
57 | Shop By TV Screen Size filters don't work | Product Listing Page | Nominal | Question | Medium | Geani | Bogdan |  |  | 18/03/2016
58 | Shop by TV Feature filters don't work | Product Listing Page | Nominal | Question | Medium | Geani | Bogdan |  |  | 18/03/2016
59 | Quantity can't be modifed from mini basket | Mini basket | Readiness | Open | Low | Geani | Bogdan |  |  | 18/03/2016
60 | Mini basket should reflect quantity or only diffrent products? | Mini basket | Readiness | Dev Completed | Low | Geani | Bogdan |  | Oz: quantinity | 18/03/2016
61 | Add to basket from "UPSELL" page redirects to homepage | Upsell | Nominal | Open | Medium | Geani | Bogdan |  |  | 18/03/2016
62 | UPSELL page - proceed to basket and continue shopping are missaligned | Upsell | Nominal | Open | Low | Geani | Bogdan |  |  | 18/03/2016
63 | Basket page - pressing the numbers steps circle the user can bypass steps in the buying flow | Basket/Checkout | Nominal | Open | Medium | Geani | Bogdan |  | Related to Bug ID 75 | 18/03/2016
64 | Completed steps from buying flow shold be marked (e.g. green text) | Basket/Checkout | Nominal | Open | Low | Geani | Bogdan |  |  | 18/03/2016
65 | Step 2 from buying flow (Login) - Two email address field are present | Basket/Checkout | Readiness | Open | Low | Geani | Bogdan |  |  | 18/03/2016
66 | Back to top link should be more visible and not only at the bottom of the page | All | Nominal | Suggestion | Low | Geani | Bogdan |  |  | 18/03/2016
67 | Footer link don't work | All | Nominal | Open | Low | Geani | Bogdan |  |  | 18/03/2016
68 | Footer search doesn't work | All | Nominal | Open | Low | Geani | Bogdan |  |  | 18/03/2016
69 | Sign-up link is missing from log in page | All | Readiness | Open | Low | Geani | Bogdan |  |  | 18/03/2016
70 | Shopping basket table is missing top line NOTE: this issue also occurs on checkout page and confirmation page an thank you page | Basket/Checkout | Nominal | Rejected | Low | Geani | Bogdan |  |  | 18/03/2016
71 | On shopping cart only one payment option is displayed (Paypal Credit) | Basket/Checkout | Readiness | Open | Low | Geani | Gary C |  | TBC | 18/03/2016
72 | Too much empty space around "Continue as guest" | Basket/Checkout | Nominal | Open | Low | Geani | Bogdan E |  |  | 18/03/2016
73 | Having only 15 products and the filter to list only 15 products will generate an empty second page. This issue can be seen at this moment (18/03/2016 11:57) on TV page | Product Listing Page | Nominal | Dev Completed | Medium | Geani | Gowthami |  | Returns incorrect number of pages | 18/03/2016
74 | Selecting page Two (for example) on another category (e.g. TV) and then selecting another category (e.g. Phones) will display page Two of phoens instead of page one | Product Listing Page | Nominal | Dev Completed | Medium | Geani | Bogdan / DragosS | 100% |  | 18/03/2016
75 | If pressing back after redirecting to the payment page, without completing the payment) and then pressing on the 4th step icon, the user can reach the order confirmation page. Presssing "place your order" will result in error It seems there was a problem with that request Charge failed: transaction is at an invalid mainStatus/subStatus: INPROGRESS/PAYPAL_SETEC_COMPLETED | Basket/Checkout | Nominal | Open | High | Geani | Bogdan |  | Also disable the checkout stepper steps when navigation is not allowed | 18/03/2016
76 | Receiving an error during payment will not reset sesion. Further payments cant be completed displaying http://10.41.7.31/null | Checkout | Nominal | Open | High | Geani | Bogdan |  | Speak to Gowthami / Andrei | 18/03/2016
77 | I'm receiving a lot of Internal Server Error at payment on Chrome and need to delete browser data to work again once or twice then again the error. On IE11 it is ok. | Checkout | Nominal | Open | High | Geani | Bogdan |  | Internal Server Error It seems there was a problem with that request java.lang.NullPointerException Possibly related to Bug ID 76 | 18/03/2016
78 | Confirmation page / Thank you page - Paymant details are missing. Only Visa, mastercard icons displayed | Checkout | Nominal | Suggestion | Low | Geani | Oz |  |  | 18/03/2016
79 | Confirmation page / Thank you page - If select different biling and shipping address .. only shipping details are displayed | Checkout | Nominal | Open | Medium | Geani | Bogdan |  |  | 18/03/2016
80 | Confirmation page / Thank you page - First name, Last name, email, phone are hard coded | Checkout | Nominal | Dev Completed | Low | Geani | Bogdan |  |  | 18/03/2016
81 | Confirmation page / Thank you page - CART TOTAL should be aligned with subtotal | Checkout | Nominal | Dev Completed | Low | Geani | DragosS | 100% |  | 18/03/2016
82 | Thank you page - Lorem ipsum dolor sit amet....... text present | Checkout | Nominal | Open | Low | Geani | Bogdan |  |  | 18/03/2016
83 | Product details - Color and size doesn't update name/price | Product Listing Page / Product Details Page | Nominal | Open | Low | Geani | Bogdan |  |  | 18/03/2016
84 | Product details - Add to basket buttons redirect to home page | Product Details Page | Nominal | Open | Low | Geani | Bogdan |  |  | 18/03/2016
85 | Product details - "Shop deals" button from the top of the page does nothing and remains clicked | Product Details Page | Nominal | Open | Low | Geani | Bogdan |  |  | 18/03/2016
86 | Product details - aditional images can't be clicked/ changed | Product Details Page | Nominal | Open | Low | Geani | Bogdan |  |  | 18/03/2016
87 | Product details - Bundle "detail" buttons don't work/ redirect to homepage | Product Details Page | Nominal | Open | Low | Geani | Bogdan |  |  | 18/03/2016
88 | Product details - Accesorry "More details" , " Quick view" ,"Offers available" buttons don't work NOTE: Same issues occurs for "Similar items" category | Product Details Page | Nominal | Open | Low | Geani | Bogdan |  |  | 18/03/2016
89 | Product details - Page sections (e.g. About, Features, Specifications) should be more clearly delimited | Product Details Page | Nominal | Suggestion | Low | Geani | Bogdan |  |  | 18/03/2016
90 | Product details - [+] Show more features link redirects to home page | Product Details Page | Nominal | Open | Low | Geani | Bogdan |  |  | 18/03/2016
91 | Product details - Product Fiche functionality is missing | Product Details Page | Nominal | Open | Low | Geani | Bogdan |  |  | 18/03/2016
92 | Should there be a page count in the URL for the listing pages? | Product Listing Page | Readiness | Suggestion | Low | Geani |  |  |  | 18/03/2016
93 | Summing a £4499.99 product 5 times resulted in £22499.949999999997 price £4499.99 x10 = £44999.899999999994 Tested with 75" JU7000 7 Series Flat UHD 4K Smart 3D LED TV | Basket/Checkout | Nominal | Dev Completed | High | Geani | Bogdan | 100% |  | 18/03/2016
94 | Link to the product details should be added in the basket, checkout, minibasket and all occurences | Basket/Checkout/Product details page | Nominal | Open | Medium | Geani | Ionut |  |  | 18/03/2016
95 | Price too long can break basket design. Please see bug id 99 screenshot | Minibasket/ Basket | Nominal | Dev Completed | Low | Geani | Bogdan |  |  | 18/03/2016
96 | Basket page - pressing + or - buttons will display an _ under the button transforming - into = and + in ± | Basket | Nominal | Dev Completed | Low | Geani | Bogdan |  |  | 18/03/2016
97 | Shouldn't on paypall page display the payment price? At this moment only the address is displayed. | Checkout | Nominal | Open | Medium | Geani | Andrei |  |  | 18/03/2016
98 | Pressing back after leaving thank you page (http://10.41.7.31/#/cart/complete) will display a blank white page | Checkout | Nominal | To Test | Medium | Geani | Bogdan |  | Scenario details | 18/03/2016
100 | How long does it takes for an offering created in PIM to appear on the site? |  | Nominal | Closed | Low | Geani |  |  | Oz: About 30 seconds | 18/03/2016
99 | On the Upsell page you have "Additional Options" for your product which can be close or expanded. If you add a product and try to close the "Additional Options" tab it won't close, but when the page is refreshed, it works. | Upsell | Nominal | Open | Low | Stefan | Bogdan |  |  | 21/03/2016
100 | On Checkout page if your press "Go back to your Cart - To update your items" you will be redirected to homepage | Checkout | Nominal | Dev Completed | Medium | Stefan | Mihaita |  |  | 21/03/2016
101 | "Add to compare" should be added on Product listing page. | Product Listing Page | Readiness | Suggestion | Low | Stefan | Oz |  |  | 21/03/2016
102 | Product details page, breadcrumbs redirect to homepage. | Product Details Page | Nominal | Dev Completed | Medium | Stefan | Mihaita | 100% |  | 21/03/2016
103 | Redirecting from checkout to PayPal will give 404 Not Found The requested URL /null was not found on this server. Apache/2.2.15 (Oracle) Server at 10.41.7.31 Port 80 | Checkout | Nominal | Closed | High | Geani |  |  |  | 21/03/2016 | 23/03/2016
104 | Checkout page, "Terms and Conditions" redirect to homepage | Checkout | Nominal | Open | Low | Stefan | Bogdan |  |  | 21/03/2016
105 | Firefox , Buttons activates on right click | All | Nominal | Dev Completed | Low | Stefan | DragosS |  |  | 23/03/2016
106 | After PayPal payment, pressing "Place Order" will display the following error: It seems there was a problem with that request No enum constant com.brandpath.psm.common.enums.SubStatusEnum.REVIEW_EXPRESS_CHECKOUT_COMPLETED | Thank you page | Nominal | Open | High | Geani |  |  |  | 24/03/2016
107 | "was £" indicator appear even if the price isn't reduced | Prodcut Listing | Nominal | Dev Completed | Medium | Geani | DragosS |  |  | 25/03/2016
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207

## Web Page Screenshots
Screenshot ID
1
2
3
4
5
bug ID 99

## PIM Bug List
SABRE 2.0 - PIM BUG LIST
BUG ID | BUG Description | Nominal / Readiness | Status | Priority | Raised By / Tester | Dev. owner | Comments | Date discovered | Date closed
1 | Draft produs have corrupt image display. Please see screenshot. |  | Suggestion | Low | Geani |  | 21.01.2016 Geani: We should have an default image for all products that are in draft mode. An place holder image untill the produt is published. | 16/12/2015
2 | Product tab - Name filter doesn't work unless selecting product from the list. 26/01/2016 Geani: Please see comments |  | Closed | Medium | Geani |  | 04/01/2016 Geani: The filter is case senzitive "nokia" doesn't generate drop down list but "Nokia" does. 26/01/2016: Geani Search now works but previous note still valid. " The filter is case senzitive "nokia" doesn't generate drop down list but "Nokia" does." 25/02/2016 Geani: Name search only display PUBLISHED prodcuts | 16/12/2015 | Stefan : 25/3/2016
3 | NullPointerException when creating new product com.brandpath.pim.web.controller.product.version.AssetVersion.initNewAsset(AssetVersion.java:383) com.brandpath.pim.web.controller.product.version.AssetVersion.showDimensionMin(AssetVersion.java:198) [:] |  | Question | Medium | Geani |  | 5/02/2016 Geani: I didn't add this and I don't know how to retest this. It' doesn't reprodus on my side, or i don't test is correctely. 09/03/2016 Geani: Who added this? It was makred "To Test". I don't know who te retest this | 2016-12-01
4 | Offerings Price list - Validation error goes out of error box. |  | Open | Medium | Geani |  | PRICELISTTABSFORM:PRICELISTTABVIEWID:PRICELISTGENERALFORM:TYPE: VALIDATION ERROR: VALUE IS NOT VALID PRICELISTTABSFORM:PRICELISTTABVIEWID:PRICELISTGENERALFORM:TYPE: VALIDATION ERROR: VALUE IS NOT VALID | 13/01/2016
5 | After some time (usuallty after being idle for 5 or so minutes) everything will stop working. To work again I need to refresh the page and log in again. then this error is displayed. After another refres everythig is working. This XML file does not appear to have any style information associated with it. The document tree is shown below. <partial-response id="j_id1"> <error> <error-name>class javax.faces.application.ViewExpiredException</error-name> <error-message> <![CDATA[ viewId:/pim/products/versionView/tabs/productTabs.xhtml - View /pim/products/versionView/tabs/productTabs.xhtml could not be restored. ]]> </error-message> </error> </partial-response> |  | Open | Medium | Geani |  | ERROR [org.keycloak.adapters.RefreshableKeycloakSecurityContext] (default task-30) Refresh token failure status: 400 {"error_description":"Refresh token expired","error":"invalid_grant"} 08/02/2016 Geani: Reopen as the issue still occurs | 18/01/2016
6 | Products - After retiring a product, there should be an option to reaactivate the product. Note: "Back to listing" button is not working after the product is retired. Note2: No error is displayed in the logs |  | Open | Medium | Geani |  | 08/02/2016 Geani: Can Not Test due to issue 55 22/02/2016 Geani : Reopen, issue still occurs | 18/01/2016
7 | Product variant creation doesn't work. Clicking "create" does nothing. Later update: The variant is created in product list but no message is displayed at creation, and the "related product" list is not updated/remains empty. This issue can generate duplicate products. |  | Closed | High | Geani | Maciej | On logs, after this line SEVERE [javax.enterprise.resource.webcontainer.jsf.context] (default task-18) javax.faces.el.EvaluationException: javax.ejb.EJBException: java.lang.ClassCastException: java.lang.String cannot be cast to com.brandpath.pim.model.template.TemplateProductPropertyValue lots of message appears | 18/01/2016 | 25/03/2016
8 | The following warning is displayed in growl when product details page is loaded: The form component needs to have a UIForm in its ancestry. Suggestion: enclose the necessary components within <h:form> |  | Open | Medium | Geani |  | Probably due to lack of standard html namespace declaration in the page header or missing <h:form> tag. Should not be solved by setting "severity" parameter on growl component | 21/01/2016
9 | Messaging service corrupted in PIM - list of recipients not being loaded. |  | Open | Medium | Geani |  |  | 22/01/2016
10 | After creating a price list, the default currency can't be changed. |  | Open | Low | Geani |  | 24/02/2016 Geani : Can not retest due to issue 63 | 28/01/2016
11 | Product Creation - Assets can't be uploaded. Afer pressing "add" nothing happens, the the log generates this long (the text is too long to paste it here) error ERROR [com.brandpath.pim.web.controller.product.version.AssetVersion] (default task-8) ERROR: java.lang.NullPointerException 19/02/2016 Geani: Has this fix been deployed? |  | Closed | High | Geani | Maciej | 19/02/2016 Geani: Has this fix been deployed? 24/02/2016 Geani : Can not test due to issue 60 25/02/2016 Geani: Please see issue 71 07/03/2016 PiotrI: Short investigation shows a problem with Calendar validation | 2016-05-02 | 25/03/2016
12 | Product Draft Edit - Pressing "edit" under the first asset image does nothing |  | Open | Medium | Geani |  | 24/02/2016 Geani : Can not retest due to issue 60 | 2016-05-02
13 | Product Draft Edit - While editing an already uploaded asset and changing the image, then pressing "Save" Nothing will happen and lots of errors appear in the log (too many to paste them here) |  | Open | High | Geani | Arvind | 24/02/2016 Geani : Can not retest due to issue 60 25/02/2016 Geani: I need to retest this 09/03/2016 Geani: Issue still occurs | 2016-05-02
14 | Product/Offerings to be able to open in browser tabs |  | Suggestion | Low | Geani |  |  | 22/02/2016
15 | Product drafts can't enter in EDIT mode. Two errors "May not be null" appear when pressing EDIT. Because of this issue new prodcuts can't be created. No ERROR apprear in the logs. NOTE THIS ISSUE ONLY OCCURS IN TYPE "MOBILE" |  | Closed | Low | Geani | Maciej | 25/02/2016 Geani : THIS ISSUE OCCURS ONLY ON TYPE "MOBILE" 07/03/2016 Piotri: The issue is related with Product Template configuration - there are dropdown properties with no values pre-populated. This should be handled gracefully, but it's not actually an error. | 24/02/2016 | Stefan: 25/3/2016
16 | Export buttons doesn't work |  | Open | Medium | Geani |  |  | 24/02/2016
17 | Products - manufacturer - creating a too long name result in a "null" value message Name i tried : geani test manufacturere tag Message : MAXIMUM LENGTH FOR THE PROPERTY "NULL": 1 |  | Open | Medium | Geani |  | Stefan 25/3/2016 : Issue still occurs VALIDATION ERROR MAXIMUM LENGTH FOR THE PROPERTY "NULL": 1 | 24/02/2016
18 | Media Asset Tab is empty |  | Open | Medium | Geani |  |  | 24/02/2016
19 | Administration - products - catalogue type description generates this message MAXIMUM LENGTH FOR THE PROPERTY "NULL": 1 Descprion used : adm geani test catalogue type |  | Open | Medium | Geani |  | Stefan 25/3/2016 Issue still occurs | 24/02/2016
20 | Voucher Instancces - Pressing the box to select all visible voucer instances doesn't activate buttons to delete or modify the vouchers |  | Closed | Medium | Geani |  |  | 25/02/2016 | 25/03/2016
21 | Offerings details - After creating an ofering, entering on draft mode will remove all details. Also not all fiels added by the "+" have the option to be removed If an filed is left empy after saving the draft, trying to publish it will give validation error. But if in this state text is introduced (without editing the draft) the validation error doesn't occur but the offering is published with an empty field |  | Open | Medium | Geani |  | 25/02/2016 Geani: If it isn't clear please call me on skype 25/03/2016 - Can not test as details fields are removed | 25/02/2016
22 | Offerings price list - Why only pricelist without offerings are displayed? |  | Question | Medium | Geani |  |  | 26/02/2016
23 | Offerings - publishing offerings doesn't update the title untill refreshign the page : (geani offering 2602 1410 [Draft v.1)]) STATUS PUBLISHED (V.1) |  | Open | High | Geani |  | Stefan 25/3/2016 Issue still occurs | 26/02/2016
24 | Offering creation - In orde to create an offering you must add the the device and click save enter in edit mode, add details, save enter edit mode again, add price list, save, publish Everythign should be done in one EDIT,SAVE,PUBLISH |  | Open | High | Geani | Cristian | 8/4/2016 Geani: After entering in edit mode, select "Testlist2" add a price list THEN add a product to the offering, the details and the price list will be rest if the draft was not saved before adding the product. ## Cristian: To approve if not auto refreshing of product add is an accepted solution. Details and Pricelist tabs are not cleaned anymore before Save. | 26/02/2016
25 | Offerings price list - assigned pricelist can't be removed |  | Open | Medium | Geani |  |  | 26/02/2016
26 | Product name search - Search vor a text in the middle of a name displays 0 result |  | Open | Medium | Geani |  |  | 26/02/2016
27 | Offerings - assigned products can't be removed or edited after publisching Note: new produts can't be added to the offering |  | Question | High | Geani | Maciej |  | 2016-01-03
28 | Default status filter only show Published prodcuts |  | Open | Medium | Geani |  |  | 2016-01-03
29 | Offering variant - after pressing "create" button the form is closed but the variant is not created |  | Closed | High | Geani | Maciej | 10/3/2016 maciejs: offering variant can be created after filling in all mandatory input filelds. Offering variants list is updated as well. | 2016-01-03
30 | Product history - no mouse over descriop for copy button |  | Open | Low | Geani |  |  | 2016-02-03
31 | Prodcut history - According to HLR search/filters for prodcut history is missing. Also details about prodcut drodcut details is missing from history tab |  | Open | Low | Geani |  |  | 2016-02-03
32 | According to HLR - HTML description is missing from prodcuts/offerings/bundles |  | Open | High | Geani | Piotr | 7/3/2016 PiotrI: Configuration issue | 2016-02-03
33 | According to HLR - Offerings (bundles) option for uploading images is missing |  | Open | High | Geani | Arvind | 07/03/2016: Functionality is underdevlopment 25/03/2016 Geani: Option to add asset is present, "Choose button is missing" | 2016-02-03
34 | Redirects (to OMS/CAI from the upper tab buttons) are invallid |  | Open | Low | Geani |  |  | 2016-02-03
35 | According to HLR (rediness) - Ratings & Reviews functionalilty is missing from PIM | Readiness | Open | Low | Geani |  |  | 2016-02-03
36 | According to HLR (rediness) - Assigning accesory to prodcuts functionality is missing | Readiness | Open | Low | Geani |  |  | 2016-02-03
37 | Offerings tab, while you are on edit mode, in price listing tab, when you try to schedule the product there is a display issue on "Select time" category ( check screenshot id 37 ) |  | Open | Low | Geani |  |  | 2016-02-03
38 | According to HLR (rediness) - Option to clone product is missing | Readiness | Open | Low | Geani |  |  | 2016-02-03
39 | According to HLR (rediness) - Services are missing | Readiness | Open | Low | Geani |  |  | 2016-02-03
40 | According to HLR (rediness) - Trade-in checkbox/field is missing | Readiness | Open | Low | Geani |  |  | 2016-02-03
41 | Offerings tab - Edit the product - Price list tab, when you set a schedule date and hour, that information is not listed anywhere. Option to edit/cancel the schedule should also be available |  | Open | Medium | Geani |  |  | 2016-02-03
42 | Abort draft doesnt work unless you complete the "Date" field, "May not be null" validation error appears. |  | Closed | High | Geani |  | 07/03/2016: Should be fixed with Bug#11 | 2016-02-03 | Stefan: 25/03/2016
43 | Price list details, history is empty. |  | Open | Low | Geani |  | Stefan: 25/03/2016 Issue still ocurs | 2016-02-03
44 | No Popup message on product workflow actions (i.e. Save, Publish etc). |  | Open | Low | Geani |  |  | 2016-07-03
45 | Errors in logs when Saving Offerings (functionality seems to be working) |  | Open | Medium | Geani | Arvind | 2016-03-07 13:27:14,078 ERROR [org.jboss.as.ejb3.invocation] (default task-13) JBAS014134: EJB Invocation failed on component ProductVersionService for method public com.brandpath.pim.model.product.ProductVersion com.brandpath.pim.business.service.product.ProductVersionService.findProductVersionWithInitialization(java.lang.Integer) throws com.brandpath.commons.business.exception.ServiceException: javax.ejb.EJBException: javax.persistence.NoResultException: No entity found for query | 2016-07-03
46 | Price List at offerings can't be searched |  | Closed | High | Geani | Arvind | 2016-03-07 13:29:31,596 ERROR [org.jboss.as.ejb3] (default task-17) javax.ejb.EJBTransactionRolledbackException: Parameter value [1, BPCREFSITE, BPC Reference Site] did not match expected type [com.brandpath.pim.model.offering.PriceListType (n/a)] | 2016-07-03 | Stefan: 25/03/2016
47 | Performance of the product details page - over 900 queries executed when opening this page |  | Open | Medium | Geani | Maciej |  | 2016-07-03
48 | In Related offerings tab - exception occurs - can't view the offering (if related offerings exists) |  | Closed | High | Geani | Maciej |  | 2016-07-03 | 25/03/2016
49 | Price list - cannot view more than 1 price type |  | Closed | Medium | Geani |  | 25/03/2016 Geani :Closed due to lacking description | 2016-07-03 | 25/03/2016
50 | Offerings listing - cannot change paging |  | Closed | Low | Geani | Cristian Uta | Fixed, paging is now available. Cristian | 2016-07-03 | 25/03/2016
51 | Images are not visible in the offerings |  | Open | Medium | Geani | Piotr | 3/7/2016 PiotrI: We need to change the logic on how images are viewed for offerings | 2016-07-03
52 | Prodcut creation - Led Lamp - Error generated in the logs Details are missing Assets can't be uploaded. "Choose" button is missing Product can't be published. |  | Open | High | Geani |  | 2016-03-10 10:30:42,940 ERROR [com.brandpath.pim.web.controller.product.version.AssetVersion] (default task-31) ERROR: java.lang.NullPointerException | 2016-10-03
53 | Offerings - Assets can't be uploaded. "Choose" button is missing |  | Closed | Medium | Geani |  | Geani: Duplicate of 33 | 14/03/2016 | 25/03/2016
54 | Offerings - The view/edit button is missing on some resolutions, tested on 1280x1024 resolution and 1366x768 |  | Open | High | Geani |  | Stefan 25/3/2016 issue still occurs | 14/03/2016
55 | Offerings - Adding multiple price list to an offering will display "Price 0" on offering listing page |  | Open | High | Geani |  | Stefan 25/3/2016 issue still occurs | 14/03/2016
56 | Product - Asset - when you add an asset there is a blue square, which if you click it and try to add another image you get the following error : Maximum number of files exceeded, please check ( screenshot 56 ) |  | Open | Low | Geani |  | Stefan 25/3/2016 issue still occurs | 14/03/2016
57 | Product creation - Mobile type creates duplicate prodcuts |  | Open | High | Geani | Cristian Uta | As tested in pimtest(15mar.) mobile type product creation creates the right number of products - only one. ## Can someone please check if bug is reproducible elsewhere? 15/03/2016 13:57 Geani: Pleasee product geani duplicate test 15032015 1325 v1, in prodcut listing appear two of them) Screenshot for confrimation attached. Please see screenshot 111 25/03/2016 Geani: Issue still occurs Please see bugid57dupliateTEST prodcut | 15/03/2016
58 | Voucher "applies to" - not generic enough. What is 'an order without items' | Nominal | Open | Medium | Simon / Kathryn |  |  | 18/03/2016
59 | Type = change from individual / open to single use / multiple use | Nominal | Open | Medium | Simon / Kathryn |  |  | 18/03/2016
60 | Max/Min spend should have unlimited as option (and default to) | Nominal | Open | Medium | Simon / Kathryn |  |  | 18/03/2016
61 | Available from / to = add time (as well as date). Applies to all scheduling options | Nominal | Open | Medium | Simon / Kathryn |  |  | 18/03/2016
62 | Usage - add unlimited usage option | Nominal | Open | Medium | Simon / Kathryn |  |  | 18/03/2016
63 | Consistency of download icons across all modules (ie. Excel, PDF) | Nominal | Open | Medium | Simon / Kathryn |  |  | 18/03/2016
64 | Vouchers nust not be included automatically to new offerings - logic | Nominal | Open | Medium | Simon / Kathryn |  |  | 18/03/2016
65 | Brandpath favicons not consistent across all modules | Nominal | Open | Medium | Simon / Kathryn |  |  | 18/03/2016
66 | Categories - add categories to "applies to" filter | Nominal | Open | Medium | Simon / Kathryn |  |  | 18/03/2016
67 | Assign products - needs reviewing. Just long list of products. UI for adding products needs re-engineering. Remove drop down. | Nominal | Open | Medium | Simon / Kathryn |  |  | 18/03/2016
68 | Do not centralise code and name columns in product listing page / PIM | Nominal | Open | Medium | Simon / Kathryn |  |  | 18/03/2016
69 | Mapping of Samsung codes to Tetra codes – 20 characters max. | Nominal | Open | High | Simon / Kathryn |  |  | 18/03/2016
70 | Design guidelines. Consistency of signposts – buttons – all in one place etc. | Nominal | Open | Medium | Simon / Kathryn |  |  | 18/03/2016
71 | Variant page – need to see main variant in related product section | Nominal | Open | Medium | Simon / Kathryn |  |  | 18/03/2016
72 | Remove Tax Rate field when setting up offering | Nominal | Open | Medium | Simon / Kathryn |  |  | 18/03/2016
73 | “DFCDF” - remove from offering details | Nominal | Open | Medium | Simon / Kathryn |  |  | 18/03/2016
74 | Price lists – default settings – default to existing chosen prices without searching | Nominal | Open | Medium | Simon / Kathryn |  |  | 18/03/2016
75 | After creating a new product the initial catalogue si category will be reset on enterign for the first time in draft mode |  | Open | Medium | Geani |  |  | 18/03/2016
76 | Offering price list are displayed only for the default (first) channel |  | Open | High | Geani |  |  | 18/03/2016
77 | Prices should have 2 decimals format (DB constraint) |  | Open | Medium | Bogdan
78 | VAT should be set in PIM for each shop |  | To Test | Medium | Bogdan | Gowthami | See Bug ID 43 (Web Page Bug List)
79 | Menu navigation is displaying wrong section - Please see Jira SAB-499 screenshot |  | Open | Medium |  |  |  | 29/03/2016
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149

## PIM Screenshots
Bug ID
Bug Id 1
Bug ID 37
Bug ID 56
Bug ID 57

## OMS Bug List
SABRE 2.0 - OMS BUG LIST
BUG ID | BUG Description | Nominal / Readiness | Status | Priority | Raised By / Tester | Dev. owner | Comments | Date discovered | Date closed
1 | OMS to PIM links – must work. PIM to OMS links – Simon T | Nominal | Open | Medium | Simon / Kathryn |  |  | 18/03/2016
2 | centre aligned from all columns | Nominal | Open | Medium | Simon / Kathryn |  |  | 18/03/2016
3 | Make sure formats of lightboxes consistent across all modules | Nominal | Open | Medium | Simon / Kathryn |  |  | 18/03/2016
4 | Consistency of download icons across all modules (ie. Excel, PDF) | Nominal | Open | Medium | Simon / Kathryn |  |  | 18/03/2016
5 | Brandpath favicons not consistent across all modules | Nominal | Open | Medium | Simon / Kathryn |  |  | 18/03/2016
6 | Mapping of Samsung codes to Tetra codes – 20 characters max. | Nominal | Open | High | Simon / Kathryn |  |  | 18/03/2016
7 | Design guidelines. Consistency of signposts – buttons – all in one place etc. | Nominal | Open | Medium | Simon / Kathryn |  |  | 18/03/2016
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149

## OMS Screenshots
Bug ID

## Clean BUG list teamplate (hidden)
SABRE 2.0 - BUG LIST
BUG ID | BUG Description | Nominal / Readiness | Status | Priority | Raised By / Tester | Dev. owner | Comments | Date discovered | Date closed
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149

## Clean Screenshots Template (hidden)
Bug ID