## Dashboard
Test Details |  |  |  |  | PayPal Test login |  |  |  |  | WorldPay Credit Card
tbc |  |  |  |  | User |  | Password |  |  | Number | Security
[5 empty] | bpc@pj-interactive.ro |  | S1nc1ty0 |  |  | 4444333322221111 | 123
[5 empty] | All - Test cases | Pending | Failed | Passed | Can not Test
[5 empty] | 310 | 11 | 13 | 278 | 4
WEB- Test cases | Pending | Failed | Passed | Can not Test | PIM - Test cases | Pending | Failed | Passed | Can not Test | OMS Test cases | Pending | Failed | Passed | Can not Test
70 | 1 | 6 | 61 | 2 | 83 | 1 | 5 | 77 | 0 | 22 | 2 | 0 | 20 | 0
System Integration - Test cases | Pending | Failed | Passed | Can not Test | End to End - Test cases | Pending | Failed | Passed | Can not Test | Offline Order Flow- Test cases | Pending | Failed | Passed | Can not Test
34 | 4 | 1 | 24 | 5 | 22 | 2 | 0 | 20 | 0 | 46 | 0 | 1 | 45 | 1
ERP - Test cases | Pending | Failed | Passed | Can not Test | Customer Service - Test cases | Pending+Retest | Failed | Passed | Can not Test
4 | 1 | 0 | 3 | 0 | 41 | 12 | 0 | 28 | 1

## Order Flow TestCases (1) (hidden)
` |  | Sabre 2.0 - Offline Order Flow TestCases
No |  | Test case | Condition | Expected Result | Pass/Fail | Actual Result | Comments
Fraud Check = Rejected
1
| I | Fraud Check = rejected |  | Order cancel | Not Runned |  | N/A at this moment 13-07-2016
Fraud Check = Approved
PayPall
2
| I | Fraud Check = Approved |  | Go to stock check | Passed |  | SUK01LT-OSXR-RJUK / H771652
| II | Stock check = Awaiting stock |  | Go to Back order Processing | Failed | Stuck at "Awaitting stock | SUK01FC-TCMX-OAKI
| III | Stock check = Stock Available |  | Go to Payment capture | Passed |  | SUK01LT-OSXR-RJUK / H771652
| IV | Payment capture = rejected |  | Order cancel | Not Runned
| V | Payment capture = taken |  | Order dispatch (ERP) | Passed |  | SUK01LT-OSXR-RJUK / H771652
| VI | Order dispatch = Canceled, rejected |  | Order cancel | Passed |  | SUK01DR-AVPD-TTOE
| VII | Order dispatch = Accepted |  | Order Processing (EDI) | Passed |  | SUK01LT-OSXR-RJUK / H771652
| VIII | Order Processing (EDI) = completed |  | Order Completed | Passed |  | SUK01LT-OSXR-RJUK / H771652
WorldPay
3
| I | Fraud Check = Approved |  | Go to stock check | Passed |  | SUK01II-IOQA-GYOT
| II | Stock check = Awaiting stock |  | Go to Back order Processing | Failed | Stuck at "Awaitting stock | SUK01II-IOQA-GYOT
| III | Stock check = Stock Available |  | Go to Payment capture | Passed |  | SUK01SY-NTKE-PRBF
| IV | Payment capture = rejected |  | Order cancel | Not Runned
| V | Payment capture = taken |  | Order dispatch (ERP) | Failed | Payment capture failed | SUK01SY-NTKE-PRBF
| VI | Order dispatch = Canceled, rejected |  | Order cancel | Not Runned
| VII | Order dispatch = Accepted |  | Order Processing (EDI) | Not Runned
| VIII | Order Processing (EDI) = completed |  | Order Completed | Not Runned
Bank transfer
4
| I | Fraud Check = Approved |  | Go to stock check | Passed |  | SUK01XM-JOLP-SCHQ
| II | Stock check = Awaiting stock |  | Go to Back order Processing | Not Runned
| III | Stock check = Stock Available |  | Go to Payment capture | Failed | Stuck at "Payment capture" | SUK01XM-JOLP-SCHQ
| IV | Payment capture = rejected |  | Order cancel | Not Runned
| V | Payment capture = taken |  | Order dispatch (ERP) | Not Runned
| VI | Order dispatch = Canceled, rejected |  | Order cancel | Not Runned
| VII | Order dispatch = Accepted |  | Order Processing (EDI) | Not Runned
| VIII | Order Processing (EDI) = completed |  | Order Completed | Not Runned
Advance Test cases
5
| I | Bundle with one product out of stock |  | Order should start "Awaiting stock" flow | Not Runned
| II | Order with different delivery type |  | Order should behave normaly | Not Runned
| III | Order with voucher per order |  | Order should behave normaly | Not Runned
| IV | Order with voucher per product |  | Order should behave normaly | Passed |  | SUK01ZG-DHUT-PWVO / H771655
| V | Fraud check - uncheck "Same as shipping address" |  | Order should be approved manually | Passed
| VI | Select One payment option, go back and select other payment optiion |  | Order should behave normaly | Failed | Payment capture failed | SUK01SY-NTKE-PRBF
| VII |  |  |  | Not Runned
| VIII |  |  |  | Not Runned
DRAFT

## WEB-Test Cases
Sabre 2.0 - Test Cases
Feature |  | Live URL |  |  | Test URL
Web Module |  | https://shop.samsung.com/uk/ |  |  | https://sabtst.brandpath.net/
No | Content | No | Test case | Condition | Expected Result | Pass/Fail | Actual Result / Bugs | Comments | Automated | Date
1 | Website Customer Journey through to Payment and Fulfilment | Service | Customer journey
|  | Function | Customer completes journey
|  | 1 | Customer arrive at SHOP home page via a number of routes |  | Home page is displayed | Passed |  |  | Available | 2016-09-14
|  | 3 | Customer navigates via shop navigation menu (black) |  | Customer can navigate via shop navigation menu | Passed |  |  | Available | 2016-09-14
|  | 4 | Menu links takes customer to Category Listing Page |  | Category Listing Page is displayed | Passed |  |  | Available | 2016-09-14
|  | 5 | Customer adjust filters |  | Listing Page is updated according to selected filters | Passed |  |  | Available | 2016-09-14
|  | 6 | Customer selects a product |  | Quick view is displayed containg prices, availalbe bundels and option to see full PDP page. | Passed |  |  | Available | 2016-09-14
|  | 7 | Customer clicks "Add to basket" button |  | Product is added to basket, the small basket icon is updated and popup with compatible accessory is displayed. | Passed |  |  | Available | 2016-09-14
|  | 8 | Customer reaches Basket page |  | Basket Page is displayed | Passed |  |  | Available | 2016-09-14
|  | 9 | Customer reaches Checkout page |  | Checkout and payment process begins | Passed |  |  | Available | 2016-09-14
2 | Home Page | Service | Home page
|  | Function | Home page functionality
|  | 1 | Customer navigates through Key promotion area |  | Key promotion area are displayed and work as intended | Failed |  | Constantly updated. Mostly hard coded |  | 2016-09-14
|  | 2 | Customer navigates through access to key journeys |  | Access to key journeys redirects to the intended pages | Failed |  | Constantly updated. Mostly hard coded |  | 2016-09-14
|  | 3 | Customer clicks on promoted products. |  | Promoted products are displayed correctly on home page. Customer is redirected to Promoted product details page. | Failed |  | Constantly updated. Mostly hard coded |  | 2016-09-14
3 | Header, footer and menu navigation | Service | Navigation
|  | Function | Header, footer and menu navigation
|  | 1 | Customer navigates through Header White bar, with blue (controlled by Samsung HQ) |  | Link to basket; basket integration with samsung.com and mini-basket, reflecting any basket updates across both sites as navigating. Link to login/log out; SSON for Samsung accounts. This information needs to feed across to the Shop when customers sign in from Samsung .com site and update across both sites as the user navigates. | Passed |  |  |  | 2016-09-14
|  | 2 | Customer navigates through Header Blue bar, with white text (controlled by Samsung HQ) |  | Search box, both within the header and footer areas of the site are Samsung .com functions and do not perform or show results for the shop site. Once actioned the user is taken to the .com site for resultant search screen. | Passed |  |  |  | 2016-09-14
|  | 3 | Customer navigates through Header Black bar, with white text (controlled by Brandpath) |  | Menu bar (3) is always visible on the page, throughout page navigation and scrolling. The Samsung controlled bars (1 and 2) remain fixed at the top of every page and disappear when the page is scrolled beyond the existing visible screen. | Passed |  |  | Available | 2016-09-14
|  | 4 | Customer navigates through Footer |  | The bottom most area of the footer contains a page link ‘Back to top’ to aid quick navigation. Static information displays; - Copyright and Rights Reserved notice - Website viewing recommendation for browser selection (Those tested) - The footer will contain key information links (e.g. privacy policy, terms and conditions etc.) and also contain logos to key accreditation/appointment as per existing. | Passed |  |  |  | 2016-09-14
4 | Category, Product Listing and Filter Options | Service | Product Listing Page
|  | Function | Category, Product Listing and Filter Options
|  | 1 | Customer selects category from home page |  | Category is displayed on homepage and redirects customer to according product listing page. | Passed |  |  | Available | 2016-09-14
|  | 2 | Customer arrives at product listing page |  | Products and filters are displayed (product listing pages are currently formatted to display a maximum of 3 tiles (Products) wide across the site and is not currently dependent on type of product) Shows key information to entice the customer to either view more details, or purchase the item (e.g. product image, name, price and teaser description) | Passed |  |  | Available | 2016-09-14
|  | 3 | Customer selects filter options |  | Product listing page is updated according to filters selected. Can be easily added or removed. Are dependent upon the product types that are in the search. Only see filter options which have matching products TV AV has additional filters. | Passed |  |  | Available | 2016-09-14
|  | 4 | Customer selected preview color, variant option |  | Product preview image is updated according to color, variant option selected | Passed |  |  |  | 2016-09-14
|  | 5 | Customer selects "Offers available" (if available) |  | Popup with available bundles is displayed and bundles details. Customer is able to "Add to basket" or open PDP of the bundles. | Failed |  | SAB-2264 |  | 2016-09-14
|  | 6 | Customer selected "More details" |  | Customer is redirected to PDP of the product | Passed |  |  |  | 2016-09-14
|  | 7 | Customer selected "Quick view" |  | Popup with product details, variant option and available bundles is displayed. Customer is able to add to basket, open PDP of the product or add to basket/open PDP of available bundle. | Passed |  |  |  | 2016-09-14
5 | Product/Bundle Details | Service | Product/Bundle Details
|  | Function | Product/Bundle Details page functionality
|  | 1 | Customer arrives at product/bundle details page (PDP) |  | PDP page is displayed correctly with all required information | Passed |  |  | Available | 2016-09-14
|  | 2 | Customer selects desired color or variant option (if available) |  | Product image is updated to the selected color or variant option | Passed |  |  |  | 2016-08-16
|  | 3 | Customer navigates through images |  | Images are changed when pressing on "<" ">" | Passed |  |  |  | 2016-09-14
|  | 4 | Customer clicks on navigation buttons (Features, Tech specs..) |  | Customer is redirected to the page section of the selected button | Passed |  |  |  | 2016-09-14
|  | 5 | Customer clicks "Add to basket" button (if available) |  | PopUp message appears with option with selected Color, memory, price, "See basket" button, "Compatible accessory" options are displayed (if available) | Passed |  |  | Available | 2016-09-14
|  | 6 | Customer clicks "Add to basket" from "Compatible accessory" |  | PopUp message appears with option with selected Color, memory, price, "See basket" button, "Compatible accessory" options are displayed (if available) | Passed |  |  |  | 2016-09-14
|  | 7 | Customer presses on "Compatible accessory" |  | Quickview of the compatible accessory is displayed | Passed |  |  |  | 2016-08-16
|  | 9 | Support section functionality |  | Customer is able to download manual, firmware updates, sending messages to support team | Passed |  |  |  | 2016-09-14
|  | 10 | PDP Header |  | While scrolling the page and PDP header will remain displayed with product name, price, "Add to basket" button, and navigation buttons to various sections of the PDP (Features, Tech specs..) | Passed |  |  |  | 2016-09-14
6 | Shopping Basket | Service | Shopping Basket
|  | Function | Shopping Basket and Mini Basket functionality
|  | 1 | Mini basket |  | Mini basket can be accessed from anywhere and the product counter is updated automatically when a new product is added. | Passed |  |  |  | 2016-09-14
|  | 2 | Customer clicks mini basket |  | A list of the selected products is displayed with color select, quantity, price. The list also contain button to remove items, total price and "Go to checkout" button. | Passed |  |  |  | 2016-09-14
|  | 3 | Customer clicks product name |  | Customer is redirected to PDP | Passed |  |  |  | 2016-09-14
|  | 4 | Customer clicks "Remove" button |  | Product is removed | Passed |  |  |  | 2016-09-14
|  | 5 | Customer clicks "Go to basket" from mini basket |  | Customer is redirected to the Upsell page | Passed |  |  |  | 2016-09-14
|  | 6 | Customer clicks "Go to checkout" from mini basket |  | Customer is redirected to checkout page Second step is highlighted | Passed |  |  |  | 2016-09-14
|  | 7 | Customer arrives at shopping basket |  | Shopping basket is displayed and first step is highlighted Payment options are displayed. Option to remove or increase quantity. Delivery packs are displayed. Option to add voucher is displayed. | Passed |  |  | Available | 2016-09-14
|  | 8 | Customer Increase Quantity |  | The Quantity is increased. Product total price is updated. Basket total price is updated. | Passed |  |  |  | 2016-09-14
|  | 9 | Customer removes product |  | Product is removed from basket Basket total price is updated | Passed |  |  |  | 2016-09-14
|  | 10 | Customer adds voucher |  | If wrong voucher then error message is displayed If valid voucher confirmation message is displayed and basket is updated. | Passed |  |  | Available | 2016-09-14
|  | 11 | Customer is able to select payment option |  | Customer select payment option, and after checkout is redirected to the selected payment option | Passed |  |  | Available | 2016-09-14
|  | 12 | Customer selects "Checkout" |  | Customer is redirected to checkout page Second step is highlighted | Passed |  |  | Available | 2016-09-14
7 | Checkout | Service | Checkout
|  | Function | Checkout page functionality
|  | 1 | Customer arrives on checkout page |  | Billing Details fields are displayed Billing Address fields are displayed Basket summary is displayed Option to place order is displayed. | Passed |  |  | Available | 2016-09-14
|  | 2 | Search address by postcode | Checkout page | Start to input post code, system search starts automatically to search for address based on postcode | Passed
|  | 3 | Customer try to place order with incomplete fields AND/OR Terms and Conditions unchecked |  | Notification message appear "This field is required." AND/OR "Please accept our Terms and Conditions before placing your order" | Passed |  |  |  | 2016-09-14
|  | 4 | Customer selects "Deliver to a different address:" |  | New fields are opened and customer can complete them | Passed |  |  | Available | 2016-09-14
8 | Payment | Service | Payment
|  | Function | Payment functionality
|  | 1 | Customer presses "Proceed to checkout" button from "Checkout page" |  | Customer is redirected to the selected payment flow | Passed |  |  | Available | 2016-09-14
|  | 2 | Customer selects Credit card option |  | Popup with credit card input fields are displayed | Passed |  |  | Available | 2016-09-14
|  | 3 | Customer inputs credit card data |  | Credit card type is automatically selected and validation is initiated | Passed |  |  | Available | 2016-09-14
|  | 4 | Customer selects PayPal payment |  | Customer is redirected cu PayPal page for payment details | Passed |  |  | Available | 2016-09-14
|  | 6 | Customer selects Bank transfer |  | Order number and bank details information are displayed. Button to complete order is present. | Passed |  |  |  | 2016-09-14
9 | Order Confirmation Page | Service | Order Confirmation Page
|  | Function | Order Confirmation Page functionality
|  | 1 | Customer arrives at order Confirmation Page |  | Order reference number Confirmation of email address that this reference has been sent to Customer Services contact information, including mail link Order Tracking link is provided Link to continue shopping | Passed |  |  | Available | 2016-09-14
|  | Service | Order Confirmation Page
|  | Function | Order Tracking
|  | 1 | Customer open order tracking page | This page is displayed initially via link on Order Confirmation page and subsequently can be revisited anytime via link received in the Order Confirmation email | Order status and details is displayed and other relevant informations | Passed |  |  |  | 2016-09-14
10 | Static Content/Information Pages | Service | Static Content/Information Pages
|  | Function | Static Content/Information Pages
|  | 1 | Customer arrives at Static Content/Information Page (e.g. about us, terms and conditions) |  | Static Content/Information Page (e.g. about us, terms and conditions) contains necessary information | Passed |  |  |  | 2016-09-14
11 | FAQ | Service | FAQ
|  | Function | FAQ page content
|  | 1 | Customer arrives at FAQ page |  | FAQ page contains all necessary informations | Passed |  |  |  | 2016-09-14
12 | Site Map | Service | Site Map
|  | Function | Site Map content
|  | 1 | Customer arrives at Site Map page | Existing site map links to Samsung .com and currently has no functionality across this site, the page is Static HTML | Site Map page links redirects to the intended page | Passed |  |  |  | 2016-09-14
13 | Site Analytics Integration | Service | Site Analytics Integration
|  | Function | Site Analytics Integration
|  | 1 | Verify that source code is present on page |  |  | Passed |  | analytics.js present on "Network" browser console |  | 2016-09-14
14 | Vouchers / Promotional Codes | Service | Vouchers / Promotional Codes
|  | Function | Vouchers / Promotional Codes functionality
|  | 1 | Customer adds valid voucher |  | The price is reduced according to voucher | Passed |  |  | Available | 2016-09-14
|  | 2 | Customer adds invalid voucher |  | Error message appear informing the voucher is invalid | Passed |  |  |  | 2016-09-14
|  | 3 | Customer adds expired voucher |  | Error message appears informing the voucher is invalid | Passed |  |  |  | 2016-09-14
|  | 4 | Customer adds special condition voucher (E.g. a voucher code for 10% off all baskets greater than £50 in value) |  | If special condition is not met, error message appear informing that special condition is not met | Passed |  |  | Available | 2016-09-14
15 | Requirement Specifications: Generic | Service | Requirement Specifications: Generic
|  | Function | Cross browser compatibility
|  | 1 | Cross browser compatibility testing : - Latest editions of Safari - Internet Explorer 9 and up. - Latest editions of Firefox - Latest editions of Chrome |  |  | Failed |  |  |  | 2016-08-16
|  | Service | Requirement Specifications: Generic
|  | Function | Mobile compatibility
|  | 1 | Mobile compatibility testing - Responsive design - Android 4.1 OS and later - Multiple mobile devices (tbd) |  |  | Failed |  |  |  | 2016-08-16
16 | Delivery, Installation options | Service | Delivery, Installation options
|  | Function | Delivery, Installation options
|  | 1 | TV installation |  | Adding TV product to basket, will activate "TV installation delivery option" | Passed |  |  |  | 2016-09-14
|  | 2 | Wet installation |  | Adding Washing machine product to basket, will activate "Wet installation" delivery option | Passed |  |  |  | 2016-09-14
|  | 3 | Panther delivery |  | Adding heavy goods to the basket, will activated "Panther delivery" option Adding both TV and washing machine, will disable individual options, and activate Panther delivery. | Passed |  |  |  | 2016-09-14
17 | Product out of stock | Service | Product out of stock
|  | Function | Product out of stock
|  | 1 | Product out of stock |  | Add to basket button not available. Order can't be placed | Can not test |  | SOM not completed |  | 2016-08-17
|  | 2 | Bundle with one or more products out of stock |  | Add to basket button not available. Order can't be placed | Can not test |  | SOM not completed |  | 2016-08-17
18 | Regression Testing | Service | Regression Testing
|  | Function | Regression Testing
|  | 1 | Regression Testing |  | Regression Testing | Pending

## PIM - Test Cases
Sabre 2.0 - Test Cases
Feature |  | Live URL |  |  | Test URL
PIM |  | tbc |  |  | https://sabtstpim.brandpath.net/pim-web/
No | Content | No | Test case | Condition | Expected Result | Pass/Fail | Actual Result / Bugs | Comments | Automated | Date
1 | UK Sales Channel | Service | UK Sales Channel
|  | Function | UK Sales Channel
|  | 1 | The administrator can associate products (offerings, product versions and product variants) or product bundles to a specific channel. |  | Products are associated to specific channel. | Passed |  |  | Available | 2016-09-14
|  | 2 | The administrator can price differently the products or product bundles for different channels. |  | Price are assigned differently for specific channel. | Passed |  |  |  | 2016-09-14
2 | Product Catalogues | Service | Product Catalogues
|  | Function | Product Catalogues functionality
|  | 1 | Administrator arrives at Product catalogues page |  | List of catalogues is displayed | Passed |  |  |  | 2016-09-14
|  | 2 | Administrator selects edit |  | Edit form is displayed | Passed |  |  |  | 2016-09-14
|  | 3 | Administrator makes changes and presses cancel |  | No changes are saved | Passed |  |  |  | 2016-09-14
|  | 4 | Administrator makes changes and presses save |  | Changes are saved | Passed |  |  |  | 2016-09-14
|  | 5 | Administrator selects delete/retired |  | Catalogue status changes to "deleted"/"retired" | Passed |  |  |  | 2016-09-14
|  | 6 | Administrator selects "Add" |  | Catalogue creation form is displayed. Pressing "Save" will save the catalogue) | Passed |  |  |  | 2016-09-14
4 | Product Properties | Service | Product Properties
|  | Function | Product Properties functionality
|  | 1 | Administrator arrives at Product property page |  | List of product properties is displayed | Passed |  |  |  | 2016-09-14
|  | 2 | Administrator selects edit |  | Edit form is displayed | Passed |  |  |  | 2016-09-14
|  | 3 | Administrator makes changes and presses cancel |  | No changes are saved | Passed |  |  |  | 2016-09-14
|  | 4 | Administrator makes changes and presses save |  | Changes are saved | Passed |  |  |  | 2016-09-14
|  | 5 | Administrator selects delete/retired |  | Property status changes to "deleted"/"retired" | Passed |  |  |  | 2016-09-14
|  | 6 | Administrator selects "Add" |  | Property creation form is displayed. Pressing "Save" will save the catalogue) | Passed |  |  |  | 2016-09-14
5 | Product lifecycle | Service | Product lifecycle
|  | Function | Product lifecycle process
|  | 1 | Create a product |  | Product is created | Passed |  |  | Available | 2016-09-14
|  | 2 | Add details for a product |  | Details of product are saved | Passed |  |  | Available | 2016-09-14
|  | 3 | Publish a product |  | Product is published | Passed |  |  | Available | 2016-09-14
|  | 4 | Remove/retire a product |  | Product is removed/retired | Failed | sab-2698 |  |  | 2016-09-14
|  | Service | Product lifecycle
|  | Function | Product Creation functionality
|  | 1 | Administrator arrives at product listing page |  | Product listing page is displayed | Passed |  |  | Available | 2016-09-14
|  | 2 | Administrator selects "Add" from product listing page |  | Product creation form is displayed | Passed |  |  | Available | 2016-09-14
|  | 3 | Form is completed and "save" option is selected |  | Product is created in Draft mode | Passed |  |  | Available | 2016-09-14
|  | 4 | Administrator presses "edit" |  | Draft enter in "in progress" status and fields become editable | Passed |  |  | Available | 2016-09-14
|  | 5 | Administrator adds all details/assets and presses "SAVE" |  | Property are updated and saved, and product goes in draft state | Passed |  |  | Available | 2016-09-14
|  | 6 | Administrator presses "publish" |  | Product is published. | Passed |  |  | Available | 2016-09-14
|  | 7 | Edit/Remove assets after publish |  | Edit/Remove assets after publish | Failed | SAB-1593 |  |  | 2016-09-14
|  | Service | Product lifecycle
|  | Function | Product Creation Validation functionality
|  | 1 | Administrator leaves one or more fields empty and presses "Publish" |  | Validation errors appear, informing what fields left empty, and the product is left in draft mode. | Passed |  |  |  | 2016-09-14
|  | 2 | Validation that a duplicate product is not already created |  | Duplicate product should not be created (i.e. an identical product, rather than one creating for cloning for variants or bundling purposes). | Passed |  |  |  | 2016-09-14
|  | Service | Product lifecycle
|  | Function | Price list functionality
|  | 1 | Administrator arrives at Price List page |  | List of prices is displayed | Passed |  |  |  | 2016-09-14
|  | 2 | Administrator selects view |  | Price details form is displayed | Passed |  |  |  | 2016-09-14
|  | 3 | Administrator makes changes and presses back |  | No changes are saved | Passed |  |  |  | 2016-09-14
|  | 4 | Administrator selects deactivate |  | Price list status changes to "inactive" | Passed |  |  |  | 2016-09-14
|  | 5 | Administrator selects retire |  | Price list status changes to "retired" | Passed |  |  |  | 2016-09-14
|  | 6 | Administrator selects clone |  | Price list is cloned | Passed |  |  |  | 2016-09-14
|  | 7 | Administrator selects edit |  | Price list enters in edit mode | Passed |  |  |  | 2016-09-14
|  | 8 | Administrator makes changes and presses save |  | Changes are saved | Passed |  |  |  | 2016-09-14
|  | 9 | Administrator selects "Add" |  | Price listing creation form is displayed. Pressing "Save" will save the price list | Passed |  |  |  | 2016-09-14
|  | 10 | Administrator opens Price list details tab |  | Price list details are displayed along with assigned offerings | Passed |  |  |  | 2016-09-14
|  | 11 | Administrator selects an assigned offering |  | Administrator is redirected to offering details page | Passed |  |  |  | 2016-09-14
|  | Service | Product lifecycle
|  | Function | Offerings creation
|  | 1 | Administrator arrives at offerings listing page |  | Offerings listing page is displayed | Passed |  |  | Available | 2016-09-14
|  | 2 | Administrator selects "Add" from offerings listing page |  | Offerings creation form is displayed | Passed |  |  | Available | 2016-09-14
|  | 3 | Form is completed and "save" option is selected |  | Offering is created in Draft mode | Passed |  |  | Available | 2016-09-14
|  | 4 | Administrator presses "edit" |  | Draft enter in "in progress" status and fields becomes editable | Failed | SAB-1876 |  | Available | 2016-09-14
|  | 5 | Administrator adds all details(including promo label, promo stamp, bundle grade(if availalbe), firnedly URL)/asset's/price and presses "SAVE" |  | Property are updated and saved, and offering goes in draft state | Passed |  |  | Available | 2016-09-14
|  | 6 | Administrator presses "publish" |  | Offering is published. | Passed |  |  | Available | 2016-09-14
6 | Search Products | Service | Search Products
|  | Function | Search Products functionality
|  | 1 | Administrator selects filter and selects "search" |  | Product listing is updated according to selected filter | Passed |  |  | Available | 2016-09-14
7 | Free of Charge Products | Service | Free of Charge Products
|  | Function | Free of Charge Products creation
|  | 1 | Administrator creates FOC product/offering |  | FOC product is created | Passed |  |  | Available | 2016-09-14
|  | 2 | FOC product is displayed through the marketing campaign |  | FOC product is displayed through the marketing campaign | Passed |  |  |  | 2016-09-14
8 | Product Variants | Service | Product Variant
|  | Function | Product Variant creation
|  | 1 | Administrator goes to product details, variants products tab |  | Product variant are displayed (if exists) and option to assign or create new variant is present | Passed |  |  | Available | 2016-09-14
|  | 2 | Administrator try to create variant when product is in published mode |  | ERROR YOU MUST CREATE A DRAFT VERSION OF THE CURRENT PRODUCT. | Passed |  |  |  | 2016-09-14
|  | 3 | Administrator creates draft, and try to create variant again |  | Variant creation form appears with Name, Base Name, sku code and variant option | Passed |  |  |  | 2016-09-14
|  | 4 | Administrator selects "create" |  | Product variant is created in draft mode | Passed |  |  | Available | 2016-09-14
|  | Service | Product Variant
|  | Function | Offering Variant creation
|  | 1 | Administrator goes to offering details, variants tab |  | Offering variant are displayed (if exists) and option to assign or create new variant is present | Passed |  |  | Available | 2016-09-14
|  | 2 | Administrator try to create variant when offerings in published mode |  | ERROR YOU MUST CREATE A DRAFT VERSION OF THE CURRENT OFFERING. | Passed |  |  |  | 2016-09-14
|  | 3 | Administrator try to create variant of an offering with a product without variants |  | ERROR NONE OF THE OFFERING'S PRODUCTS HAS (OTHER) VARIANTS. | Passed |  |  |  | 2016-09-14
|  | 4 | Administrator creates draft, and try to create variant again |  | Variant creation form appears with Name, Base Name, sku code and variant option | Passed |  |  |  | 2016-09-14
|  | 5 | Administrator selects "create" |  | Offering variant is created in draft mode | Passed |  |  | Available | 2016-09-14
9 | Product versions | Service | Product versions
|  | Function | Product versions functionality
|  | 1 | Administrator reaches History tab from product description |  | List of product history is displayed | Passed |  |  |  | 2016-09-14
|  | 2 | Administrator selects view of an product history |  | The product history details page is displayed | Passed |  |  |  | 2016-09-14
|  | 3 | Administrator selects copy |  | A new product draft is created with details from the history product already populated. | Passed |  |  |  | 2016-09-14
10 | Bundles | Service | Bundles
|  | Function | Bundles creation
|  | 1 | Administrator arrives at offerings creation page and selects "Promo bundle" |  | Offering flow is the same as normal offering but with multiple products inside offering | Passed |  |  |  | 2016-09-14
|  | 2 | Upsell offering |  | Offering flow is the same as normal offering but with multiple products inside offering. Additional options in details tab for promotion are present (promo text, promo rosette). | Passed |  |  | Available | 2016-09-14
11 | PDPs (Product Description Pages) | Service | PDPs (Product Description Pages)
|  | Function | PDPs (Product Description Pages)
|  | 1 | PDPs (Product Description Pages) should be hosted on the same platform. |  | All necessary information is displayed in the PDPs. | Passed |  |  |  | 2016-09-14
12 | Vouchers | Service | Vouchers
|  | Function | Vouchers creation
|  | 1 | Administrator arrives at Voucher List page |  | List of vouchers is displayed | Passed |  |  |  | 2016-09-14
|  | 2 | Administrator selects view |  | Voucher details form is displayed | Passed |  |  |  | 2016-09-14
|  | 3 | Administrator selects deactivate |  | Voucher status changes to "inactive" | Passed |  |  |  | 2016-09-14
|  | 4 | Administrator selects delete |  | Voucher status changes to "deleted" | Passed |  |  |  | 2016-09-14
|  | 5 | Administrator makes changes and presses save |  | Changes are saved | Passed |  |  |  | 2016-09-14
|  | 6 | Administrator selects "Add" |  | Voucher creation form is displayed. Pressing "Save" will save the voucher | Passed |  |  |  | 2016-09-14
|  | 7 | Administrator arrives at instances tab |  | List of instances is displayed | Passed |  |  |  | 2016-09-14
|  | 8 | Administrator presses "Generate new" |  | instances creation is displayed | Passed |  |  |  | 2016-09-14
|  | 9 | Form is completed generate is pressed |  | Input number of instances is generated | Passed |  |  |  | 2016-09-14
|  | 10 | Administrator selects one or more instance/instances |  | Option to modify or remove becomes available | Passed |  |  |  | 2016-09-14
|  | 11 | Modify select is pressed |  | Form to modify the selected instances is displayed | Passed |  |  |  | 2016-09-14
|  | 12 | Administration is able to set special rules for voucher |  | Administration is able to set special rules for voucher | Passed |  |  |  | 2016-09-14
|  | 13 | Modification are made and Save button is selected |  | Selected instances are updated | Passed |  |  |  | 2016-09-14
13 | Product Accessories | Service | Product Accessories
|  | Function | Product Accessories functionality
|  | 1 | Administrator can assign/link accessory to products |  | Accessory are assigned to products in the "Related products" tab | Passed |  |  | Available | 2016-09-14
|  | 2 | Administrator can create Product Accessories with specific type (i.e. Car Kits, Controllers, ..) |  |  | Passed |  |  |  | 2016-09-14
14 | Tagging Support | Service | Tagging Support
|  | Function | Tagging Support
|  | 1 | Administrator can create tags/short sku for online channels analtric reporting system can identify products |  |  | Passed |  |  |  | 2016-09-14
15 | Scheduling | Service | Scheduling
|  | Function | Scheduling functionality
|  | 1 | Administrator sets a Scheduling offering price time |  | Offering price is updated according to Scheduling time | Failed | sab-437 |  |  | 2016-09-14
16 | Services | Service | Services
|  | Function | Services functionality
|  | 1 | Administrator can view and filter by service name, service type and other key fields |  |  | Passed |  |  |  | 2016-09-14
|  | 2 | Administrator can map services related to catalogues/categories/products |  |  | Failed |  | Can be created from PIM, but additional setting that must be done are only from DB possible at this moment |  | 2016-09-14
17 | Audit | Service | Audit
|  | Function | Audit
|  | 1 | PIM register actions taken against a product for audit purposes |  |  | Passed |  |  |  | 2016-09-14
18 | Regression Testing | Service | Regression Testing
|  | Function | Regression Testing
|  | 1 | Regression Testing |  |  | Pending

## OMS - Test Cases
Sabre 2.0 - Test Cases
Feature |  | Live URL |  |  | Test URL
OMS |  | tbc |  |  | https://sabtstoms.brandpath.net/oms-web/
No | Content | No | Test case | Condition | Expected Result | Pass/Fail | Actual Result / Bugs | Comments | Automated | Date
1 | Dashboard | Service | Dashboard
|  | Function | Dashboard
|  | 1 | Administrator can see report of orders |  | Created orders appear on OMS dashboard | Passed |  |  |  | 2016-09-14
|  | 2 | Orders are sorted by status on the dashboard |  | Orders are sorted by status on the dashboard | Passed |  |  |  | 2016-09-14
2 | Order searching and filtering | Service | Order searching and filtering
|  | Function | Order searching and filtering
|  | 1 | Administrator can filter order based on the order status |  | Order list is updated according to the filter | Passed |  |  | Available | 2016-09-14
|  | 2 | Administrator can search orders based on reference number |  | Order list is updated according to the filter | Passed |  |  | Available | 2016-09-14
|  | 3 | Administrator can filter orders based on creation date |  | Order list is updated according to the filter | Passed |  |  |  | 2016-09-14
|  | 4 | Administrator can filter orders based on site |  | Order list is updated according to the filter | Passed |  |  | Available | 2016-09-14
|  | 5 | Administrator can filter orders based on client |  | Order list is updated according to the filter | Passed |  |  | Available | 2016-09-14
|  | 6 | Administrator can filter orders based on order type |  | Order list is updated according to the filter | Passed |  |  | Available | 2016-09-14
3 | Order Flows | Service | Order Flows
|  | Function | Order Flows
|  | 1 | PayPal orders start PayPal offline order flow |  | See Offline order flow tab | Passed |  |  | Available | 2016-09-14
|  | 2 | WorldPAy orders start WorldPay offline order flow |  | See Offline order flow tab | Passed |  |  | Available | 2016-09-14
|  | 3 | Bank transfer orders start Bank Transfer offline order flow |  | See Offline order flow tab | Passed |  |  |  | 2016-09-14
4 | Returns / Refund | Service | Returns / Refund
|  | Function | Returns / Refund
|  | 1 | Orders with returns |  | Orders with returns are listied | Passed |  |  |  | 2016-09-14
|  | 2 | Orders with refunds |  | Orders with refunds are listied | Passed |  |  |  | 2016-09-14
|  | 3 | Returns cases |  | Returns cases are listed | Passed |  |  |  | 2016-09-14
|  | 4 | Returns |  | See Offline order flow tab | Pending |  |  |  | 2016-09-14
|  | 5 | Refund |  | See Offline order flow tab | Passed |  |  |  | 2016-09-14
5 | Audit | Service | Audit
|  | Function | Audit
|  | 1 | OMS register actions taken against orders for audit purposes |  |  | Passed |  |  |  | 2016-09-14
6 | Order comments/ Customer communications (emails) | Service | Order comments/ Customer communications (emails)
|  | Function | Order comments/ Customer communications (emails)
|  | 1 | Comments are stored against orders |  |  | Passed |  |  |  | 2016-09-14
7 | Payment confirmation download | Service | Payment confirmation download
|  | Function | Payment confirmation download
|  | 1 | Operator should upload payment confirmation |  | Operator opens order summary and goes to attachments tab and uploads payment confirmation. | Passed
|  | 2 | View/download payment confirmation from save screen |  | View/Download | Passed
8 | Order tracking | Service | Order tracking
|  | Function | Order tracking
|  | 1 | Order tracking link availalbe at order summary tab |  | ORder trackign link visible | Passed
9 | Regression Testing | Service | Regression Testing
|  | Function | Regression Testing
|  | 1 | Regression Testing |  |  | Pending

## Offline Order Flow
Sabre 2.0 - Offline Order Flow Test Cases
No | Test case | Date | Expected Result | Pass/Fail | Actual Result / Status | Comments
Fraud Check = Rejected
1 | Fraud Check = rejected - manual | 2016-07-26 | Order cancel | Passed |  | SUK01TK-SDHE-IHJI - manual reject for WorldPay payment option
2 | Fraud Check = rejected - automatic | 2016-07-26 | Order cancel | Can not test |  | Can't simulate fraud checks in the system
Fraud Check = Approved
PayPal
1 | Fraud Check = Approved | 2016-07-26 | Go to stock check | Passed |  | SUK01WF-ZVJP-VLEO
2 | Stock check = Awaiting stock | 2016-07-26 | Go to Backorder Processing | Passed | Stuck at Awaiting stock | SUK01GH-LQDI-UHLJ / H771798 - manual sent to backorder .. new status "Awaiting Stock ERP" - SAB - 2607,2608,2608,2610 Bugs fixed
3 | Stock check = Rejected, cancel | 2016-07-26 | Cancel Order | Passed | Canceled | SUK01SD-YKYD-ZKDO
4 | Stock check = Stock Available | 2016-07-26 | Go to Payment capture | Passed |  | SUK01WF-ZVJP-VLEO
5 | Payment capture = rejected | 2016-08-12 | Order cancel | Passed |  | Change PayPal transaction ID to an invalid one
6 | Payment capture = taken | 2016-07-26 | Order dispatch (ERP) | Passed |  | SUK01WF-ZVJP-VLEO
7 | Order dispatch = Canceled, rejected | 2016-07-26 | Order cancel | Passed | Delivery cancelled | Progress Tetra order to status 9 (PI/AP) SUK01KA-CVQC-MHGQ / H771796 SAB - 2607,2608,2608,2610 Bugs fixed
8 | Order dispatch = Accepted | 2016-07-26 | Order Processing (EDI) | Passed |  | SUK01WF-ZVJP-VLEO / H771797 Dispatched by Florin Neacsu inside tetra
9 | Order Processing (EDI) = completed | 2016-08-12 | Order Completed | Passed | Completed | SUK01WF-ZVJP-VLEO / H771797
WorldPay
1 | Fraud Check = Approved | 2016-07-26 | Go to stock check | Passed |  | SUK01DK-PNEE-TDZP
2 | Stock check = Awaiting stock | 2016-08-12 | Go to Backorder Processing | Passed | Stuck at Awaiting stock | SUK01TZ-UQFR-XEPM / H771804 - manual sent to backorder .. new status "Awaiting Stock ERP" - SAB - 2607,2608,2608,2610 Bugs fixed
3 | Stock check = Rejected, cancel | 2016-07-26 | Cancel Order | Passed | Canceled | SUK01SA-AROL-GITI
4 | Stock check = Stock Available | 2016-07-26 | Go to Payment capture | Passed |  | SUK01DK-PNEE-TDZP
5 | Payment capture = rejected | 2016-08-12 | Order cancel | Passed |  | Change WorldPay transaction ID to an invalid one
6 | Payment capture = taken | 2016-07-26 | Order dispatch (ERP) | Passed |  | SUK01DK-PNEE-TDZP
7 | Order dispatch = Canceled, rejected | 2016-08-12 | Order cancel | Passed | Delivery cancelled | Progress Tetra order to status 9 (PI/AP) SUK01RQ-HABE-DFLK / H771801 SAB - 2607,2608,2608,2610 Bugs fixed
8 | Order dispatch = Accepted | 2016-07-26 | Order Processing (EDI) | Passed |  | SUK01DK-PNEE-TDZP / H771795 Dispatched by Florin Neacsu inside tetra
9 | Order Processing (EDI) = completed | 2016-07-29 | Order Completed | Passed | Completed | SUK01DK-PNEE-TDZP / H771795 Provisioned by Piotr
Bank transfer
1 | Fraud Check = Approved | 2016-07-26 | Payment pending | Passed |  | SUK01OI-KFDA-NYRN
2 | Payment Rejected | 2016-07-26 | Cancel Order | Passed | Canceled | SUK01ZO-SIRV-PGFM
3 | Payment Accepted | 2016-07-26 | Go to stock check | Passed |  | SUK01OI-KFDA-NYRN
4 | Stock check = Awaiting stock | 2016-07-26 | Go to Backorder Processing | Passed |  | SUK01OI-KFDA-NYRN
5 | Stock check = Rejected, cancel | 2016-07-26 | Cancel Order | Passed | Canceled | SUK01CL-YTXE-SQEK - manual forced refound after status "Payment refund"
6 | Stock check = Stock Available | 2016-07-26 | Go to Payment capture | Passed |  | SUK01OI-KFDA-NYRN
7 | Payment capture = rejected | 2016-08-12 | Order cancel | Passed |  | Waiting for SAB - 2534 and SAB-2438 to be completed
8 | Payment capture = taken | 2016-07-26 | Order dispatch (ERP) | Passed
9 | Order dispatch = Canceled, rejected | 2016-08-12 | Order cancel | Passed | Delivery cancelled | SUK01NU-TXBH-DJJU / H771806 SAB - 2607,2608,2608,2610 Bugs fixed
10 | Order dispatch = Accepted | 2016-07-26 | Order Processing (EDI) | Passed |  | SUK01OI-KFDA-NYRN / H771800 Dispatched by Florin Neacsu inside tetra
11 | Order Processing (EDI) = completed | 2016-08-12 | Order Completed | Passed | Completed | SUK01OI-KFDA-NYRN / H771800
Advanced Test cases
1 | Order with voucher per order | 2016-07-26 | Order should behave normally | Passed | Completed | SUK01QB-SSDE-DUHF / H771805 Dispatched by Florin Neacsu inside tetra
2 | Order with voucher per product | 2016-07-26 | Order should behave normally | Passed | Pick Packed | SUK01TY-TUZJ-FJEA / H771807 Dispatched by Florin Neacsu inside tetra Order got stuck in tetra because of a product had serial set to it and at the dispatch moment the no serials were available. WW10H9600EX/EU
3 | Fraud check - uncheck "Same as shipping address" | 2016-07-26 | Order should be approved manually | Passed |  | SUK01OH-EIFF-RLEI
4 | Select WorldPay, reach WorldPay credit information popup, go back and finish payment with PayPal | 2016-07-26 | Order should behave normally | Passed |  | SUK01KA-CVQC-MHGQ
5 | Select PayPal reach PayPal login information, go back and finish payment with WorldPay | 2016-07-19 | Order should behave normally | Passed |  | SUK01DK-PNEE-TDZP
6 | Orders with custom delivery type ( Smart TV Installation service: Free Standing) | 2016-07-26 | Order should behave normally | Passed | Stock Allocated | SUK01JD-QNPW-OUTT with DELOTHTVFSTAND - H771824
7 | Orders with custom delivery type (Home Appliances Installation: Wet connection) | 2016-07-26 | Order should behave normally | Passed | Stock Allocated | SUK01SP-SZBU-ENMQ with DELOTHINTWETCON - H771825
8 | Bundles (with stock) | 2016-07-29 | Order should behave normally | Passed | Completed | SUK01ZU-IHOU-MDPN / H771830
9 | Orders with huge quantity | 2016-07-29 | Order should behave normally | Passed | Completed | SUK01ZU-IHOU-MDPN / H771830 20 x Bundle with 2 TV's Initially went to "Awaiting stock ERP" Stock has been increased and order progressed to dispatched inside tetra
10 | Payment not delivered | 2016-08-01 | order must be canceled automatically | Passed |  | SUK01RW-KJDI-GKEK 2016-08-01 09:30 Cancelled CANCELLED oms-ws 2016-08-01 09:30 Pending Cancellation PENDING_CANCELLATION oms-ws 2016-08-01 09:30 Payment Expired PAYMENT_EXPIRED scheduledtask 2016-07-22 13:00 Payment pending PAYMENT_PENDING oms-ws 2016-07-22 13:00 Fraud Check Completed FRAUD_CHECK_COMPLETED oms-ws 2016-07-22 13:00 Fraud Check Started FRAUD_CHECK_STARTED oms-ws 2016-07-22 13:00 Created CREATED
Retuns/Refund Test cases
1 | Check RMA number |  | After order is dispatched/completed, RMA number should be availalbe | Passed
2 | Create Return order in CTS |  | Return order is created in CTS | Failed |  | sab-3081, sab-3101
3 | Check return details in OMS | 2016-09-14 | After return order is created in CTS, details should be availalbe in OMS "Returns" tab. Returns of each item is traced by OMS separately | Passed
4 | Partial refund | 2016-09-14 | If returns are accepted partial refund should be performed | Passed |  | Customer opens order summary and then goes to "Payment" tab. Pressing "+" at the "Refund" section will open refund popup where fillds can be populated
5 | Full refund | 2016-09-14 | If returns are accepted full refund should be performed | Passed |  | Customer opens order summary and then goes to "Payment" tab. Pressing "+" at the "Refund" section will open refund popup where fillds can be populated.
6 | Check order tracking for retun/refund details | 2016-09-14 | Order tracking page should be updated for returns/refund details | Passed

## ERP - Test Cases
Sabre 2.0 - Test Cases
Feature |  | Live URL |  |  | Test URL
ERP |  | tbc |  |  | https://sagetest.secureselect.net/webclient/en-gb/HTMLLaunch.asp?SES_PRODUCT=webclient&SES_CONNECTION=camaro
No | Content | No | Test case | Condition | Expected Result | Pass/Fail | Actual Result / Bugs | Comments | Date
1 | Requirement Specifications: Generic | Service | Requirement Specifications: Generic
|  | Function | Requirement Specifications: Generic
|  | 1 | Check order create status |  | Valid orders should be created on ERP | Passed |  |  | 2016-09-14
|  | 2 | Check product created |  | PIM created products should be created in ERP | Passed |  |  | 2016-09-14
|  | 3 | Check product and order informations |  | Administrator can manually check order details and product stock | Passed |  |  | 2016-08-18
2 | Regression Testing | Service | Regression Testing
|  | Function | Regression Testing
|  | 1 | Regression Testing |  |  | Pending

## Order Flow TestCases (hidden)
` |  | Sabre 2.0 - Offline Order Flow TestCases
No |  | Test case | Condition | Expected Result | Pass/Fail | Actual Result | Comments
Fraud Check = Rejected
1
| I | Fraud Check = rejected |  | Order cancel | Not Runned |  | N/A at this moment 13-07-2016
Fraud Check = Approved
PayPall
2
| I | Fraud Check = Approved |  | Go to stock check | Passed |  | SUK01LT-OSXR-RJUK / H771652
| II | Stock check = Awaiting stock |  | Go to Back order Processing | Failed | Stuck at "Awaitting stock | SUK01FC-TCMX-OAKI
| III | Stock check = Stock Available |  | Go to Payment capture | Passed |  | SUK01LT-OSXR-RJUK / H771652
| IV | Payment capture = rejected |  | Order cancel | Not Runned
| V | Payment capture = taken |  | Order dispatch (ERP) | Passed |  | SUK01LT-OSXR-RJUK / H771652
| VI | Order dispatch = Canceled, rejected |  | Order cancel | Passed |  | SUK01DR-AVPD-TTOE
| VII | Order dispatch = Accepted |  | Order Processing (EDI) | Passed |  | SUK01LT-OSXR-RJUK / H771652
| VIII | Order Processing (EDI) = completed |  | Order Completed | Passed |  | SUK01LT-OSXR-RJUK / H771652
WorldPay
3
| I | Fraud Check = Approved |  | Go to stock check | Passed |  | SUK01II-IOQA-GYOT
| II | Stock check = Awaiting stock |  | Go to Back order Processing | Failed | Stuck at "Awaitting stock | SUK01II-IOQA-GYOT
| III | Stock check = Stock Available |  | Go to Payment capture | Passed |  | SUK01SY-NTKE-PRBF
| IV | Payment capture = rejected |  | Order cancel | Not Runned
| V | Payment capture = taken |  | Order dispatch (ERP) | Failed | Payment capture failed | SUK01SY-NTKE-PRBF
| VI | Order dispatch = Canceled, rejected |  | Order cancel | Not Runned
| VII | Order dispatch = Accepted |  | Order Processing (EDI) | Not Runned
| VIII | Order Processing (EDI) = completed |  | Order Completed | Not Runned
Bank transfer
4
| I | Fraud Check = Approved |  | Go to stock check | Passed |  | SUK01XM-JOLP-SCHQ
| II | Stock check = Awaiting stock |  | Go to Back order Processing | Not Runned
| III | Stock check = Stock Available |  | Go to Payment capture | Failed | Stuck at "Payment capture" | SUK01XM-JOLP-SCHQ
| IV | Payment capture = rejected |  | Order cancel | Not Runned
| V | Payment capture = taken |  | Order dispatch (ERP) | Not Runned
| VI | Order dispatch = Canceled, rejected |  | Order cancel | Not Runned
| VII | Order dispatch = Accepted |  | Order Processing (EDI) | Not Runned
| VIII | Order Processing (EDI) = completed |  | Order Completed | Not Runned
Advance Test cases
5
| I | Bundle with one product out of stock |  | Order should start "Awaiting stock" flow | Not Runned
| II | Order with different delivery type |  | Order should behave normaly | Not Runned
| III | Order with voucher per order |  | Order should behave normaly | Not Runned
| IV | Order with voucher per product |  | Order should behave normaly | Passed |  | SUK01ZG-DHUT-PWVO / H771655
| V | Fraud check - uncheck "Same as shipping address" |  | Order should be approved manually | Passed
| VI | Select One payment option, go back and select other payment optiion |  | Order should behave normaly | Failed | Payment capture failed | SUK01SY-NTKE-PRBF
| VII |  |  |  | Not Runned
| VIII |  |  |  | Not Runned
DRAFT

## System Integration - Test cases
Sabre 2.0 - Test Cases
Feature |  | Live URL |  |  | Test URL
System Integration
No | Content | No | Test case | Condition | Expected Result | Pass/Fail | Actual Result / Bugs | Comments | Automated | Date
1 | System Integration | Function | WEB-PIM integration
|  | 1 | Created offerings inside PIM appear on the web with all related informations |  |  | Passed |  |  | Available | 2016-09-14
|  | 2 | PIM offering/products edits are reflected on the WEB |  |  | Passed |  |  |  | 2016-09-14
|  | 3 | Product,Offering,Voucher,Services details are passed from PIM to WEB |  |  | Passed |  |  | Available | 2016-09-14
|  | 4 | Vouchers information and validations are passed from PIM to the WEB |  |  | Passed |  |  | Available | 2016-09-14
|  | Function | WEB - OMS integration
|  | 1 | Pre-allocate stock |  |  | Passed |  |  |  | 2016-09-14
|  | 2 | Confirm stock reservation |  |  | Passed |  |  |  | 2016-09-14
|  | 3 | Order status sent to Order tracking page |  |  | Passed |  |  | Available | 2016-09-14
|  | 4 | Created orders on the WEB are created inside OMS with same "Reference" number |  |  | Passed |  |  | Available | 2016-09-14
|  | Function | WEB - SOM integration
|  | 1 | Asynchronous stock level data updates |  |  | Can not test |  | SOM not completed
|  | Function | WEB - Pay service integration
|  | 1 | Payment pre-authorization |  |  | Passed |  |  |  | 2016-09-14
|  | Function | PIM - ERP integration
|  | 1 | Created products inside PIM are also created inside ERP |  |  | Passed |  |  | Available | 2016-09-14
|  | 2 | Stock status is sent from ERP to PIM |  |  | Passed |  |  |  | 2016-09-14
|  | Function | OMS-SOM integration
|  | 1 | Stock is soft allocated (short time out) |  |  | Can not test |  | SOM not completed
|  | 2 | Pre-allocate stock (timeout adjustment) |  |  | Can not test |  | SOM not completed
|  | 3 | Pre-allocated stock, Update to sold |  |  | Can not test |  | SOM not completed
|  | Function | OMS-PSM integration
|  | 1 | Capture payment |  |  | Passed |  |  |  | 2016-09-14
|  | Function | OMS-ESOM integration
|  | 1 | Get product stock |  |  | Passed |  |  |  | 2016-09-14
|  | 2 | Create order / Stock allocated |  |  | Passed |  |  |  | 2016-09-14
|  | 3 | Get order status |  |  | Passed |  |  |  | 2016-09-14
|  | 4 | Order and customer information are passed between OMS and ESOM |  |  | Passed |  |  |  | 2016-09-14
|  | Function | ESOM-ERP integration
|  | 1 | Get/Run Product stock |  |  | Passed |  |  |  | 2016-09-14
|  | 2 | Create orders / Save / Modify |  |  | Passed |  |  |  | 2016-09-14
|  | 3 | Order and customer information are passed between ERP and ESOM |  |  | Passed |  |  |  | 2016-09-14
|  | 4 | Allocate stock |  |  | Passed |  |  |  | 2016-09-14
|  | 5 | Get order status |  |  | Passed |  |  |  | 2016-09-14
|  | Function | ESOM-SOM integration
|  | 1 | Stock check (Periodic) |  |  | Can not test |  | SOM not completed
|  | Function | PSM - Pay Service integration
|  | 1 | Capture payment |  |  | Passed |  |  |  | 2016-09-14
|  | Function | ERP - Courier Service integration
|  | 1 | Courier delivery status |  |  | Passed |  |  |  | 2016-09-14
|  | Function | OMS-ERP-SAP
|  | 1 | Send fulfilled order informations to samsung SAP via EDI integration |  |  | Passed |  |  |  | 2016-09-14
|  | Function | CTS-OMS
|  | 1 | Return/Refund info pushed to OMS via Callback API |  |  | Failed | sab-3081, sab-3101 |  |  | 2016-09-26
|  | Function | OMS - Email
|  | 1 | Reports |  |  | Pending
|  | Function | ERP - Email
|  | 1 | Reports |  |  | Pending
|  | Function | Web - Google analytics
|  | 1 | Reports |  |  | Pending
2 | Regression Testing | Service | Regression Testing
|  | Function | Regression Testing
|  |  | Regression Testing |  |  | Pending

## Customer Service
Sabre 2.0 - Test Cases
Feature |  | Live URL |  |  | Test URL
Customer Service |  | tbc |  |  | eCommerce platform : https://sabdev.brandpath.net/ OMS platform: https://sabdevoms.brandpath.net/oms-web/ PayPal sandbox platform: https://www.sandbox.paypal.com/uk/cgi-bin/webscr?cmd=_history
No | Content | No | Test case | Condition | Expected Result | Pass/Fail | Actual Result / Bugs | Comments | Date
1 | Customer Service | 1 | Create order
|  | 1.1 | Create order with Paypal
|  |  | Open eCommerce platform |  | Home page will be displayed | Passed |  |  | 2016-08-30
|  |  | Go to any category (example: Mobiles & wearables) |  | Listing page will be displayed | Passed |  |  | 2016-08-30
|  |  | Press "Add to basket" |  | Popup confirmation will be displayed | Passed |  |  | 2016-08-30
|  |  | Press "See basket" |  | Basket page will be displayed | Passed |  |  | 2016-08-30
|  |  | Select Paypal payment type, then select check box "I understand and agree to the Samsung Terms and Conditions" then press proceed to checkout |  | Login page will be displayed. | Passed |  | Note: PayPal credit not available for testing | 2016-08-30
|  |  | Fill all fields and press checkout |  | Payment journey will start according to selection. Order confirmation received at email filled in Details page (please use your own email). | Passed |  | PayPal : bpc@pj-interactive.ro - S1nc1ty0 Note: This login informations can be used on sandbox platform | 2016-08-30
|  |  | Note order reference number |  | After payment is complete, Thank you Page will be displayed. | Passed |  |  | 2016-08-30
|  | 1.2 | Create order with Worldpay
|  |  | Repeat previous steps and select Worldpay at basket as payment option |  | After payment is complete, Thank you Page will be displayed, confirmation email received - order moves to OMS | Passed |  | WorldPay : 4444333322221111 expire date in the future (not longer than 3 years) any name any CVV2 | 2016-08-30
|  | 1.3 | Create order with Bank Transfer
|  |  | Repeat previous steps and select Bank Transfer at basket as payment option |  | Thank you Page will be displayed, confirmation email received - order moves to OMS | Passed |  |  | 2016-08-30
|  | 2 | Check current status
|  | 2.1 | Search by Order Number
|  |  | Operator goes to "Advanced search" and select filter options, adding order reference |  | Orders list is updated based on filter selections | Passed |  |  | 2016-08-30
|  |  | Operator opens order summary and goes to order history tab |  | Order history operations is displayed. | Passed |  |  | 2016-08-30
|  | 2.2 | Search by Email/Name
|  |  | Operator goes to "Advanced search" and select filter options, adding email/Name , if customer does not remember Order Reference number |  | Orders list is updated based on filter selections | Passed |  |  | 2016-08-30
|  |  | Operator opens order summary and goes to order history tab |  | Order history operations is displayed. | Passed |  |  | 2016-08-30
|  | 3 | Order Validation
|  | 3.1 | Order approve - Complete fraud check
|  |  | PayPal, WorldPay and Bank transfer orders are checked automatically | Same Shipping and Billing address | PayPal, WorldPay and Bank transfer orders to be automatically approved or rejected by fraud check | Out of scope |  |  | 2016-08-30
|  |  | Operator goes to "Order Approval" and select filter options | Different Shipping and Billing address (Bank Transfer orders are skipping this step) | Orders list is updated based on filter selections | Out of scope |  |  | 2016-08-30
|  |  | Press quarantine button |  | Popup with textbox for quarantine message appears. Options to abort or continue approve are present. | Out of scope |  |  | 2016-08-30
|  |  | Press approve button |  | Popup with textbox for approval message appears. Options to abort or continue approve are present. | Out of scope |  |  | 2016-08-30
|  |  | Press reject button |  | Popup with textbox for reject message appears. Options to abort or continue approve are present. | Out of scope |  |  | 2016-08-30
|  | 4 | Order Validation
|  | 4.1 | Managing Bank Transfer Orders
|  |  | Place order on web |  | Order goes to status "Payment pending" | Out of scope |  |  | 2016-08-30
|  |  | Operator goes "Payment handling" inside OMS and search for the order reference and status "Payment Pending" |  | Order is displayed with option to cancel or approve | Out of scope |  |  | 2016-08-30
|  |  | Press "Payment failed" |  | Popup is displayed with option to abort or continue the operation. Text box is also displayed to leave comment for the operation. | Out of scope |  |  | 2016-08-30
|  |  | Press "Payment received" |  | Popup is displayed with option to abort or continue the operation. Text box is also displayed to leave comment for the operation. Order is picked up by automate processes | Out of scope |  |  | 2016-08-30
|  |  | Operator should upload payment confirmation |  | Operator opens order summary and goes to attachments tab and uploads payment confirmation. | Out of scope |  |  | 2016-08-30
|  |  | View/download payment confirmation from save screen |  | View/Download | Retest |  |  | 2016-08-30
|  | 5 | Order Validation
|  | 5.1 | Managing Orders without stock
|  |  | Operator goes to "backorder management" section of OMS |  | Option to search orders by different status is displayed (Awaiting stock, Pre Order, Awaiting stock ERP, Release back order). Orders with "Waiting stock ERP" can be managed inside ERP. Orders with "Release back order" are managed by automated tasks. | Out of scope |  |  | 2016-08-30
|  |  | Operator selects "Reject" | Order status "Awaiting stock" | Popup with option to continue or abort operation is displayed. Textbox to leave comment for the operation is displayed. | Out of scope |  |  | 2016-08-30
|  |  | Operator selects "Release back order" | Order status "Awaiting stock" | Popup with option to continue or abort operation is displayed. Textbox to leave comment for the operation is displayed. Order is sent to "Back order" automate tasks. | Out of scope |  |  | 2016-08-30
|  | 6 | Cancel an order
|  | 6.1 | Bank transfer orders
|  |  | Operator goes to "Payment handling" inside OMS, select relevant status (Payment pending) and search for the order reference |  | Order is displayed with option to cancel or approve | Passed |  |  | 2016-08-30
|  |  | Press "Payment failed" |  | Popup is displayed with option to abort or continue the operation. Text box is also displayed to leave comment for the operation. | Retest |  | Telus note: Please consider an unified search field where order management tools are included, rather than having to find an order in a different section based on current status | 2016-08-30
|  | 6.2 | Orders without stock
|  |  | Operator goes to "backorder management" section of OMS |  | Option to search orders by different status is displayed (Awaiting stock, Pre Order, Awaiting stock ERP, Release back order). Orders with "Waiting stock ERP" can be managed inside ERP. Orders with "Release back order" are managed by automated tasks. | Passed |  |  | 2016-08-30
|  |  | Operator selects "Reject" | Search status is selected "Awaiting stock" Order status "Awaiting stock" | Popup with option to continue or abort operation is displayed. Textbox to leave comment for the operation is displayed. | Retest |  | Telus note: Please consider an unified search field where order management tools are included, rather than having to find an order in a different section based on current status | 2016-08-30
|  | 6.3 | Order Approval
|  |  | Operator goes to "Order Approval" tab and select filter options | Different Shipping and Billing address (Bank Transfer orders are skipping this step) | Orders list is updated based on filter selections | Out of scope |  |  | 2016-08-30
|  |  | Press reject button |  | Popup with textbox for reject message appears. Options to abort or continue approve are present. | Out of scope |  |  | 2016-08-30
|  | 7 | Order details
|  | 7.1 | Cancel/Swap an item in an order
|  |  | Operator should cancel old order |  | Old order is canceled, given it was not passed to ERP | Out of scope |  |  | 2016-08-30
|  |  | Create new order with the new details |  | New order should be created Reference the old order in the notes section of the order record | Passed |  | Telus note:Not optimal - existing order should be modified rather than cancelled | 2016-08-30
|  | 8 | Order details
|  | 8.1 | Edit address in an order
|  |  | Operator should cancel old order |  | Old order is canceled, given it was not passed to ERP | Out of scope |  |  | 2016-08-30
|  |  | Create new order with the new details |  | New order should be created Reference the old order in the notes section of the order record | Passed |  | Telus note: Not optimal - existing order should be modified rather than cancelled | 2016-08-30
|  | 9 | Order details
|  | 9.1 | Leave a note marking the customer's desire
|  |  | Operator opens order summary and goes to Comments tab |  | Previous comments are displayed and status updates. Option to add a new comment is displayed and they can be Customer/internal. Maximum character limit was raised to 500. | Retest |  |  | 2016-08-30
|  | 10 | Order details
|  | 10.1 | Check stock of a product
|  |  | 1.Check product on eCommerce |  | If product is out of stock, buy button will display "Out of stock" | Can not test |  | No feed from ERP | 2016-08-30
|  |  | 2.Operator goes to "Advanced search" and select filter options, adding order reference |  | Orders list is updated based on filter selections. If product is out of stock, the order will have status "Awaiting stock". | Passed |  |  | 2016-08-30
|  | 11 | Order details
|  | 11.1 | Returns/Refunds
|  |  | Create order on front end |  |  | Retest |  |  | 2016-08-30
|  |  | Email BPC team the order refference number, the prodcut you want to create return to, and ammount for refund |  |  | Retest |  |  | 2016-08-30
|  |  | BPC team will create return and send Telus team email when done |  |  | Retest |  |  | 2016-08-30
|  |  | Open order details in OMS and go to "Return" tab to see returns details |  |  | Retest |  |  | 2016-08-30
|  |  | Modify/Approve/Reject "Refund" on "Payment" tab, "Refund" section |  |  | Retest |  |  | 2016-08-30
|  | 12 | Commercial Gestures
|  | 12.1 | Commercial Gestures - Discount and partial refund
|  |  | Operator goes to "Advanced search" and select filter options, adding order reference then opens order summary |  | Orders list is updated based on filter selections and order summary is displayed | Passed |  |  | 2016-08-30
|  |  | Operator opens order summary and goes to Payment tab |  | Payment and refunds details and status is displayed. | Passed |  |  | 2016-08-30
|  |  | Operator places "+" at Refund section in the Payment tab |  | Popup with refund details will be displayed | Passed |  | Note by Kaloyan: I'm concerned about agents being able to approve refunds - will this feature be restricted based on privileges? | 2016-08-30
|  | 13 | Manual orders
|  | 13.1 | Manual orders (made by phone)
|  |  | Phone orders will be done by operator through eCommerce interface |  | The order will act as an normal order. Phone orders should be Bank transfer only, but the system won't enforce this option. | Passed |  |  | 2016-08-30
|  | 14 | Check tracking information
|  | 14.1 | Check tracking information
|  |  | This can be done via web and link sent to customer on confirmation email. This can also be checked via OMS order status. |  |  | Passed |  | Telus note: Please consider an option to place order through OMS - we could use agent's name for sales statistics | 2016-08-30
|  | 15 | Check Payment capture/Refunded for PayPal
|  | 15.1 | Check Payment capture/Refunded for PayPal
|  |  | After order has been place check if temporary hold has been applied on the paypal sandbox platform | Order completed on web | Temporary hold has been placed | Passed |  |  | 2016-08-30
|  |  | After payment has been taken (order reached ERP) check payment taken | Order reached ERP | Payment has been captured | Passed |  |  | 2016-08-30
|  |  | Check temporary hold removal | Order canceled before reaching ERP | Temporary hold is removed | Passed |  |  | 2016-08-30
|  |  | Check payment refund | Order canceled after reaching ERP | Payment is refunded | Passed |  |  | 2016-08-30
|  |  | Check partial refund |  | Partial refund is added to account | Passed |  |  | 2016-08-30
|  | 16 | Doawnload orders
|  | 16.1 | Doawnload orders
|  |  | Open "Advanced search" or any other category needs to be downloaded |  |  | Retest |  |  | 2016-08-30
|  |  | Adjust the required filters - Note: if only 10 orders are display, only 10 will be downloaded. |  |  | Retest |  |  | 2016-08-30
|  |  | Press the "PDF" or "EXCEL" icon to download the report in the desired format |  |  | Retest |  |  | 2016-08-30

## End to End Test Cases
Sabre 2.0 - Test Cases
Feature |  | Live URL |  |  | Test URL
End to End |  | tbc
No | Content | No | Test case | Condition | Expected Result | Pass/Fail | Actual Result / Bugs | Comments | Date
1 | End to End | Service
Function
|  | 1 | Create product in PIM |  | Product in published in pim and ERP (sku) | Passed |  |  | 2016-09-14
|  | 2 | Create Offering in PIM | a. Normal Offering b. Upsell bundle c. Variants | Offering appear on WEB listing page | Passed |  |  | 2016-09-14
|  | 2.1. | Normal Offering |  | Offering appear on WEB listing page | Passed |  |  | 2016-09-14
|  | 2.2. | Upsell Bundle |  | Offering appear on WEB listing page | Passed |  |  | 2016-09-14
|  | 2.3. | Variants |  | Offering appear on WEB listing page | Passed |  |  | 2016-09-14
|  | 3 | Place order with created offering | a. WorldPay b. Paypal c. Bank transfer d. Vouchers | Order reaches OMS | Passed |  |  | 2016-09-14
|  | 3.1. | World Pay |  | Order reaches OMS | Passed |  |  | 2016-09-14
|  | 3.2. | Paypal |  | Order reaches OMS | Passed |  |  | 2016-09-14
|  | 3.3. | Paypal Credit |  | Order reaches OMS | Passed |  |  | 2016-09-26
|  | 3.4. | Bank Transfer |  | Order reaches OMS | Passed |  |  | 2016-09-14
|  | 3.5. | Vouchers |  | Order reaches OMS | Passed |  |  | 2016-09-14
|  | 4 | Order reaches OMS - internal automatic processes progressed |  | Payment pre-authorized Fraud Check complete Customer communications (emails delivered) | Passed |  |  | 2016-09-14
|  | 4.1. | Customer Services team approves Bank Transfer manually |  | Status update in OMS automatically so flow can continue | Passed |  |  | 2016-09-14
|  | 5 | Stock is updated in ERP via SOM |  |  | Passed |  |  | 2016-09-14
|  | 6 | Order is progressed up to ERP | a. Order with stock b. Order without stock c. Stock + vouchers | ERP order is created | Passed |  |  | 2016-09-14
|  | 7 | Dispatch order from ERP | a. Dispatch b. Return | OMS status is updated | Passed |  |  | 2016-09-14
|  | 8 | Send information to Samsung SAP via EDI | Florin/Andrei Popa to raise 3b13; Salman to process 3b13; Salman to check with Gurminder in test system and send back 4b2 with SO/DO number | Chekck 3B13 3B2 4B2 4C1 SO/DO | Pending
|  | 9 | Reports are updated |  |  | Passed |  |  | 2016-09-14
|  | 10 | Return order is created | a. Partial Products b. Full | Once return case created in CTS, OMS is updated, and option to Refund | Passed |  |  | 2016-09-14
|  | 11 | Refund from OMS | a. Partial refund b. Full refund | Status updated. Payment processed. CS raises request in EXI for Refund in case of Bank Transfer | Passed |  |  | 2016-09-14
|  | 12 | Reports are updated |  |  | Passed
2 | Regression Testing | Service | Regression Testing
|  | Function | Regression Testing
|  | 1 | Regression Testing |  |  | Pending

## System Integration - Diagram
Sabre 2.0 - Test Cases
Feature | Live URL | Test URL
System Integration

## Gap analisys
Sabre 2.0 - Test Cases
Feature |  | Live URL |  |  | Test URL
No | Content | No | Test case | Condition | Expected Result | Pass/Fail | Actual Result / Bugs | Comments | Date
|  | Service | OMS
|  | Function | Payment confirmation download
|  |  | Operator should upload payment confirmation |  | Operator opens order summary and goes to attachments tab and uploads payment confirmation. | Passed
|  |  | View/download payment confirmation from save screen |  | View/Download | Passed
|  | Service | OMS
|  | Function | Order tracking
|  |  | Order tracking link availalbe at order summary tab |  | ORder trackign link visible | Passed
|  | Service | PIM
|  | Function | Promo labler and Promo stamp offering level
|  |  | Add Promo Label |  | Promo label text field present | Passed
|  |  | Add Promo Stamp |  | Promo stamp drop down present | Passed
|  | Service | Web
|  | Function | Postcoder
|  |  | Search address by postcode | Checkout page | Start to input post code, system search starts automatically to search for address based on postcode | Passed
|  | Service | OMS
|  | Function | Returns and refunds
|  |  | Orders with returns |  | Orders with returns are listied | Passed
|  |  | Orders with refunds |  | Orders with refunds are listied | Passed
|  |  | Returns cases |  | Returns cases are listed | Passed
|  | Service | PIM
|  | Function | Edit/Remove assets after publish
|  |  | Edit/Remove assets after publish |  | Edit/Remove assets after publish | Failed | SAB-1593

## Screenshots
Screenshots
ID | Screenshot