## Sheet1
Total Downtime (Hrs): | 166 | 41.92% | = Percentage Downtime
Sprint 1
Total Downtime Sprint 1 (Hrs): | 14 | 19.44% | = Percentage Downtime Sprint 1
Day | Downtime (Hrs) | Potential Hours | Problem
Sprint 1 | 14 | 72
Sprint 2
Total Downtime Sprint 2 (Hrs): | 44 | 78.57% | = Percentage Downtime Sprint 2
Day | Downtime (Hrs) | Potential Hours | Problem
2016-04-21 | 4 | 8 | Show&Tell Testing restriction
2016-04-22 | 8 | 8 | PIM Offerings not available PIM, OMS Really slow
2016-04-25 | 8 | 8 | PIM Offerings not available PIM Really slow
2016-04-26 | 5 | 8 | PIM Offerings not available PIM Really slow Servers issues - PIM,OMS not available | 6h 4h 2h
2016-04-27 | 8 | 8 | Servers issues - PIM,OMS not available Webpage not available | 4h 8h
2016-04-28 | 3 | 8 | PIM not working, white page after login
2016-04-29 | 8 | 8 | Add to basket isn't working
Sprint 3
Total Downtime Sprint 3 (Hrs): | 68 | 94.44% | = Percentage Downtime Sprint 3
Day | Downtime (Hrs) | Potential Hours | Problem
2016-05-03 | 8 | 8 | Add to basket isn't working Changes in PIM are not refleting to web page
2016-05-04 | 8 | 8 | Add to basket isn't working Changes in PIM are not refleting to web page | 8h 3h
2016-05-05 | 8 | 8 | Add to basket isn't working Creating Offerings Not Avaiblae Payment not working | 2h 2h 6h
2016-05-06 | 8 | 8 | Payment not working PIM really slow | 8h 2h
2016-05-09 | 8 | 8 | Payment not working PIM product create not working
2016-05-10 | 8 | 8 | Payment not working PIM product create not working Web listing not workin Add to basket not working Orders are not reaching OMS | 6h 8h 4h 1h 2h
2016-05-11 | 8 | 8 | Server issues-nothing works Web not working-server issue OMS not working-server issue PIM not working PIM product create not working (PIM started working after 4h but not fully) Payment not working Orders not reaching OMS | 5h 5h 5h 4h 4h 2h 2h
2016-05-12 | 4 | 8 | PIM product create not working Testing on hold untill a full release is done. Too much old data on test servers | 4h less than 1h
2016-05-13 | 8 | 8 | Changes made in PIM are not reflected on web
Sprint 4
Total Downtime Sprint 4 (Hrs): | 62 | 70.45% | = Percentage Downtime Sprint 4
Day | Downtime (Hrs) | Potential Hours | Problem
2016-05-16 | 8 | 8 | - PIM product image upload is broken. “Choose” button is missing. - Orders are not reaching OMS | 8h 4h
2016-05-17 | 6 | 8 | PIM product image upload is broken. “Choose” button is missing. Web problems. 404 on PDP, internal server error. | 4h 6h
2016-05-18 | 8 | 8 | Offerings can’t be created in PIM Orders are not reaching TETRA ERP product creation not working | 4 8 8
2016-05-19 | 8 | 8 | Orders are not reaching TETRA ERP product creation not working Orders are not reaching OMS | 8 8 2
2016-05-20 | 8 | 8 | Orders are not reaching TETRA ERP product creation not working Orders are not reaching OMS Publish offering is not working | 8 8 8 7
2016-05-22 | 8 | 8 | Orders are not reaching TETRA. ERP product creation not working OMS and PIM internal server error. Page initialization error. Add to basket not working properly
2016-05-23 | 8 | 8 | Orders are not reaching TETRA. ERP product creation not working Add to basket not working properly
2016-05-24 | 8 | 8 | Orders are not reaching TETRA. ERP product creation not working Add to basket not working properly Offering publish not working | 2h - ordes are reaching tetra, but a walkaround is made. Not properly fixed 8h 8h 5h
2016-05-25 | 8 | 8 | ERP product creation not working Add to basket not working properly Offering publish not working
2016-05-26 | 8 | 8 | ERP product creation not working Orders are not reaching TETRA | 6h 8h
2016-05-27 | 2 | 8 | Orders are not reaching TETRA
Sprint 5
Total Downtime Sprint 5 (Hrs): | 20 | 22.73% | = Percentage Downtime Sprint 5
Day | Downtime (Hrs) | Potential Hours | Problem
2016-05-30 | 0 | 8
2016-05-31 | 3 | 8 | server issue, can't login to PIM,OMS
2016-06-01 | 4 | 8 | PIM really slow, can't do anything
2016-06-02 | 5 | 8 | Orders not reaching tetra Orders can't be completed on web | 3h-morning 2h-evning
2016-06-03 | 4 | 8 | Web not working payment not working | 2h-morning 2h-evning
2016-06-05 | 0 | 8
2016-06-06 | 0 | 8
2016-06-07 | 0 | 8
2016-06-08 | 0 | 8
2016-06-09 | 4 | 8 | Paypall not working
2016-06-10 | 0 | 8
Sprint 6
Total Downtime Sprint 6 (Hrs): | 20 | 83.33% | = Percentage Downtime Sprint 6
Day | Downtime (Hrs) | Potential Hours | Problem
2016-06-13 | 8 | 8 | Release required - realy old data on test env
2016-06-14 | 4 | 8 | Add to basket not working Product create not working | 2h-morning 2h-evning
2016-06-15 | 8 | 8 | Release required - realy old data on test env WEb broken after release | 4h 4h
2016-06-16
2016-06-17
2016-06-20
2016-06-21
2016-06-22
2016-06-23
2016-06-24