## Sheet1
Story - Name | Story - code | Steps for testing | Requirements | Story Owner (07.04.2016) | Epic | Priority | Test Owner | Status | Dependency | Completion Date
Key promotion area consists of Hero banner, carousel slideshow banner. | sab-17 | We need more details about this story. | Where do we set and test this? | Victor Sarateanu | Home Page - Web |  | Ionut / Stefan / Geani | TO DO
Site Navigation: Access to key journeys e.g. via banner, content or button area links | sab-18 | testing homepage buttons |  | Victor Sarateanu | Home Page - Web |  |  | TO DO | SAB-331, SAB-346, SAB-397
Header | sab-23 | Requirements are presented intro description. We will test those requirements |  | Victor Sarateanu | Header, footer,menu - Web |  |  | TO DO | SAB-479, SAB-477, SAB-486,SAB-492
Footer | sab-24 | Requirements are presented intro description. We will test those requirements |  | Victor Sarateanu | Header, footer,menu - Web |  |  | TO DO | SAB-353, SAB-354, SAB-352,SAB-480
Product Listing Page | sab-25 | Requirements are presented intro description. We will test those requirements |  | Victor Sarateanu | Regular Order Management - OMS |  |  | TO DO | SAB-1377, SAB-356, SAB-476,SAB-337, SAB-344, SAB-357,SAB-497, SAB-478, SAB-336,SAB-327, SAB-333, SAB-328,SAB-329, SAB-347, SAB-348,SAB-349, SAB-1375, SAB-1403,SAB-332, SAB-487, SAB-488,SAB-494, SAB-495
Product Details Page (PDP) | sab-26 | Requirements are presented intro description. We will test those requirements |  | Victor Sarateanu | Product Listing - Web |  |  | READY FOR TEST | SAB-1404, SAB-1428, SAB-1397
PDP: There is one product detail page for each product/bundle/variation of products. | sab-28 | Creating products in PIM and testing them on web page |  | Catalin Geani Fleancu | Product/Bundle Details - Web |  |  | READY FOR TEST | SAB-1404, SAB-218
The website designs should be branded as per the Sabre branding guidelines document. | sab-34 | Testing to be done, to compare testing environment with Brand Guidelines |  | Catalin Geani Fleancu | Generic requirements - Web |  |  | READY FOR TEST
The 'Add to Basket' page contains links to enable customers to continue shopping or proceed to checkout | sab-35 | Requirements are presented intro description. We will test those requirements |  | Gary Challoner | Shopping Basket - Web |  |  | TO DO | SAB-374, SAB-355
The 'Add to Basket' page includes all (if any) upsell products | sab-36 | Create Upsell products (offerings) in PIM, testing add to basket page with upsell products |  | Gary Challoner | Shopping Basket - Web |  |  | TO DO | SAB-351, SAB-350, SAB-378
Shopping basket page: includes options to select item quantities and payment type | sab-37 | Testing to be done, trying different options to check if item quantities and payment type work as intended |  | Stefan Chiosea | Shopping Basket - Web |  |  | READY FOR TEST | SAB-373, SAB-335, SAB-375,SAB-376, SAB-481, SAB-341,SAB-338, SAB-339, SAB-482,SAB-1406
Checkout page - billing details and address | sab-41 | Requirements are presented intro description. We will test those requirements, tests will be done to check different scenarios |  | Stefan Chiosea | Checkout - Web |  |  | READY FOR TEST | SAB-385, SAB-389, SAB-491,SAB-388
Once the necessary payment step(s) (depends upon the payment method) is complete the customer can continue their order journey | sab-46 | Testing different payment options, different scenarios, checkout flow, order journey | Payment options necessary. Andrei Popa provided some testing information for Paypal, wolrdPay and CC. If any other payment is required, Andrei Popa should provide details. | Victor Sarateanu | Payment Page |  |  | TO DO | SAB-496
Order Completion - information on page | sab-48 | Testing order journey, confirmation page details |  | Stefan Chiosea | Order Confirmation Page - Web |  |  | READY FOR TEST | SAB-377, SAB-334, SAB-361,SAB-362, SAB-359, SAB-360,SAB-363
Integrated with the Optimus Order Management Module ? for cart, checkout, payment and order confirmation functionality. | sab-82 | place orders on fornt end (web page) and see if the reach OMS with the correct data |  | Catalin Geani Fleancu | System integration - Web |  |  | READY FOR TEST
Top level Product Categories are Mobiles & Wearables, Tablets, TV & AV, PC & Monitors, Home Appliances, Accessories, Offers, and Bespoke. | sab-189 | Create products and offerings for the specific categorys Test if the reach front end with the correct data |  | Catalin Geani Fleancu | Product Categories - PIM |  |  | TEST IN PROGRESS | SAB-471, SAB-462
Update Product Details | sab-194 | Creating products in PIM and changing different details. Test if the details are also changed on the front end |  | Piotr Ignaczak | Product Lifecycle - PIM |  |  | TO DO | SAB-408, SAB-409, SAB-452
Configure the Sage 500 UBL ERP in ESOM (commons to OMS, PIM, etc) | 271 | We need more details about this story. Story added 07.04.2016 to the sprint! | We need more details about this story. Story added 07.04.2016 to the sprint! | Catalin Geani Fleancu | Product Variants - PIM |  |  | READY FOR TEST
Implement createSalesOrder (OMS) | 271 | We need more details about this story. Story added 07.04.2016 to the sprint! | We need more details about this story. Story added 07.04.2016 to the sprint! | Catalin Geani Fleancu | Product Variants - PIM |  |  | READY FOR TEST | SAB-1424, SAB-1425
The key features which will be part of the variant can be specified by the administration e.g. size, colour etc. This is based upon the fields for a product. | 208 | duplicate of 210? |  | Catalin Geani Fleancu | Product Variants - PIM |  |  | TEST IN PROGRESS | SAB-1468, SAB-1469
The administrator can add the information for the different variants; this can be one or more key features for a product type. | 210 | create variants. test that variant details are related to product type and they change correctly |  | Catalin Geani Fleancu | Offerings - PIM |  |  | TEST IN PROGRESS | SAB-425, SAB-469, SAB-446,SAB-421, SAB-447, SAB-433,SAB-468, SAB-423, SAB-441,SAB-450, SAB-463, SAB-470,SAB-472
Each variant produced has a different SKU and the variants should be sent from Samsung. | 211 | create variants and test assigning sku to variants |  | Catalin Geani Fleancu | Offerings - PIM |  |  | TO DO | SAB-473
An administrator can create different prices for same product, product variant or product bundle for all product types. | 215 | create products,variants, offerings and bundles in PIM and assign different prices to them. Test that on front end the prices are displayed correctly |  | Catalin Geani Fleancu | Offerings - PIM |  |  | TO DO | SAB-442, SAB-437, SAB-451,SAB-460, SAB-472
Product Catalogue should permit administrator to set prices decimals | 216 | Requirements are presented into description. We will test those requirements |  | Ozkan Mustafa | Bundles - PIM |  |  | TEST IN PROGRESS | SAB-1409
For each offering in Product Catalogue, administrator should be able to set three prices | 217 | Assign different prices to offerings. Test prices are displayed correctely on front end |  | Maciej Szewczykowski | Bundles - PIM |  |  | TEST IN PROGRESS | SAB-437, SAB-1465, SAB-451,SAB-472, SAB-1453
A bundle has a specific SKU | 219 | creating offerings and bundles with same sku. Testing that it is not possiblethis scenario and other related scenarios |  | Catalin Geani Fleancu | Bundles - PIM |  |  | TEST IN PROGRESS
A bundle has a specific price | 220 | duplicate of 215? |  | Catalin Geani Fleancu | Bundles - PIM |  |  | TEST IN PROGRESS | SAB-1433
The Product Catalogue supports any product type or version being bundled together | 221 | crate bundle offerings in PIM. test they appear correctely on front end |  | Catalin Geani Fleancu | Integration - PIM |  |  | TO DO
The first product added to the bundle is the primary product of the bundle | 222 | crate bundle offerings in PIM. test they appear correctely on front end |  | Catalin Geani Fleancu | PDPs - PIM |  |  | TEST IN PROGRESS | SAB-1367, SAB-471, SAB-428
eCommerce core | 253 | We need more details about this story. | We need more details about this story. | Emil Posmyk | UBL interface - ESOM |  |  | READY FOR TEST
Products Details page should be hosted on the same platform. Product catalogue should be able to provide all the necessary information to be displayed in the PDPs. | 266 | create products,variants, offerings and bundles in PIM. Test that they are displayed correctly on front end |  | Catalin Geani Fleancu | UBL interface - ESOM |  |  | READY FOR TEST
Initial load of products & bundles should be done to match the current website offer | 280 | This looks like a task. Is this testable by us? |  | Alin Radu | Product Lifecycle - PIM |  |  | IN PROGRESS
Mini-Basket Phase 1 | 501 | Requirements are presented intro description. We will test those requirements |  | Stefan Chiosea | Shopping Basket - Web |  |  | READY FOR TEST | SAB-485, SAB-490, SAB-1366
Payment Types - Paypal & Worldpay | 502 | Requirements are presented intro description. We will test those requirements |  | Victor Sarateanu | Payment Page |  |  | TO DO | SAB-1439, SAB-493
Order Journey | 503 | Requirements are presented intro description. We will test those requirements |  | Stefan Chiosea | Shopping Basket - Web |  |  | TEST IN PROGRESS | SAB-391, SAB-392, SAB-1369
Prepare Offering Summary from cached offeirng | 1316 | This looks like a task. Is this testable by us? |  | Gowthami Mopur | System integration - Web |  |  | IN PROGRESS | SAB-1368, SAB-1372, SAB-1370,SAB-1374
Hardware Configuration | 1329 | Is this testable by us? |  | Laviniu Gavanescu | Infrastructure - Test Environment |  |  | IN PROGRESS | SAB-1333, SAB-1335, SAB-1336,SAB-1337, SAB-1334, SAB-1338
Network Configuration | 1330 | Is this testable by us? |  | Laviniu Gavanescu | Infrastructure - Test Environment |  |  | IN PROGRESS | SAB-1339, SAB-1340, SAB-1341,SAB-1342, SAB-1343, SAB-1344
Configure infinispan cache on REST Application platforms | 1368 | This looks like a task. Is this testable by us? | I talked with Marek and created a "task" for me sepparately. Sab-1372 | Emil Posmyk | System integration - Web |  |  | READY FOR TEST | SAB-1316, SAB-1405, SAB-1372,SAB-1370, SAB-1374
Implement new Filter structure and filter generation mechanism. | 1370 | This looks like a task. Is this testable by us? |  | Marek Chmielowski | System integration - Web |  |  | TO DO
Sabre REST services modifycation | 1372 | This looks like a task. Is this testable by us? |  | Marek Chmielowski | System integration - Web |  |  | READY FOR TEST
Modify Filter interface | 1373 | This looks like a task. Is this testable by us? |  | Marek Chmielowski | System integration - Web |  |  | TO DO
Test new self-synchronising cache | 1374 | This should be a task? | No familiar with SoapUI. Strategy provide, but we may require addition guidance | Catalin Geani Fleancu | System integration - Web |  |  | TO DO
Categories - Web Implementation | 1379 | Will create products in PIM and then test if the right category are displayed on front end. | We need more details if this is the right approach. | Gowthami Mopur | Product Listing - Web |  |  | TO DO
Filtering - Web Implementation | 1382 | Filters will be tested if they display the right filtered information |  | Ionut Corlau | Product Listing - Web |  |  | TO DO
Details Page - Web Implementation | 1383 | create products,variants, offerings and bundles in PIM. Test that they are displayed correctly on front end |  | Gowthami Mopur | Product/Bundle Details - Web |  |  | TO DO
Document modyfied jason interface and new data structure | 1387 | This looks like a task. Is this testable by us? |  | Marek Chmielowski | System integration - Web |  |  | ON HOLD
Product Details Page (PDP) Additional Content | 1397 | Requirements are presented intro description. We will test those requirements Create products,variants, offerings and bundles in PIM. Test that they are displayed correctly on front end |  | Victor Sarateanu | Product Listing - Web |  |  | TO DO
Implement createSalesOrder (OMS) | 1443 | Not testable by us | Tom Freemantle added a comment - 06/Apr/16 3:34 PM Development done. Testing to be undertaken by Andrei or Cristian | Bogdan Arvinte | UBL interface - ESOM |  |  | TEST IN PROGRESS
create PO to book stock on | 1463 | We need more details about this story. Story added 07.04.2016 to the sprint! | We need more details about this story. Story added 07.04.2016 to the sprint! | Debby Auld | Tetra ERP Config |  |  | IN PROGRESS
create serials for stock | 1464 | We need more details about this story. Story added 07.04.2016 to the sprint! | We need more details about this story. Story added 07.04.2016 to the sprint! | Debby Auld | Tetra ERP |  |  | IN PROGRESS

## Sheet3
sab-17 | SAB-17 | Key promotion area consists of Hero banner, carousel slideshow banner. | Victor Sarateanu | Tom Freemantle | TO DO | Unresolved | 2016-02-26 | 2016-04-04 |  | Sprint 1 (Nominal 1) | Home Page - Web | Actions
sab-18 | SAB-18 | Site Navigation: Access to key journeys e.g. via banner, content or button area links | Victor Sarateanu | Tom Freemantle | TO DO | Unresolved | 2016-02-26 | 2016-04-04 | SAB-331, SAB-346, SAB-397 | Sprint 1 (Nominal 1) | Home Page - Web
sab-23 | SAB-23 | Header | Victor Sarateanu | Tom Freemantle | TO DO | Unresolved | 2016-02-26 | 2016-04-04 | SAB-479, SAB-477, SAB-486,SAB-492 | Sprint 1 (Nominal 1) | Header, footer,menu - Web
sab-24 | SAB-24 | Footer | Victor Sarateanu | Tom Freemantle | TO DO | Unresolved | 2016-02-26 | 2016-04-04 | SAB-353, SAB-354, SAB-352,SAB-480 | Sprint 1 (Nominal 1) | Header, footer,menu - Web
sab-25 | SAB-25 | Product Listing Page | Victor Sarateanu | Tom Freemantle | TO DO | Unresolved | 2016-02-26 | 2016-04-06 | SAB-1377, SAB-356, SAB-476,SAB-337, SAB-344, SAB-357,SAB-497, SAB-478, SAB-336,SAB-327, SAB-333, SAB-328,SAB-329, SAB-347, SAB-348,SAB-349, SAB-1375, SAB-1403,SAB-332, SAB-487, SAB-488,SAB-494, SAB-495 | Sprint 1 (Nominal 1) | Regular Order Management - OMS
sab-26 | SAB-26 | Product Details Page (PDP) | Victor Sarateanu | Tom Freemantle | READY FOR TEST | Unresolved | 2016-02-26 | 2016-04-06 | SAB-1404, SAB-1428, SAB-1397 | Sprint 1 (Nominal 1) | Product Listing - Web
sab-28 | SAB-28 | PDP: There is one product detail page for each product/bundle/variation of products. | Catalin Geani Fleancu | Tom Freemantle | READY FOR TEST | Unresolved | 2016-02-26 | 2016-04-06 | SAB-1404, SAB-218 | Sprint 1 (Nominal 1) | Product/Bundle Details - Web
sab-34 | SAB-34 | The website designs should be branded as per the Sabre branding guidelines document. | Catalin Geani Fleancu | Tom Freemantle | READY FOR TEST | Unresolved | 2016-02-26 | 2016-04-05 |  | Sprint 1 (Nominal 1) | Generic requirements - Web
sab-35 | SAB-35 | The 'Add to Basket' page contains links to enable customers to continue shopping or proceed to checkout | Gary Challoner | Tom Freemantle | TO DO | Unresolved | 2016-02-26 | 2016-04-01 | SAB-374, SAB-355 | Sprint 1 (Nominal 1) | Shopping Basket - Web
sab-36 | SAB-36 | The 'Add to Basket' page includes all (if any) upsell products | Gary Challoner | Tom Freemantle | TO DO | Unresolved | 2016-02-26 | 2016-04-01 | SAB-351, SAB-350, SAB-378 | Sprint 1 (Nominal 1) | Shopping Basket - Web
sab-37 | SAB-37 | Shopping basket page: includes options to select item quantities and payment type | Stefan Chiosea | Tom Freemantle | READY FOR TEST | Unresolved | 2016-02-26 | 2016-04-05 | SAB-373, SAB-335, SAB-375,SAB-376, SAB-481, SAB-341,SAB-338, SAB-339, SAB-482,SAB-1406 | Sprint 1 (Nominal 1) | Shopping Basket - Web
sab-41 | SAB-41 | Checkout page - billing details and address | Stefan Chiosea | Ozkan Mustafa | READY FOR TEST | Unresolved | 2016-02-26 | 2016-04-05 | SAB-385, SAB-389, SAB-491,SAB-388 | Sprint 1 (Nominal 1) | Checkout - Web
sab-46 | SAB-46 | Once the necessary payment step(s) (depends upon the payment method) is complete the customer can continue their order journey | Mihaita Nicolae | Tom Freemantle | TO DO | Unresolved | 2016-02-26 | 2016-04-07 | SAB-496 | Sprint 1 (Nominal 1) | Payment Page
sab-48 | SAB-48 | Order Completion - information on page | Stefan Chiosea | Tom Freemantle | READY FOR TEST | Unresolved | 2016-02-26 | 2016-04-06 | SAB-377, SAB-334, SAB-361,SAB-362, SAB-359, SAB-360,SAB-363 | Sprint 1 (Nominal 1) | Order Confirmation Page - Web
sab-82 | SAB-82 | Integrated with the Optimus Order Management Module ? for cart, checkout, payment and order confirmation functionality. | Catalin Geani Fleancu | Tom Freemantle | READY FOR TEST | Unresolved | 2016-02-26 | 2016-04-07 |  | Sprint 1 (Nominal 1) | System integration - Web
sab-189 | SAB-189 | Top level Product Categories are Mobiles & Wearables, Tablets, TV & AV, PC & Monitors, Home Appliances, Accessories, Offers, and Bespoke. | Catalin Geani Fleancu | Alin Radu | TEST IN PROGRESS | Unresolved | 2016-03-16 | 2016-04-05 | SAB-471, SAB-462 | Sprint 1 (Nominal 1) | Product Categories - PIM
sab-194 | SAB-194 | Update Product Details | Piotr Ignaczak | Alin Radu | TO DO | Unresolved | 2016-03-16 | 2016-04-04 | SAB-408, SAB-409, SAB-452 | Sprint 1 (Nominal 1) | Product Lifecycle - PIM
208 | SAB-208 | The key features which will be part of the variant can be specified by the administration e.g. size, colour etc. This is based upon the fields for a product. | Catalin Geani Fleancu | Alin Radu | READY FOR TEST | Unresolved | 2016-03-16 | 2016-04-05 |  | Sprint 1 (Nominal 1) | Product Variants - PIM
210 | SAB-210 | The administrator can add the information for the different variants; this can be one or more key features for a product type. | Catalin Geani Fleancu | Alin Radu | READY FOR TEST | Unresolved | 2016-03-16 | 2016-04-06 | SAB-1424, SAB-1425 | Sprint 1 (Nominal 1) | Product Variants - PIM
211 | SAB-211 | Each variant produced has a different SKU and the variants should be sent from Samsung. | Catalin Geani Fleancu | Alin Radu | TEST IN PROGRESS | Unresolved | 2016-03-16 | 2016-04-07 | SAB-1468, SAB-1469 | Sprint 1 (Nominal 1) | Product Variants - PIM
215 | SAB-215 | An administrator can create different prices for same product, product variant or product bundle for all product types. | Catalin Geani Fleancu | Alin Radu | TEST IN PROGRESS | Unresolved | 2016-03-16 | 2016-04-05 | SAB-425, SAB-469, SAB-446,SAB-421, SAB-447, SAB-433,SAB-468, SAB-423, SAB-441,SAB-450, SAB-463, SAB-470,SAB-472 | Sprint 1 (Nominal 1) | Offerings - PIM
216 | SAB-216 | Product Catalogue should permit administrator to set prices decimals | Ozkan Mustafa | Alin Radu | TO DO | Unresolved | 2016-03-16 | 2016-04-06 | SAB-473 | Sprint 1 (Nominal 1) | Offerings - PIM
217 | SAB-217 | For each offering in Product Catalogue, administrator should be able to set three prices | Maciej Szewczykowski | Alin Radu | TO DO | Unresolved | 2016-03-16 | 2016-04-06 | SAB-442, SAB-437, SAB-451,SAB-460, SAB-472 | Sprint 1 (Nominal 1) | Offerings - PIM
219 | SAB-219 | A bundle has a specific SKU | Catalin Geani Fleancu | Alin Radu | TEST IN PROGRESS | Unresolved | 2016-03-16 | 2016-04-05 | SAB-1409 | Sprint 1 (Nominal 1) | Bundles - PIM
220 | SAB-220 | A bundle has a specific price | Catalin Geani Fleancu | Alin Radu | TEST IN PROGRESS | Unresolved | 2016-03-16 | 2016-04-07 | SAB-437, SAB-1465, SAB-451,SAB-472, SAB-1453 | Sprint 1 (Nominal 1) | Bundles - PIM
221 | SAB-221 | The Product Catalogue supports any product type or version being bundled together | Catalin Geani Fleancu | Alin Radu | TEST IN PROGRESS | Unresolved | 2016-03-16 | 2016-04-05 |  | Sprint 1 (Nominal 1) | Bundles - PIM
222 | SAB-222 | The first product added to the bundle is the primary product of the bundle | Catalin Geani Fleancu | Alin Radu | TEST IN PROGRESS | Unresolved | 2016-03-16 | 2016-04-06 | SAB-1433 | Sprint 1 (Nominal 1) | Bundles - PIM
253 | SAB-253 | eCommerce core | Emil Posmyk | Alin Radu | TO DO | Unresolved | 2016-03-16 | 2016-04-01 |  | Sprint 1 (Nominal 1) | Integration - PIM
266 | SAB-266 | Products Details page should be hosted on the same platform. Product catalogue should be able to provide all the necessary information to be displayed in the PDPs. | Catalin Geani Fleancu | Alin Radu | TEST IN PROGRESS | Unresolved | 2016-03-16 | 2016-04-05 | SAB-1367, SAB-471, SAB-428 | Sprint 1 (Nominal 1) | PDPs - PIM
280 | SAB-271 | Configure the Sage 500 UBL ERP in ESOM (commons to OMS, PIM, etc) | Catalin Geani Fleancu | Tom Freemantle | READY FOR TEST | Done | 2016-03-18 | 2016-04-05 |  | Sprint 1 (Nominal 1) | UBL interface - ESOM
501 | SAB-272 | Implement createSalesOrder (OMS) | Catalin Geani Fleancu | Tom Freemantle | READY FOR TEST | Done | 2016-03-18 | 2016-04-05 |  | Sprint 1 (Nominal 1) | UBL interface - ESOM
502 | SAB-280 | Initial load of products & bundles should be done to match the current website offer | Alin Radu | Alin Radu | IN PROGRESS | Unresolved | 2016-03-21 | 2016-04-07 |  | Sprint 1 (Nominal 1) | Product Lifecycle - PIM
503 | SAB-501 | Mini-Basket Phase 1 | Stefan Chiosea | Gary Challoner | READY FOR TEST | Unresolved | 2016-03-29 | 2016-04-06 | SAB-485, SAB-490, SAB-1366 | Sprint 1 (Nominal 1) | Shopping Basket - Web
1316 | SAB-502 | Payment Types - Paypal & Worldpay | Victor Sarateanu | Gary Challoner | TO DO | Unresolved | 2016-03-29 | 2016-04-06 | SAB-1439, SAB-493 | Sprint 1 (Nominal 1) | Payment Page
1329 | SAB-503 | Order Journey | Stefan Chiosea | Gary Challoner | TEST IN PROGRESS | Unresolved | 2016-03-29 | 2016-04-06 | SAB-391, SAB-392, SAB-1369 | Sprint 1 (Nominal 1) | Shopping Basket - Web
1330 | SAB-1316 | Prepare Offering Summary from cached offeirng | Gowthami Mopur | Marek Chmielowski | IN PROGRESS | Unresolved | 2016-03-30 | 2016-04-04 | SAB-1368, SAB-1372, SAB-1370,SAB-1374 | Sprint 1 (Nominal 1) | System integration - Web
1368 | SAB-1329 | Hardware Configuration | Laviniu Gavanescu | Alin Radu | IN PROGRESS | Unresolved | 2016-03-30 | 2016-04-06 | SAB-1333, SAB-1335, SAB-1336,SAB-1337, SAB-1334, SAB-1338 | Sprint 1 (Nominal 1) | Infrastructure - Test Environment
1370 | SAB-1330 | Network Configuration | Laviniu Gavanescu | Alin Radu | IN PROGRESS | Unresolved | 2016-03-30 | 2016-04-06 | SAB-1339, SAB-1340, SAB-1341,SAB-1342, SAB-1343, SAB-1344 | Sprint 1 (Nominal 1) | Infrastructure - Test Environment
1372 | SAB-1368 | Configure infinispan cache on REST Application platforms | Emil Posmyk | Marek Chmielowski | READY FOR TEST | Unresolved | 2016-03-31 | 2016-04-06 | SAB-1316, SAB-1405, SAB-1372,SAB-1370, SAB-1374 | Sprint 1 (Nominal 1) | System integration - Web
1373 | SAB-1370 | Implement new Filter structure and filter generation mechanism. | Marek Chmielowski | Marek Chmielowski | TO DO | Unresolved | 2016-03-31 | 2016-04-06 | SAB-1316, SAB-1368, SAB-1422,SAB-1373 | Sprint 1 (Nominal 1) | System integration - Web
1374 | SAB-1372 | Sabre REST services modifycation | Marek Chmielowski | Marek Chmielowski | READY FOR TEST | Unresolved | 2016-03-31 | 2016-04-06 | SAB-1316, SAB-1434, SAB-1368,SAB-1371, SAB-1374 | Sprint 1 (Nominal 1) | System integration - Web
1379 | SAB-1373 | Modify Filter interface | Marek Chmielowski | Marek Chmielowski | TO DO | Unresolved | 2016-03-31 | 2016-04-01 | SAB-1370 | Sprint 1 (Nominal 1) | System integration - Web
1382 | SAB-1374 | Test new self-synchronising cache | Catalin Geani Fleancu | Marek Chmielowski | TO DO | Unresolved | 2016-03-31 | 2016-04-01 | SAB-1316, SAB-1368, SAB-1372 | Sprint 1 (Nominal 1) | System integration - Web
1383 | SAB-1379 | Categories - Web Implementation | Gowthami Mopur | Tom Freemantle | TO DO | Unresolved | 2016-03-31 | 2016-04-01 |  | Sprint 1 (Nominal 1) | Product Listing - Web
1387 | SAB-1382 | Filtering - Web Implementation | Ionut Corlau | Tom Freemantle | TO DO | Unresolved | 2016-03-31 | 2016-04-06 |  | Sprint 1 (Nominal 1) | Product Listing - Web
1397 | SAB-1383 | Details Page - Web Implementation | Gowthami Mopur | Tom Freemantle | TO DO | Unresolved | 2016-03-31 | 2016-04-06 |  | Sprint 1 (Nominal 1) | Product/Bundle Details - Web
1443 | SAB-1387 | Document modyfied jason interface and new data structure | Marek Chmielowski | Marek Chmielowski | ON HOLD | Unresolved | 2016-04-01 | 2016-04-05 |  | Sprint 1 (Nominal 1) | System integration - Web
1463 | SAB-1397 | Product Details Page (PDP) Additional Content | Victor Sarateanu | Tom Freemantle | TO DO | Unresolved | 2016-04-01 | 2016-04-06 | SAB-1445, SAB-26 | Sprint 1 (Nominal 1) | Product Listing - Web
1464 | SAB-1443 | Implement createSalesOrder (OMS) | Bogdan Arvinte | Andrei Popa | TEST IN PROGRESS | Unresolved | 2016-04-06 | 2016-04-07 |  | Sprint 1 (Nominal 1) | UBL interface - ESOM
| SAB-1463 | create PO to book stock on | Debby Auld | Debby Auld | IN PROGRESS | Unresolved | 2016-04-07 | 2016-04-07 |  | Sprint 1 (Nominal 1) | Tetra ERP Config
| SAB-1464 | create serials for stock | Debby Auld | Debby Auld | IN PROGRESS | Unresolved | 2016-04-07 | 2016-04-07 |  | Sprint 1 (Nominal 1) | Tetra ERP