## Bug List
Bug ID | Description | System | Assigned To | Status | Priority (L/M/H) | Testing Status/Comment | Date Raised | Date Closed
1 | Remove package on cart doesn't work | REFSITE | BA | Closed | M | Pass | 2015-09-11 | 2015-09-17 | Open
2 | Add to cart should open mini cart. | REFSITE | BA | Closed | L | Pass | 2015-09-11 | 2015-09-17 | Closed
3 | Highlight (pulse effect) added item to minicart. | REFSITE | BA | Closed | L | Pass | 2015-09-11 | 2015-09-17 | Dev Completed
4 | Quantity not updated when added for the second time. | REFSITE | MG | Closed | H | Pass | 2015-09-11 | 2015-09-17 | To Test
5 | Add Billing and Delivery address fields | REFSITE | BA | Closed | M | Pass | 2015-09-11 |  | Rejected
6 | Confirmation E-mail: Monthly cost column to be removed | CORE | EP | Closed | M | Pass | 2015-09-11 |  | Moved to the next Phase
7 | Confirmation E-mail: Image resizing class needs to be applied | CORE | EP | Closed | M | Pass | 2015-09-11 | 2015-09-21
8 | OMS - 4 address are populated | REFSITE | AS | Closed | H | Pass / order sample REFSITE00000223 | 2015-09-11 | 2015-09-21
9 | Weight is not multiplied (and potentially not added) correctly | CORE/OMS | MG/AP | Closed | M |  | 2015-09-11
10 | Middle name is NULL | OMS | AP | Closed | L | Pass | 2015-09-11 | 2015-09-17
11 | Send correct payment properties to OMS | CORE | AP/AS | Complete | H | Pass | 2015-09-11 | 2015-09-28
12 | Add delivery line (service line) when calling OMS | CORE | AS/GM | To Test | M | Need more details | 2015-09-11
13 | Fix the need for comments | OMS | AP | Complete | M | Pass | 2015-09-11 | 2015-09-29
14 | Close the session post complete. | REFSITE | BA/MG | Complete | H | Pass | 2015-09-11 | 2015-09-28
15 | Rethink how quanties will be shown on items | OMS | PI | Moved to the next Phase | L |  | 2015-09-11
16 | Discount = 1 needs to removed | REFSITE | MG | Closed | M | Pass | 2015-09-11
17 | Order Approval Screen: show first 10 orders automatically | OMS | MS | Closed | L | Pass | 2015-09-11 | 2015-09-17
18 | Remove logo from client dropdown | OMS | MS | Closed | L | Pass | 2015-09-11 | 2015-09-17
19 | Left alignment of text in order listing with a bit of left padding | OMS | MS | Closed | L | Need more details | 2015-09-11
20 | Quick search to Search by reference | OMS | MS | Closed | L | Pass | 2015-09-11 | 2015-09-21
21 | Product Ids not to break layout (Maybe Column Toggler) | OMS | PI/MS | Moved to the next Phase | L |  | 2015-09-11
23 | Total cost price mismatch - see order REFSITE00000157 (2 products in the email but only one in the basket) | REFSITE / OMS | MG | Closed | H | Pass | 2015-09-15 | 2015-09-21
24 | Order reference hardcoded on the confirmation page #165548 | REFSITE | AS | Closed | H | Pass | 2015-09-15 | 2015-09-21
25 | After session times out the page collapse to just a header and footer | REFSITE | BA/MG | Unable to replicate/Complete | L | Pass | 2015-09-15 | 2015-09-29
26 | Session timeout not handled in OMS, missing - order history, order audit, comments and attachment info and not message displayed to user regarding session timing out. | OMS | EP | Moved to the next Phase | L | Complex fix required | 2015-09-15
27 | Intermittent error - This XML file does not appear to have any style information associated with it. The document tree is shown below. <partial-response id="j_id1"> <error> <error-name>class javax.faces.application.ViewExpiredException</error-name> <error-message> <![CDATA[ viewId:/oms/so/salesOrders.xhtml - View /oms/so/salesOrders.xhtml could not be restored. ]]> </error-message> </error> </partial-response> | OMS | EP | To Test | M | Need more details | 2015-09-15
28 | Total cost price mismatch - see order REFSITE00000440 | REFSITE | MG | Closed | L | Pass | 2015-09-16 | 2015-09-21
29 | Complete page not showing data for cart | REFSITE | BA | Closed | H | Pass | 2015-09-17 | 2015-09-21
30 | Quantity on complete page not matching email | REFSITE | GM | Closed | H | Pass | 2015-09-17 | 2015-09-21
31 | Able to proceed to checkout with an empty cart | REFSITE | BA | Closed | H | Pass / fixed. To able to go to check out with empty basket | 2015-09-17 | 2015-09-21
32 | 500 error on complete page | REFSITE | MG | Closed | H | Pass | 2015-09-21 | 2015-09-21
33 | Sort by price has two arrows in Internet Explorer | REFSITE | DG | Complete | L | Pass | 2015-09-21 | 2015-09-28
34 | Unable to remove product from basket in IE11 | REFSITE | DG | Complete | H | Pass | 2015-09-21 | 2015-09-29
35 | Can't move multiple products from Awaiting stock to Pick and Pack | OMS | PI | Complete | H | Pass | 2015-09-21 | 2015-09-29
36 | Processing order to Paypal leads to an error and redirecting back to basket page | REFSITE | MG | Closed | H |  | 2015-09-21 | 2015-09-21
37 | Change SALES ORDERS to reflect the the order status interface the admin is working on such as Credit Check etc. | OMS | PI | Moved to the next Phase | L |  | 2015-09-21
38 | Export to Excel and export to PDF links are leading to 500 Internal errors | OMS | EP | Closed | M | Pass | 2015-09-21
39 | Weight is shown in kilograms | OMS | AP | Moved to the next Phase | M | Solution ready - Andrei implementing | 2015-09-21
40 | Shipping address not captured on order confirmation page and in OMS | REFSITE/OMS | AS | Complete | H | Pass | 2015-09-21 | 2015-09-28
41 | FROM address looks strange - contains multiple names of individuals - MAIL FROM:<sravani.yella@pjmedia.co.uk,piotr.ignaczak@pjmedia.co.uk,andrei.popa@pj-interactive.ro>" | ESOM | EP | Closed | M | Pass | 2015-09-22
42 | Shipping address is over written by Billing address when you click Proceed To PayPal with "Shipping address is same as billing address" check box clicked | REFSITE | BA | Complete | M | Pass | 2015-09-22 | 2015-09-28
43 | Expression Error: Named Object: langConverter not found. | PIM/CAI | EP | Complete | M | Need more details | 2015-09-22
44 | Banner links broken. For instance the SAMSUNG GALAXY S5 on the homepage should link through to - http://reftest.brandpath.com/#/smartphones/03B31C94-C428-4F1F-95E8-CE19EB022A3C | REFSITE | BA | Complete | M | Pass | 2015-09-23 | 2015-09-28
45 | Repitition of product images - http://reftest.brandpath.com/#/smartphones/65AE30D7-DF38-4D39-9FEC-1F3010C55C73 | OMS | EP | Complete | M | Pass | 2015-09-23 | 2015-09-28
46 | PDF export site name NOT site id | OMS | EP | Complete | L | Pass | 2015-09-23
47 | Unable to Reject from Failed_DC: org.jbpm.workflow.instance.WorkflowRuntimeException: [so.subprocess.orderDispatch:2,127 - Status? | OMS | EP | Complete | M |  | 2015-09-23
48 | Unable to Reject from Failed_DC: org.jbpm.workflow.instance.WorkflowRuntimeException: [so.subprocess.orderDispatch:2,127 - Status? | OMS | EP | REJECTED | M |  | 2015-09-23
49 | (EG13):27] -- XOR split could not find at least one valid outgoing connection for split Status? (EG13) | OMS | EP | REJECTED | M |  | 2015-09-23
50 | We need valid tetra codes in order to make E2E order processing simulation | REFSITE/OMS | PI | Complete | M |  | 2015-09-23
51 | product prices are wrong for REFSITE00000295 | REFSITE/Core | MG | Complete | H | Pass | 2015-09-23 | 2015-09-29
52 | list with products that have duplicate images | REFSITE | MG | Complete | H | Pass | 2015-09-23 | 2015-09-28
53 | unable to place order on REFSITE - on cart review page | REFSITE | MG | Open | H | Fail / Unable to pass with order REFSITE00000346 | 2015-09-23
54 | links to be implemented on home page for products that have no CTA to details page on Smartphones page | REFSITE | MG | Complete | H | Pass | 2015-09-23 | 2015-09-28
55 | list of links to be implemented on home page | REFSITE | BA | Complete | H | Pass | 2015-09-23 | 2015-09-28
56 | Different product quantities captured - #REFSITE00000257 had 4 products different quantities - captured in OMS only two products | REFSITE | MG | Complete | H | Pass | 2015-09-23 | 2015-09-29
56 | Delivery appearing in smartphones listing page | REFSITE | BA/GM | Complete | H | Pass | 2015-09-23 | 2015-09-28
57 | Payment failure going to order complete page | REFSITE | AS/BA | Dev Completed | M |  | 2015-09-25
58 | Some of the actions in progressing an order in OMS are performed by user actions and some by automated task and that should be visible in order history. For order REFSITE00000344 it shows me as the person that progreessed the order to Complete status but that was an automated action after Dispatch. We need to distinguish in order history who did the progression of order on each step. | OMS | EP | Open | L |  | 2015-09-29
59 | able to pass from PayPal to REFSITE without completion of payment | REFSITE | BA | Dev Completed | M |  | 2015-09-29
60 | Order REFSITE00000343 has three comments and that comment was inserted once while moving order from Awaiting Approval to Approved | OMS | EP | Open | L