## Bug List
Bug ID | Description | System | Assigned To | Status | Priority (L/M/H) | Testing Status/Comment | Date Raised | Date Closed
1 | Remove package on cart doesn't work | REFSITE | BA | Closed | M | Pass | 2015-09-11 | 2015-09-17 | Open
2 | Add to cart should open mini cart. | REFSITE | BA | Closed | L | Pass | 2015-09-11 | 2015-09-17 | Closed
3 | Highlight (pulse effect) added item to minicart. | REFSITE | BA | Closed | L | Pass | 2015-09-11 | 2015-09-17 | Dev Completed
4 | Quantity not updated when added for the second time. | REFSITE | MG | Closed | H | Pass | 2015-09-11 | 2015-09-17 | To Test
5 | Add Billing and Delivery address fields | REFSITE | BA | Open | M |  | 2015-09-11 |  | Rejected
6 | Confirmation E-mail: Monthly cost column to be removed | CORE | EP | Open | M | Fail - Order placed REFSITE00000174 still contains Monthly cost | 2015-09-11
7 | Confirmation E-mail: Image resizing class needs to be applied | CORE | EP | To Test | M | Need more details | 2015-09-11
8 | OMS - 4 address are populated | REFSITE | AP/BA/AS | Open | H | Fail / still 4 addresses stored | 2015-09-11
9 | Weight is not multiplied (and potentially not added) correctly | CORE/OMS | MG/AP | To Test | M | In Progress - not able to receive email for orders placed | 2015-09-11
10 | Middle name is NULL | OMS | AP | Closed | L | Pass | 2015-09-11 | 2015-09-17
11 | Send correct payment properties to OMS | CORE | MG/AS | To Test | H | In Progress - not able to receive email for orders placed | 2015-09-11
12 | Add delivery line (service line) when calling OMS | CORE | MG | Open | M |  | 2015-09-11
13 | Fix the need for comments | OMS | AP | Open | M |  | 2015-09-11
14 | Close the session post complete. | REFSITE | BA/MG | Open | H |  | 2015-09-11
15 | Rethink how quanties will be shown on items | OMS | PI | Open | L |  | 2015-09-11
16 | Discount = 1 needs to removed | REFSITE | MG | To Test | M | Need more details | 2015-09-11
17 | Order Approval Screen: show first 10 orders automatically | OMS | MS | Closed | L | Pass | 2015-09-11 | 2015-09-17
18 | Remove logo from client dropdown | OMS | MS | Closed | L | Pass | 2015-09-11 | 2015-09-17
19 | Left alignment of text in order listing with a bit of left padding | OMS | MS | To Test | L | Need more details | 2015-09-11
20 | Quick search to Search by reference | OMS | MS | Open | L | Fail / Not working every time, and when it appears it doesn't show like is looking for results. No loading/transition animation while expecting result | 2015-09-11
21 | Product Ids not to break layout (Maybe Column Toggler) | OMS | PI/MS | Open | L |  | 2015-09-11
23 | Total cost price mismatch - see order REFSITE00000157 (2 products in the email but only one in the basket) | REFSITE / OMS | MG | Open | H | Fail/ Still seeing different quantities - REFSITE00000174 | 2015-09-15
24 | Order reference hardcoded on the confirmation page #165548 | REFSITE | AS | Open | H | Fail / Order reference removed but not showing actual order number | 2015-09-15
25 | After session times out the page collapse to just a header and footer | REFSITE | MG | Open | L |  | 2015-09-15
26 | Session timeout not handled in OMS, missing - order history, order audit, comments and attachment info and not message displayed to user regarding session timing out. | OMS | EP | Open | L |  | 2015-09-15
27 | Intermittent error - This XML file does not appear to have any style information associated with it. The document tree is shown below. <partial-response id="j_id1"> <error> <error-name>class javax.faces.application.ViewExpiredException</error-name> <error-message> <![CDATA[ viewId:/oms/so/salesOrders.xhtml - View /oms/so/salesOrders.xhtml could not be restored. ]]> </error-message> </error> </partial-response> | OMS | EP | Open | M |  | 2015-09-15
28 | Total cost price mismatch - see order REFSITE00000440 | REFSITE | MG | To Test | L | In Progress - not able to receive email for orders placed | 2015-09-16
29 | Complete page not showing data for cart | REFSITE | MG | Open | H |  | 2015-09-17
30 | Quantity on complete page not matching email | REFSITE | GM | Open | H |  | 2015-09-17
31 | Able to proceed to checkout with an empty cart | REFSITE | ? | Open | H |  | 2015-09-17
32 | Unable to place order | REFSITE | ? | Open | H |  | 2015-09-21
33 | Unable to find order after changing status to Back order | OMS | ? | Open | H |  | 2015-09-21