## Activities by time
| 2015-07-27 | 2015-07-28 | 2015-07-29 | 2015-07-30 | 2015-07-31 | 2015-08-03 | 2015-08-10 | 2015-08-17 | 2015-08-24 | 2015-08-31 | 2015-09-07 | 2015-09-14
use cases n… | bar: 2015-07-27; 2015-07-31
Test Cases
Front end ecommerce | bar: 2015-08-24
Testing etc
Deploy 1.0 | bar: 2015-08-31
Define Feb Target Plan | bar: 2015-08-10 to 2015-08-17

## Activities List
Note - the current designs for the reference site are Concept 2 v0.5
Relevant Journey | Description | Use Case needed (Y/N) | Comments
1.0 Demonstrable
eshopper | end to end shopper order journey
eshopper | home page | Y | Requires a static html page. Home page will have a link to smartphones - providing a product listing and product filter
eshopper | menu | Y
eshopper | listing | Y | Filter and select
eshopper | filter | Y
eshopper | details | Y | No 'choose a plan' no colour or memory variations, there is a 'buy button', no compare. 'social media pins - like, pin' are present but not clickable. Multiple, clickable images, no enlarge function. Tabs - overview, features, whats in the box - use lorem ipsum
eshopper | add to basket | Y | Dynamic elements as current,, but remove 'change' monthly cost', coupon is static, Related products and services should be in visible components, but not functioning. Keep Delivery options as basic.
eshopper | checkout (minimum) | Y | Merge payment and personal details onto the same page…remove paypal…basket needs to represent the order.
eshopper | Order confirmation | Y | Again remove the monthly reference
eshopper | simple email confirmation | Y
PIM | products loaded | Y
PIM | 4-6 products loaded | Y
PIM | tabs - overview, specification, several images | Y
PIM | choose products that are affected by filtering | Y
PIM | product admin (PIM) | Y
PIM | edit existing product | Y
PIM | publish | Y
OMS | order management | Y
OMS | view the order in the system | Y
OMS | manually progress the order (approve) | Y
OMS | manually cancel an order | Y
OMS | flow for device? (no credit check) | Y
OMS | tetra view the order | Y
PIM/OMS | multilingual (back office PIM and OMS) | Y
| front office responsive | Y
Activities Out of scope for Demonstration
cms (including multilingual front end)
multi currency
multi country
load balanced implementation
hardened
performacne tested
back offcie responsive
minibakset

## User Journeys to Demo
User Journeysto be Demonstrated on the Day - Minimum Set of Features
| 1. eShopper Journey |  | JOURNEY STEP | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
| 1 | View the home page | Activity | View the home page | Navigate to a list of products | Select a product based upon the filter | View the product detail, viewing each of the tabs | Select the product for the shopping cart | View the shopping cart | Complete checkout information | Purchase | View the Summary | View the confirmation email
| 2 | Navigate to a list of products | Sub Activities
| 3 | Select a product based upon the filter
| 4 | View the product detail, viewing each of the tabs
| 5 | Select the product for the shopping cart
| 6 | View the shopping cart
| 7 | Complete checkout information
| 8 | Purchase
| 9 | View the Summary
| 10 | View the confirmation email
2. PIM Administrator Journey
| 1 | Log in to Optimus
| 2 | Navigate to the PIM
| 3 | List the available products
| 4 | Select a product and view the details
| 5 | Update the product
| 6 | Approve and Publish the Update the Product change
| 7 | List available offerings
| 8 | Select an offering and view the details
| 9 | Update the price of the offering
| 10 | Approve and Publish the Update the Offering change
2. OMS Administrator Journey
| 1 | Log in to Optimus
| 2 | Navigate to the OMS
| 3 | List the current Orders
| 4 | Select an Order and view the details
| 5 | Update the Order
| 6 | Show Order Despatch Messaging

## Burndown chart Use Cases
Related Top Level Use Cases for Demo
Component | Function | Use Case Name | Mark/Piotr - % complete
PIM | PRODUCT | Update a Product | 75%
PIM |  | Publish a product
PIM | PRODUCT | List products | 100%
PIM | OFFERING | Update an Offering | 50%
PIM |  | Publish a price change
OMS | PROCESS ORDER | Create Order via API | 100%
OMS | PROCESS ORDER | View Order | 100%
OMS |  | List Orders
OMS | PROCESS ORDER | Create Despatch in Tetra | 60%
OMS | PROCESS ORDER | Approval Process | 90%
OMS | PROCESS ORDER | Cancel order | 75%

## Activities By Journey Step
eShopper | JOURNEY STEP | 1 |  |  | 2 |  |  | 3 |  |  | 4 |  |  | 5 |  |  | 6 |  |  | 7 |  |  | 8 |  |  | 9 |  |  | 10
| Activity | View the home page | Owner | Duration | Navigate to a list of products | Owner | Duration | Select a product based upon the filter | Owner | Duration | View the product detail, viewing each of the tabs | Owner | Duration | Select the product for the shopping cart | Owner | Duration | View the shopping cart | Owner | Duration | Complete checkout information | Owner | Duration | Purchase | Owner | Duration | View the Summary | Owner | Duration | View the confirmation email | Owner | Duration
| Sub Activities | Aurelia application code | BA | 2 | REST service to return all offerings inc pagination | GM | 2 | REST service to return all offerings filtered and sorted | GM | 2 | REST Service to return single offering | GM | 2 | REST Service - addToCart | MS | 0.5 | REST Service - removeFromCart | MS | 0.5 | REST Service - addConsumer | EP | 0.5 | ESOM Authorise (SOAP) Integration | AP | 2 | REST Service - getConsumer | GM | 0.5 | HTML/CSS | DG | 1
|  | HTML/CSS | DG | 2 | Aurelia application code | BA | 3 | REST service to provide filters | GM | 3 | Aurelia application code | BA | 3 | SOAP Service - addToCart | MS | 0.5 | SOAP Service - removeFromCart | MS | 0.5 | SOAP Service - Consumer.add | EP | 0.5 | POST to Paypal via ESOM | AP | 1 | REST Service - getAddress | GM | 0.5 | ESOM Send Comms (SOAP) Integration | EP | 3
[5 empty] | HTML/CSS | DG | 2 | Aurelia application code | BA | 2 | HTML/CSS | DG | 2 | REST Service - initialiseCart | MS | 0.5 | REST Service - updateQuantity | MS | 0.5 | REST Service - updateConsumer | EP | 0.5 | eShop Review Service (accepts HTTP POST) | AP | 1 | REST Service - getCart | GM | 0.5
[8 empty] | HTML/CSS | DG | 2 |  |  |  | SOAP Service - initialiseCart | MS | 0.5 | SOAP Service - updateQuantity | MS | 0.5 | SOAP Service - Consumer.update | EP | 0.5 | eShop SOAP Service to update Payment Reference | AP | 2 | SOAP Service - Consumer.get | GM | 0.5
[14 empty] | Basic Business Rules | MS | 2 | REST Service - emptyCart | MS | 0.5 | Basic Business Rules | EP | 1 | ESOM charge (SOAP) integration | AP | 2 | SOAP Service - Address.get | GM | 0.5
[14 empty] | Aurelia application code | BA | 2 | SOAP Service - emptyCart | MS | 0.5 | Aurelia application code | BA | 2 | Handle payment failure | AP | 1 | SOAP Service - Cart.get | GM | 1
[17 empty] | Basic Business Rules | MS | 3 | HTML/CSS | DG | 2 | Handle payment success | AP | 1 | Aurelia application code | BA | 2
[17 empty] | Aurelia application code | BA | 5 |  |  |  | REST Service - addAddress | EP | 1 | HTML/CSS | DG | 2
[17 empty] | HTML/CSS | DG | 2 |  |  |  | SOAP Service - Address.add | EP | 0.5 | OMS CreateOrder (SOAP) Integration | AP | 3
[23 empty] | REST Service - updateAddress | EP | 1 | ESOM getPaymentDetails (SOAP) | GM | 2
[23 empty] | SOAP Service - Address.update | EP | 0.5
PIM | JOURNEY STEP | 1 |  |  | 2 |  |  | 3 |  |  | 4 |  |  | 5 |  |  | 6 |  |  | 7 |  |  | 8 |  |  | 9 |  |  | 10
| Activity | Log in to Optimus | Owner | Duration | Navigate to the PIM | Owner | Duration | List the available products | Owner | Duration | Select a product and view the details | Owner | Duration | Update the product | Owner | Duration | Approve and Publish the Update the Product change | Owner | Duration | List available offerings | Owner | Duration | Select an offering and view the details | Owner | Duration | Update the price of the offering | Owner | Duration | Approve and Publish the Update the Offering change | Owner | Duration
| Sub Activities | Enable security | MG | 0.5 | Fine-tune layout | GM | 2 | Update Product Listing Page to display primary product image | AS | 1 | Implement Primefaces components inline with new design | DG | 2 | no tasks - same as create / view |  |  | Copy product images to CDN | AS | 2 | Update to include primary offering image | AS | 1 | Implement Primefaces components inline with new design | DG | 1 | Create new price record on each change when offering is live | AS | 2 | Copy offering images to CDN | AS | 2
|  | Ensure Logout button works | MG | 0.25 | Ensure links/pages/sites are protected | AS | 5 | Test Data | MG / AS | 2 | Update product page to new design | AS | 3 | [6 empty] | Test Data | MG | 1 | Update offering page to new design | AS | 3
[5 empty] | Test Data | MG | 0.5 |  |  |  | Create Primefaces controls for product properties | DG | 1 | [9 empty] | Complete Offering Property Control Rendering | AS | 1
[11 empty] | Complete Product Property Control Rendering | AS | 2 | [9 empty] | Deep-link View Offering Modal for OMS Integration | AS | 2
OMS | JOURNEY STEP | 1 |  |  | 2 |  |  | 3 |  |  | 4 |  |  | 5 |  |  | 6
|  | Log in to Optimus | Owner | Duration | Navigate to the OMS | Owner | Duration | List the current Orders | Owner | Duration | Select an Order and view the details | Owner | Duration | Update the Order | Owner | Duration | Show Order Despatch Messaging | Owner | Duration
|  | Upgrade to KC 1.3.1 (or 1.4) | EP | 1 | Fine-tune layout | MS | 2 | Resolve WS Security Roles issue | AP | 3,5 (???) | Fix the payment tab in order details | AP/MS | 0.5 | ERP Status Update - basic | EP | 1 | Store tracking reference from ERP | AP | 1
|  | Upgrade KC templates | BA | 2,5 (??) | Dashboard - ensure it's working | EP/PI | 0.5 | Advanced search - fix | EP | 0.5 | Test data | AP | 0.5 | Standard Delivery flow | EP | 1 | Configure sending e-mails | AP | 0.5
|  | I18N support in KC enabled | PI | 1 | Re-confiure roles | PI | 0.5 | Test Data | AP | 0.5 |  |  |  | Update KIE Workbench | EP | 0.25 | Prepare e-mail templates | BA/FC | ??
|  | Ensure Logout button works | PI | 0.25 | Ensure links/pages/sites are protected | MS/AP | 5 | [6 empty] | ERP Status Update - generic | AP | 2.5 | Other test data | AP | 0.5
|  | Account Management screen | PI | 0.5 | Test Data | PI | 0.5 | [6 empty] | Saving comment and updating by WIH | EP | 1.5
|  | Test Data | PI | 0.5 | [9 empty] | Quartz scheduler improvements | EP | 1
[14 empty] | Other test data | AP | 0.5

## Backlog
# | Journey | Use Case | Task | Resource | Effort (days) | % Complete | Effort Remaining | Module | Notes | Priority | Sequence
1 | eShopper | View the home page | Aurelia application code | BA / IC | 2 | 100 | 0 | Reference Site |  | 1 | 4
2 | eShopper | View the home page | HTML/CSS | DG | 0.5 | 100 | 0 | Reference Site |  | 1 | 4
3 | eShopper | Navigate to a list of products | REST service to return all offerings inc pagination including images | MS | 2 | 100 | 0 | PIM/IMP |  | 1 | 1
4 | eShopper | Navigate to a list of products | Aurelia application code | BA / IC | 3 | 100 | 0 | Reference Site |  | 1 | 1
5 | eShopper | Navigate to a list of products | HTML/CSS | DG | 0.5 | 100 | 0 | Reference Site |  | 1 | 1
6 | eShopper | Select a product based upon the filter | REST service to return all offerings filtered and sorted | GM | 2 | 100 | 0 | PIM/IMP |  | 1 | 2
7 | eShopper | Select a product based upon the filter | REST service to provide filters | GM | 3 | 100 | 0 | PIM/IMP |  | 1 | 1
8 | eShopper | Select a product based upon the filter | Aurelia application code | BA / IC | 2 | 100 | 0 | Reference Site |  | 1 | 2
9 | eShopper | Select a product based upon the filter | HTML/CSS | DG | 1 | 100 | 0 | Reference Site |  | 1 | 2
10 | eShopper | View the product detail, viewing each of the tabs | REST Service to return single offering including images | MS | 2 | 100 | 0 | PIM/IMP |  | 1 | 3
11 | eShopper | View the product detail, viewing each of the tabs | Aurelia application code | BA / IC | 3 | 25 | 2.25 | Reference Site | Bogdan to review data available via WS | 1 | 3
12 | eShopper | View the product detail, viewing each of the tabs | HTML/CSS | DG | 0.5 | 100 | 0 | Reference Site |  | 1 | 3
13 | eShopper | Select the product for the shopping cart | SOAP Service - initialiseCart | SY | 0.5 | 100 | 0 | ECOM |  | 1 | 4
14 | eShopper | Select the product for the shopping cart | REST Service - initialiseCart | SY | 0.5 | 100 | 0 | IMP |  | 1 | 5
15 | eShopper | Select the product for the shopping cart | SOAP Service - addToCart | SY | 0.5 | 100 | 0 | ECOM |  | 1 | 6
16 | eShopper | Select the product for the shopping cart | REST Service - addToCart | SY | 0.5 | 100 | 0 | IMP |  | 1 | 7
17 | eShopper | Select the product for the shopping cart | Basic Business Rules | MS | 2 |  | 2 | ECOM |  | 7 | -
18 | eShopper | Select the product for the shopping cart | Aurelia application code | BA / IC | 2 | 100 | 0 | Reference Site |  | 1 | 5
19 | eShopper | View the shopping cart | SOAP Service - removeFromCart | SY | 0.5 | 100 | 0 | ECOM |  | 1
20 | eShopper | View the shopping cart | REST Service - removeFromCart | SY | 0.5 | 100 | 0 | IMP |  | 1
21 | eShopper | View the shopping cart | SOAP Service - updateQuantity | SY | 0.5 | 100 | 0 | ECOM |  | 1
22 | eShopper | View the shopping cart | REST Service - updateQuantity | SY | 0.5 | 100 | 0 | IMP |  | 1
23 | eShopper | View the shopping cart | SOAP Service - emptyCart | SY | 0.5 | 100 | 0 | ECOM |  | 2
24 | eShopper | View the shopping cart | REST Service - emptyCart | SY | 0.5 | 100 | 0 | IMP |  | 2
25 | eShopper | View the shopping cart | Basic Business Rules | MS | 3 |  | 3 | ECOM |  | 7 | -
26 | eShopper | View the shopping cart | Aurelia application code | BA / IC | 5 | 100 | 0 | Reference Site |  | 1 | 6
27 | eShopper | View the shopping cart | HTML/CSS | DG | 1 | 100 | 0 | Reference Site |  | 1 | 6
28 | eShopper | Complete checkout information | SOAP Service - Consumer.add | EP | 0.5 | 100 | 0 | ECOM |  | 5 | 1
29 | eShopper | Complete checkout information | REST Service - addConsumer | MS | 0.5 | 100 | 0 | IMP |  | 5 | 2
30 | eShopper | Complete checkout information | SOAP Service - Consumer.update | MS | 1 | 100 | 0 | ECOM |  | 1 | 3
31 | eShopper | Complete checkout information | REST Service - updateConsumer | MS | 1 | 100 | 0 | IMP |  | 1 | 4
32 | eShopper | Complete checkout information | Basic Business Rules | EP | 1 |  | 1 | ECOM |  | 7 | -
33 | eShopper | Complete checkout information | Aurelia application code | BA / IC | 2 | 100 | 0 | Reference Site |  | 1 | 7
34 | eShopper | Complete checkout information | HTML/CSS | DG | 1 | 100 | 0 | Reference Site |  | 1 | 7
35 | eShopper | Purchase | ESOM Authorise (SOAP) Integration | AP / AS | 2 | 100 | 0 | IMP |  | 1 | 1
36 | eShopper | Purchase | POST to Paypal via ESOM | AP / AS | 1 | 100 | 0 | IMP |  | 1 | 2
37 | eShopper | Purchase | eShop Review Service (accepts HTTP POST) | AS | 1 | 100 | 0 | IMP |  | 1 | 3
38 | eShopper | Purchase | eShop SOAP Service to update Payment Reference | AS | 2 | 100 | 0 | IMP |  | 1 | 4
39 | eShopper | Purchase | ESOM charge (SOAP) integration | AP / AS | 2 | 100 | 0 | IMP |  | 1 | 5
40 | eShopper | Purchase | Handle payment failure | AS | 1 | 100 | 0 | IMP |  | 1 | 6
41 | eShopper | Purchase | Handle payment success | AS | 1 | 100 | 0 | IMP |  | 1 | 7
42 | eShopper | Purchase | SOAP Service - Address.add | EP | 1 | 100 | 0 | ECOM |  | 1 | 5
43 | eShopper | Purchase | REST Service - addAddress | EP | 1 | 100 | 0 | IMP | May not be needed - check with Andrei | 1 | 6
44 | eShopper | Purchase | SOAP Service - Address.update | EP | 0.5 | 100 | 0 | ECOM |  | 1 | 7
45 | eShopper | Purchase | REST Service - updateAddress | EP | 0.5 | 100 | 0 | IMP | May not be needed - check with Andrei | 1 | 8
46 | eShopper | View the Summary | SOAP Service - Consumer.get | MS | 0.5 | 100 | 0 | ECOM |  | 1 | 9
47 | eShopper | View the Summary | SOAP Service - Address.get | EP | 0.5 | 100 | 0 | ECOM |  | 1 | 10
48 | eShopper | View the Summary | SOAP Service - Cart.get | EP | 0.5 | 100 | 0 | ECOM |  | 1 | 8
49 | eShopper | View the Summary | REST Service - getConsumer | MS | 0.5 | 100 | 0 | IMP |  | 1 | 11
50 | eShopper | View the Summary | REST Service - getAddress | EP | 0.5 | 100 | 0 | IMP |  | 1 | 12
51 | eShopper | View the Summary | REST Service - getCart | EP | 0.5 | 100 | 0 | IMP |  | 1 | 9
52 | eShopper | View the Summary | Aurelia application code | BA / IC | 2 | 100 | 0 | Reference Site |  | 1 | 8
53 | eShopper | View the Summary | HTML/CSS | DG | 0.5 | 100 | 0 | Reference Site |  | 1 | 8
54 | eShopper | View the Summary | OMS CreateOrder (SOAP) Integration | EP | 3 | 100 | 0 | ECOM |  | 2 | 10
55 | eShopper | View the Summary | ESOM getPaymentDetails (SOAP) Integration | AS | 2 | 100 | 0 | IMP |  | 1 | 8
56 | eShopper | View the confirmation email | HTML/CSS | DG | 0.5 | 100 | 0 | IMP |  | 1 | 9
57 | eShopper | View the confirmation email | ESOM Send Comms (SOAP) Integration | EP | 3 | 100 | 0 | ECOM |  | 1 | 13
59 | PIM | Log in to Optimus | Ensure Logout button works | MG | 0.25 |  | 0.25 | PIM |  | 7
60 | PIM | Navigate to the PIM | Fine-tune layout | GM | 2 |  | 2 | PIM |  | 7
61 | PIM | Navigate to the PIM | Ensure links/pages/sites are protected | AS | 5 |  | 5 | PIM |  | 7
62 | PIM | Navigate to the PIM | Test Data | MG | 0.5 |  | 0.5 | PIM |  | 7
63 | PIM | List the available products | Update Product Listing Page to display primary product image | AS | 1 |  | 1 | PIM |  | 7
64 | PIM | List the available products | Test Data | MG / ASH | 2 | 100 | 0 | PIM |  | 1
65 | PIM | Select a product and view the details | Implement Primefaces components inline with new design | DG | 2 |  | 2 | PIM |  | 7
66 | PIM | Select a product and view the details | Update product page to new design | AS | 3 |  | 3 | PIM |  | 7
67 | PIM | Select a product and view the details | Create Primefaces controls for product properties | DG | 1 |  | 1 | PIM |  | 7
68 | PIM | Select a product and view the details | Complete Product Property Control Rendering | AS | 2 |  | 2 | PIM |  | 7
69 | PIM | Approve and Publish the Update the Product change | Copy product images to CDN | AS | 2 |  | 2 | PIM |  | 7
70 | PIM | List available offerings | Update to include primary offering image | AS | 1 |  | 1 | PIM |  | 7
71 | PIM | List available offerings | Test Data | MG | 1 | 100 | 0 | PIM |  | 1
72 | PIM | Select an offering and view the details | Implement Primefaces components inline with new design | DG | 1 |  | 1 | PIM |  | 7
73 | PIM | Select an offering and view the details | Update offering page to new design | AS | 3 |  | 3 | PIM |  | 7
74 | PIM | Select an offering and view the details | Complete Offering Property Control Rendering | AS | 1 |  | 1 | PIM |  | 7
75 | PIM | Select an offering and view the details | Deep-link View Offering Modal for OMS Integration | AS | 2 | 100 | 0 | PIM |  | 3
76 | PIM | Update the price of the offering | Create new price record on each change when offering is live | AS | 2 |  | 2 | PIM |  | 7
77 | PIM | Approve and Publish the Update the Offering change | Copy offering images to CDN | AS | 2 |  | 2 | PIM |  | 7
78 | OMS | Log in to Optimus | Upgrade KeyCloak to version 1.4 | EP | 1 | 100 | 0 | OMS |  | 3
79 | OMS | Log in to Optimus | Upgrade KC templates | VR | 2.5 | 100 | 0 | OMS |  | 3
80 | OMS | Log in to Optimus | I18N support in KC enabled | PI | 1 | 100 | 0 | OMS | Translations still needed | 3
81 | OMS | Log in to Optimus | Ensure Logout button works | PI | 0.25 | 100 | 0 | OMS |  | 3
82 | OMS | Log in to Optimus | Account Management screen | PI | 0.5 | 100 | 0 | OMS |  | 3
83 | OMS | Log in to Optimus | Test Data | AP | 0.5 | 100 | 0 | OMS |  | 6
84 | OMS | Navigate to the OMS | Fine-tune layout | MS | 2 |  | 2 | OMS |  | 7
85 | OMS | Navigate to the OMS | Dashboard - ensure it's working | EP/PI | 0.5 | 100 | 0 | OMS | Background change still missing / Dashboard should be a starting page | 4
86 | OMS | Navigate to the OMS | Re-confiure roles | PI | 0.5 | 100 | 0 | OMS |  | 4
87 | OMS | Navigate to the OMS | Ensure links/pages/sites/actions are protected | MS/AP | 5 | 10 | 4.5 | OMS |  | 7
89 | OMS | List the current Orders | Resolve WS Security Roles issue | AP | 5 | 25 | 3.75 | OMS |  | 7
90 | OMS | List the current Orders | Advanced search - fix | EP | 0.5 | 100 | 0 | OMS |  | 4
91 | OMS | List the current Orders | Test Data | PI/AP | 0.5 | 15 | 0.425 | OMS |  | 6
92 | OMS | Select an Order and view the details | Fix the payment tab in order details | AP / MS | 0.5 | 100 | 0 | OMS | Needs to be fixed to show only when Payment is enabled / Payment data available | 4
94 | OMS | Update the Order | ERP Status Update - basic | EP | 1 | 100 | 0 | OMS |  | 4
95 | OMS | Update the Order | Standard Delivery flow | EP | 1 | 100 | 0 | OMS |  | 4
96 | OMS | Update the Order | Update KIE Workbench | EP | 0.25 |  | 0.25 | OMS |  | 7
97 | OMS | Update the Order | ERP Status Update - generic | AP | 2.5 |  | 2.5 | OMS |  | 7
98 | OMS | Update the Order | Saving comment and updating by WIH | EP | 1.5 | 100 | 0 | OMS |  | 5
99 | OMS | Update the Order | Quartz scheduler improvements | EP | 1 |  | 1 | OMS |  | 7
100 | OMS | Update the Order | Other test data | AP | 0.5 |  | 0.5 | OMS |  | 7
101 | OMS | Show Order Despatch Messaging | Store tracking reference from ERP | AP | 1 | 100 | 0 | OMS |  | 5
102 | OMS | Show Order Despatch Messaging | Configure sending e-mails | AP | 1 | 100 | 0 | OMS | Issue with Yahoo | 4
103 | OMS | Show Order Despatch Messaging | Prepare e-mail templates | DG | 1 | 100 | 0 | OMS |  | 4
104 | OMS | Show Order Despatch Messaging | Other test data | AP | 0.5 |  | 0.5 | OMS |  | 7
105 | eShopper | View the confirmation page | HTML/CSS | DG | 0.5 | 100 | 0 | Reference Site |  | 1
106 | eShopper | Complete the journey | Aurelia application code | BA / IC | 0.5 | 100 | 0 | Reference Site |  | 1
107 | eShopper | Complete the journey | Set the Cart Status to completed and rotate the session | MG/ EP | 1 | 100 | 0 | IMP |  | 1
108 | eShopper | Complete checkout information | Persist Cart in session | MS | 2 | 100 | 0 | IMP |  | 1
109 | eShopper | Complete checkout information | Persist Consumer in session | MS | 1 | 100 | 0 | IMP |  | 1
110 | eShopper | Complete checkout information | Persist Addresses in session | MS | 1 | 100 | 0 | IMP |  | 1
112 | eShopper | Test harness creation for session init | Implementation | BA / IC | 2 | 100 | 0 | IMP |  | 1

## Sheet1
eShopper | JOURNEY STEP | 1 |  |  | 2 |  |  | 3 |  |  | 4 |  |  | 5 |  |  | 6 |  |  | 7 |  |  | 8 |  |  | 9 |  |  | 10
| Activity | View the home page | Owner | Duration | Navigate to a list of products | Owner | Duration | Select a product based upon the filter | Owner | Duration | View the product detail, viewing each of the tabs | Owner | Duration | Select the product for the shopping cart | Owner | Duration | View the shopping cart | Owner | Duration | Complete checkout information | Owner | Duration | Purchase | Owner | Duration | View the Summary | Owner | Duration | View the confirmation email | Owner | Duration
| Sub Activities | Aurelia application code | BA | 2 | REST service to return all offerings inc pagination | GM | 2 | REST service to return all offerings filtered and sorted | GM | 2 | REST Service to return single offering | GM | 2 | REST Service - addToCart | SY | 0.5 | REST Service - removeFromCart | SY | 0.5 | REST Service - addConsumer | GM | 0.5 | ESOM Authorise (SOAP) Integration | AS | 2 | REST Service - getConsumer | GM | 0.5 | HTML/CSS | DG | 1
|  | HTML/CSS | DG | 2 | Aurelia application code | BA | 3 | REST service to provide filters | GM | 3 | Aurelia application code | BA | 3 | SOAP Service - addToCart | SY | 0.5 | SOAP Service - removeFromCart | SY | 0.5 | SOAP Service - Consumer.add | GM | 0.5 | POST to Paypal via ESOM | AS | 1 | REST Service - getAddress | GM | 0.5 | ESOM Send Comms (SOAP) Integration | SY | 3
[5 empty] | HTML/CSS | DG | 2 | Aurelia application code | BA | 2 | HTML/CSS | DG | 2 | REST Service - initialiseCart | SY | 0.5 | REST Service - updateQuantity | SY | 0.5 | REST Service - updateConsumer | GM | 0.5 | eShop Review Service (accepts HTTP POST) | AS | 1 | REST Service - getCart | GM | 0.5
[8 empty] | HTML/CSS | DG | 2 |  |  |  | SOAP Service - initialiseCart | SY | 0.5 | SOAP Service - updateQuantity | SY | 0.5 | SOAP Service - Consumer.update | GM | 0.5 | eShop SOAP Service to update Payment Reference | AS | 2 | SOAP Service - Consumer.get | GM | 0.5
[14 empty] | Basic Business Rules | SY | 2 | REST Service - emptyCart | SY | 0.5 | Basic Business Rules | GM | 1 | ESOM charge (SOAP) integration | AS | 2 | SOAP Service - Address.get | GM | 0.5
[14 empty] | Aurelia application code | BA | 2 | SOAP Service - emptyCart | SY | 0.5 | Aurelia application code | BA | 2 | Handle payment failure | AS | 1 | SOAP Service - Cart.get | GM | 1
[17 empty] | Basic Business Rules | SY | 3 | HTML/CSS | DG | 2 | Handle payment success | AS | 1 | Aurelia application code | BA | 2
[17 empty] | Aurelia application code | BA | 5 |  |  |  | REST Service - addAddress | SY | 1 | HTML/CSS | DG | 2
[17 empty] | HTML/CSS | DG | 2 |  |  |  | SOAP Service - Address.add | SY | 0.5 | OMS CreateOrder (SOAP) Integration | ? | 3
[23 empty] | REST Service - updateAddress | SY | 1 | ESOM getPaymentDetails (SOAP) | GM | 2
[23 empty] | SOAP Service - Address.update | SY | 0.5
PIM | JOURNEY STEP | 1 |  |  | 2 |  |  | 3 |  |  | 4 |  |  | 5 |  |  | 6 |  |  | 7 |  |  | 8 |  |  | 9 |  |  | 10
| Activity | Log in to Optimus | Owner | Duration | Navigate to the PIM | Owner | Duration | List the available products | Owner | Duration | Select a product and view the details | Owner | Duration | Update the product | Owner | Duration | Approve and Publish the Update the Product change | Owner | Duration | List available offerings | Owner | Duration | Select an offering and view the details | Owner | Duration | Update the price of the offering | Owner | Duration | Approve and Publish the Update the Offering change | Owner | Duration
| Sub Activities | Enable security | MG | 0.5 | no tasks |  |  | Update Product Listing Page to display primary product image | AS | 1 | Implement Primefaces components inline with new design | DG | 2 | no tasks - same as create / view |  |  | Copy product images to CDN | AS | 2 | Update to include primary offering image | AS | 1 | Implement Primefaces components inline with new design | DG | 1 | Create new price record on each change when offering is live | AS | 2 | Copy offering images to CDN | AS | 2
[11 empty] | Update product page to new design | AS | 3 | [9 empty] | Update offering page to new design | AS | 3
[11 empty] | Create Primefaces controls for product properties | DG | 1 | [9 empty] | Complete Offering Property Control Rendering | AS | 1
[11 empty] | Complete Product Property Control Rendering | AS | 2 | [9 empty] | Deep-link View Offering Modal for OMS Integration | AS | 2