## Plan
Sabre 2:0 Test Plan | [8 empty] | Nonimal Flow Testing |  |  | Operational Readiness Testing
Categories | Subject | HLR Ref v2 | HLR Page | HLD Ref | HDL Page | Owner | 2016-02-15 | 2016-02-22 | 2016-02-29 | 2016-03-07 | 2016-03-14 | 2016-03-21 | 2016-03-28 | Dependencies
Test Strategy | Overview of Test Method, Documents, etc. | n/a | n/a | n/a |  | David
Ecommerce Module | Website Customer Journey through to Payment and Fulfilment | 4.2 | 5 | tbc |  | Geani | 2016-02-15: Test Case; 2016-02-29: Nominal Testing; 2016-03-21: OR Testing
| Home Page | 4.4 | 7 | tbc |  | Geani | 2016-02-15: Test Case; 2016-02-29: Nominal Testing; 2016-03-21: OR Testing
| Header, footer and menu navigation | 4.5 | 9 | tbc |  | Geani | 2016-02-15: Test Case; 2016-02-29: Nominal Testing; 2016-03-21: OR Testing
| Category, Product Listing and Filter Options | 4.6 | 10 | tbc |  | Geani | 2016-02-15: Test Case; 2016-02-29: Nominal Testing; 2016-03-21: OR Testing
| Product/Bundle Details | 4.7 | 17 | tbc |  | Geani | 2016-02-15: Test Case; 2016-02-29: Nominal Testing; 2016-03-21: OR Testing
| Shopping Basket | 4.8 | 18 | tbc |  | Geani | 2016-02-15: Test Case; 2016-02-29: Nominal Testing; 2016-03-21: OR Testing
| Checkout | 4.9 | 21 | tbc |  | Geani | 2016-02-15: Test Case; 2016-02-29: Nominal Testing; 2016-03-21: OR Testing | Dummy/Tessting Credit Card/Bank account
| Payment Page | 4.1 | 23 | tbc |  | Geani | 2016-02-15: Test Case; 2016-02-29: Nominal Testing; 2016-03-21: OR Testing
| Order Confirmation Page | 4.11 | 25 | tbc |  | Geani | 2016-02-15: Test Case; 2016-02-29: Nominal Testing; 2016-03-21: OR Testing
| Static Content/Information Pages | 4.12 | 28 | tbc |  | Geani | 2016-02-15: Test Case; 2016-02-29: Nominal Testing; 2016-03-21: OR Testing
| FAQ | 4.13 | 28 | tbc |  | Geani | 2016-02-15: Test Case; 2016-02-29: Nominal Testing; 2016-03-21: OR Testing
| Site Map | 4.14 | 28 | tbc |  | Geani | 2016-02-15: Test Case; 2016-02-29: Nominal Testing; 2016-03-21: OR Testing
| Site Analytics Integration | 4.15 | 28 | tbc |  | Geani | 2016-02-15: Test Case; 2016-02-29: Nominal Testing; 2016-03-21: OR Testing
| Vouchers / Promotional Codes | 4.16 | 29 | tbc |  | Geani | 2016-02-15: Test Case; 2016-02-29: Nominal Testing; 2016-03-21: OR Testing
| Trade-Ins | 4.17 | 32 | tbc |  | Geani | 2016-02-15: Test Case; 2016-02-29: Nominal Testing; 2016-03-21: OR Testing
| Affiliate | 4.19 | 37 | tbc |  | Geani | 2016-02-15: Test Case; 2016-02-29: Nominal Testing; 2016-03-21: OR Testing
| Employee Partner Portal (EPP) | 4.19 | 37 | tbc |  | Geani | 2016-02-15: Test Case; 2016-02-29: Nominal Testing; 2016-03-21: OR Testing | EPP accounts
| Requirement Specifications: Generic | 5 | 42 | tbc |  | Geani | 2016-02-15: Test Case; 2016-02-29: Nominal Testing; 2016-03-21: OR Testing
SIT Testing | System integration | tbc | tbc | tbc |  | tbc | [7 empty] | Details tbc
PIM |  | tbc | tbc | tbc |  | Geani | 2016-02-22: Test Case; 2016-03-07: Nominal Testing (on going); 2016-03-21: OR Testing
OMS / ESOM |  | tbc | tbc | tbc |  | Geani | 2016-02-29: Test Case; 2016-03-14: Testing; 2016-03-28: OR Testing
Sage X3 (ERP) |  | tbc | tbc | tbc |  | tbc
Sabre 1 (Exp) Bugs & Fixes | Ensure they haven't been duplicated | tbc | tbc | tbc |  | Geani | 2016-03-14: Test Case; 2016-03-21: Testing; 2016-03-28: OR Testing
Change Requests |  | tbc | tbc | tbc |  | Geani | 2016-03-14: Test Case; 2016-03-21: Testing; 2016-03-28: OR Testing

## Questions
Testing Questions
1 | IE 9 & IE 10 supported? Microsoft dropped suppoprt for IE 9 & IE 10.
2 | Dummy/Tessting Credit Card/Bank account?
3 | Geani to do SIT Testing?
4 | Sage X3 in Testing Scope for Geani's team?
5 | EPP accounts provided by Samsung or can be created by us ( for testing purposes)?