## VFT eShop Testing Feedback
VFT eShop Interim Testing - Feedback Form | [12 empty] | Version: |  |  |  | Date:
ID | Date | Priority | Raised by | Title | Functional, design, or content | Detailed Description | Type | Replication Steps | Page URL | Test Device / Tariff | Screenshot (next tab) | Bug / CR | PJM Status | Severity | Assigned to | PJM Owner | PJM Comments | PJM Date Resolved
1 | 2015-12-08 | p3 | Geani | Translation are missing | Content | Some text are missing translation on multiple pages. For example Product detail page, Tariff listing page |  |  |  |  | No | Bug | Open
2 | 2015-12-09 |  | Geani | Slide banner is not centered | Design | This issue was tested on both android and iOS devices and only occurs on mobile devices. The banner should be centered. Screenshot 1 |  | 1. Open home page on mobile devices 2. Notice that banner link type slide is not cenered | http://vodafonetr-stage.pjmedia.co.uk/ | http://vodafonetr-stage.pjmedia.co.uk/ | Yes | Bug | Closed |  |  | Viji |  | 2015-12-10
3 | 2015-12-09 |  | Geani | Slider overlap after rotating from portrait to landscape mode | Design | While rotatin the device in landscape mode and back, the slider will combine. Note that while rotating from portrait mode to landscape mode the slider whill move from its position. Screenshot 2 |  | 1. Open home page on mobile devices 2. rote device in landscape mode and back | http://vodafonetr-stage.pjmedia.co.uk/ | http://vodafonetr-stage.pjmedia.co.uk/ | Yes | Bug | Rejected |  |  | Viji | It's part of Simplicity design | 2015-12-10
4 | 2015-12-09 |  | Geani | Digital package is not added to SKU code on mobile devices | Functional | When buying a phone and selecting an digital package the SKU code is not modified. Notice that package price doesn't add to total price. Screenshot 3 |  | 1. Select a phone and a degital package 2. notice that SKU code is not modifed | Product details page | http://vodafonetr-stage.pjmedia.co.uk/handset/htc-one-m8s | Yes | Bug | Closed |  |  |  | Geani: Fixed
5 | 2015-12-09 |  | Geani | Tarrif filter text overlaps radio buttons | Design | Tarrif filter text overlaps radio buttons Screenshot 4 |  | 1. Reach Tariff listing page | http://vodafonetr-stage.pjmedia.co.uk/kampanyalar/tarifeler | http://vodafonetr-stage.pjmedia.co.uk/kampanyalar/tarifeler | Yes | Bug | Closed |  |  |  |  | 2015-12-11
6 | 2015-12-09 | P3 | Geani | Tariff filter keeps loading in background | Functional | On Tariff listing page if selecting "Post paid" filter then before the filter finish loading select "Pre to post" filter after the "Post paid" filter finished loading will replace "Pre to post" filter |  | 1. Reach Tariff listing page 2. Select Post paid and then select imediately Pre to post | http://vodafonetr-stage.pjmedia.co.uk/kampanyalar/tarifeler | http://vodafonetr-stage.pjmedia.co.uk/kampanyalar/tarifeler | No | Bug | Closed |  |  | Ionut | Geani: Fixed | 2015-12-11
7 | 2015-12-09 |  | Geani | Deselected aditional Tariff filters doesn't apply after pressing "Apply" button | Functional | After selecting an optional filter, it can’t be disabled unless pressing "clear all filters. |  | 1. Reach Tariff listing page 2. Select optional filter and press apply 3. Deselet optional filter and press Apply 4. Refresh page 5. Notice filter is still active | http://vodafonetr-stage.pjmedia.co.uk/kampanyalar/tarifeler | http://vodafonetr-stage.pjmedia.co.uk/kampanyalar/tarifeler | No | Bug | Closed |  |  | Ionut |  | 2015-12-11
8 | 2015-12-09 |  | Viji | Missing banner on Tariff page | Design | Banner is missing (Ref- t04-plan-listing-v4.html/handlisting page) |  | 1. Reach Tariff listing page | http://vodafonetr-stage.pjmedia.co.uk/kampanyalar/tarifeler | http://vodafonetr-stage.pjmedia.co.uk/kampanyalar/tarifeler | No | Bug | Closed |  |  |  |  | 2015-12-11
9 | 2015-12-09 |  | Viji |  | Design | Tariff table - Pre-paid (option) Contract duration column missing - (Ref- t04-plan-listing-v4.html) Screenshot 5 |  | 1. Reach Tariff listing page | http://vodafonetr-stage.pjmedia.co.uk/kampanyalar/tarifeler | http://vodafonetr-stage.pjmedia.co.uk/kampanyalar/tarifeler | Yes | Bug | Closed |  |  |  |  | 2015-12-11
10 | 2015-12-09 | P4 | Viji |  | Design | Tariff table - Filter section - left border misaligned, category left border touches the filter buttons- need top margin (Ref - handlisting filter section) Screenshot 6 |  | 1. Reach Tariff listing page | http://vodafonetr-stage.pjmedia.co.uk/kampanyalar/tarifeler | http://vodafonetr-stage.pjmedia.co.uk/kampanyalar/tarifeler | Yes | Bug | Open |  |  | Doug/Bill
11 | 2015-12-09 | P4 | Viji |  | Design | Filter section - outer border and background color is missing / looks different from Handset listing filter section Screenshot 7 |  | 1. Reach Tariff listing page | http://vodafonetr-stage.pjmedia.co.uk/kampanyalar/tarifeler | http://vodafonetr-stage.pjmedia.co.uk/kampanyalar/tarifeler | Yes | Bug | Open |  |  | Doug/Bill
12 | 2015-12-09 | P2 | Viji |  | Design | Tariff Table - column name missing in Mobile view ( Ref-Screenshot) Refer- http://stage.vodafone-simplicity.dddev.io/vodafone-simplicity-v4.1/templates/eshop/t04-plan-listing.html Screenshot 8 |  | 1. Reach Tariff listing page | http://vodafonetr-stage.pjmedia.co.uk/kampanyalar/tarifeler | http://vodafonetr-stage.pjmedia.co.uk/kampanyalar/tarifeler | Yes | Bug | Open |  |  | Bill | Fixed Geani: Please see issue 17
13 | 2015-12-09 | P2 | Viji |  | Functional | Tariff table Tabs - Multiple radio buttons -selected (ref-screenshot) Screenshot 9 |  | 1. Reach Tariff listing page | http://vodafonetr-stage.pjmedia.co.uk/kampanyalar/tarifeler | http://vodafonetr-stage.pjmedia.co.uk/kampanyalar/tarifeler | Yes | Bug | Closed |  |  | Bill | Fixed (CMS issue) Geani: Confirmed as fixed | 2015-12-11
14 | 2015-12-09 |  | Viji |  | Design | Ne Öderim? - Table border missing, Empty content box needs to be removed in the table, Table row- Font should be bold Screenshot 10 |  | 1. Reach Tariff listing page | http://vodafonetr-stage.pjmedia.co.uk/kampanyalar/tarifeler | http://vodafonetr-stage.pjmedia.co.uk/kampanyalar/tarifeler | Yes | Bug | Closed |  |  | Bill | Fixed | 2015-12-11
15 | 2015-12-09 |  | Viji |  | Design | Footer should be full- width,pl refer Handlisting page, pl see the screenshot Screenshot 11 |  | 1. Reach Tariff listing page | http://vodafonetr-stage.pjmedia.co.uk/kampanyalar/tarifeler | http://vodafonetr-stage.pjmedia.co.uk/kampanyalar/tarifeler | Yes | Bug | Closed |  |  |  |  | 2015-12-11
16 | 2015-12-06 | P2 | Geani | "Buy now" button doesn't work | Functional | "Buy now" button does nothing |  | 1. Reach accessories page 2. Reach accessorry produc page | Accesorry product details page | http://vodafonetr-stage.pjmedia.co.uk/accessories/apple-accessory | No | Bug | Hold
17 | 2015-12-11 | P2 | Geani | Trafiif details is out of screen on mobile devices | Design | Trafiif details is out of screen on mobile devices |  | 1. Reach tariff details page 2. Press Ne Oderim 3. Notice details are out of page on mobile devices. Tested on iPhone 4S | Tariff details page | http://vodafonetr-stage.pjmedia.co.uk/priceplans/red-small1/OfferingID/5D076C90-62D2-11E5-94F2000C29AF9363 | Yes | Bug | Open |  |  | Doug/Bill | nb: Content is html in CMS
18 | 2015-12-11 |  | Geani | Digital package selection generates wrgon sums | Functional | Digital package selection generates wrgon sums |  | 1. Open HT One M8s 2. select purple color 3. Select and deselect second digital product 4. Notice wrong sums | Product details page | http://vodafonetr-stage.pjmedia.co.uk/handset/htc-one-m8s | Yes | Bug | Closed |  |  | Ionut | Geani: Fixed | 2015-12-11
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35

## Screenshots
Please provide screenshots here for relevant defects:
ID | Screenshot
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
`

## Data Validation (hidden)
Functional
Design
Content
Bug
CR
Open
Closed
In Progress
Hold
Rejected
Yes
No