## October 2015 (hidden)
Service Capacity Management (SCM)
Hours per day Legend: | Bold = confirmed
Red = unconfirmed
SCM | Release Date | Tester | Total | 2015-09-28 | 2015-09-29 | 2015-09-30 | 2015-10-01 | 2015-10-02 | 2015-10-03 | 2015-10-04 | 2015-10-05 | 2015-10-06 | 2015-10-07 | 2015-10-08 | 2015-10-09 | 2015-10-10 | 2015-10-11 | 2015-10-12 | 2015-10-13 | 2015-10-14 | 2015-10-15 | 2015-10-16 | 2015-10-17 | 2015-10-18 | 2015-10-19 | 2015-10-20 | 2015-10-21 | 2015-10-22 | 2015-10-23 | 2015-10-24 | 2015-10-25 | 2015-10-26 | 2015-10-27 | 2015-10-28 | 2015-10-29 | 2015-10-30 | 2015-10-31 | 2015-11-01
Projects
Vodafone Qatar Retainer
iPhone 6S Preorder | 2nd October? | Ionut | 30 | 2015-09-28: 8; 2015-09-29: 8; 2015-09-30: 8; 2015-10-01: 6
API trade In | 5 - 8 October? | Geani | 16 | 2015-09-28: 4; 2015-09-29: 4; 2015-09-30: 4; 2015-10-01: 4
4g+ Revamp | 2015-09-30 | Geani | 6 | 2015-09-28: 4; 2015-09-29: 2
BAU - Website updates ticket #5150 |  | Ionut | 16 | 2015-10-13: 8; 2015-10-14: 8
Tickets, Bugs and Fixes, Regression |  | Ionut | 88 | 2015-10-01: 2; 2015-10-05: 8; 2015-10-06: 8; 2015-10-07: 8; 2015-10-08: 6; 2015-10-12: 8; 2015-10-15: 8; 2015-10-19: 8; 2015-10-20: 8; 2015-10-21: 8; 2015-10-22: 8; 2015-10-23: 8; 2015-10-26: 8; 2015-10-27: 8; 2015-10-28: 8; 2015-10-29: 8; 2015-10-30: 8
Tickets, Bugs and Fixes, Regression |  | Geani | 2 | 2015-10-01: 2
Release to Production Support |  | Ionut | 8 | 2015-10-02: 8
Release to Production Support |  | Geani | 28 | 2015-09-30: 4; 2015-10-02: 8; 2015-10-15: 8; 2015-10-16: 8
Release to Production Support |  | Adinel | 4 | 2015-10-08: 4
Redesign of store locator page | 5 - 8 October? | Ionut | 0
Sunday Support |  | Ionut | 8 | 2015-10-18: 8
Sunday Support |  | Adinel | 16 | 2015-10-04: 8; 2015-10-25: 8
Sunday Support |  | Geani | 8 | 2015-10-11: 8; 2015-11-01: 8
Other |  | TBC | 0
Vodafone Strategic
|  | Adinel | 0
DTAC Retainer
Sort package prices | 2015-10-07 | Geani | 8 | 2015-09-29: 1; 2015-10-01: 1; 2015-10-05: 2; 2015-10-06: 2; 2015-10-07: 2
Delivery to store | 2015-10-07 | Geani | 8 | 2015-09-29: 1; 2015-10-01: 1; 2015-10-05: 2; 2015-10-06: 2; 2015-10-07: 2
Other |  | Geani | 32 | 2015-10-05: 4; 2015-10-06: 4; 2015-10-07: 4; 2015-10-08: 4; 2015-10-19: 8; 2015-10-21: 8; 2015-10-26: 8; 2015-10-27: 8; 2015-10-28: 8
DTAC Strategic
DTAC CR 17 |  | TBC | 0
DTAC CR 3 |  | Adinel | 29 | 2015-10-05: 3; 2015-10-06: 3; 2015-10-07: 3; 2015-10-08: 3; 2015-10-09: 3; 2015-10-12: 6; 2015-10-14: 4; 2015-10-15: 4
DTAC CR 6 |  | Adinel | 3 | 2015-09-28: 2; 2015-09-29: 1
DTAC CR 18 |  | TBC | 0
DTAC CR16 |  | Adinel | 0
Tickets, Bugs and Fixes |  | Geani
Tickets, Bugs and Fixes |  | Adinel | 0
Other |  | TBC | 0
Optimus
OMS |  | Adinel | 11 | 2015-09-28: 2; 2015-09-29: 2; 2015-09-30: 2; 2015-10-01: 2; 2015-10-07: 1; 2015-10-08: 1; 2015-10-09: 1
Core |  | Adinel | 0
REFSITE |  | Adinel | 10 | 2015-09-28: 2; 2015-09-29: 2; 2015-09-30: 2; 2015-10-01: 2; 2015-10-05: 2
0
Google
Google - Reverse Logistics Carriers |  | Adinel | 0
Google - Weiss Rohlig Carrier |  | Adinel | 10 | 2015-10-12: 2; 2015-10-14: 4; 2015-10-15: 4
Google - EasyVan Development |  | Adinel | 0
Vodafone Turkey Interim
Internal testing/UAT Support |  | Adinel | 0
Performance Testing |  | Adinel | 0
Samsung
Sabre - Exploratory Testing/Automation |  | Adinel | 17 | 2015-09-28: 2; 2015-09-29: 3; 2015-09-30: 2; 2015-10-01: 2; 2015-10-05: 2; 2015-10-06: 2; 2015-10-07: 2; 2015-10-08: 1; 2015-10-09: 1
Store Locator |  | Adinel | 40 | 2015-10-06: 2; 2015-10-07: 2; 2015-10-08: 2; 2015-10-09: 2; 2015-10-20: 8; 2015-10-21: 8; 2015-10-22: 8; 2015-10-23: 8; 2015-10-27: 8; 2015-10-28: 8; 2015-10-29: 8
Performance Testing |  | Adinel | 14 | 2015-09-30: 2; 2015-10-01: 2; 2015-10-08: 1; 2015-10-09: 1; 2015-10-13: 8
Digicel Phase 2
|  | TBC | 0
|  | TBC | 0
Digicel Retainer
|  | Adinel | 2 | bar: 2015-10-05 to 2015-10-06
|  | TBC | 0
Innodoo
Translations |  | Geani | 48 | 2015-10-12: 8; 2015-10-13: 8; 2015-10-14: 8; 2015-10-19: 8; 2015-10-20: 8; 2015-10-22: 8
Holiday |  | Adinel | 8 | 2015-10-16: 8
Holiday |  | Geani | 0
Holiday |  | Ionut | 10 | 2015-10-08: 2; 2015-10-09: 8
Total |  | Adinel (Total) | 160 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8
Total |  | Geani (Total) | 152 | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 |  |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8
Total |  | Ionut (Total) | 168 | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  | 8 | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8
Grand Total |  |  | 480
Total Capacity |  |  |  | 24 | 24 | 24 | 24 | 16 | 0 | 8 | 24 | 24 | 24 | 24 | 16 | 0 | 8 | 24 | 24 | 24 | 24 | 16 | 0 | 8 | 24 | 24 | 24 | 24 | 16 | 0 | 8 | 16 | 24 | 24 | 16 | 8 | 0 | 8
Spare Capacity |  |  |  | 0 | 0 | 0 | 0 | N/A |  |  | 0 | 0 | 0 | 0 | N/A |  |  | 0 | 0 | 0 | 0 | N/A |  |  | 0 | 0 | 0 | 0 | N/A |  |  | 8 | 0 | 0 | 8 | N/A

## November 2015 (hidden)
Service Capacity Management (SCM)
Hours per day Legend: | Bold = confirmed
Red = unconfirmed
SCM | Release Date | Tester | Total | 2015-11-02 | 2015-11-03 | 2015-11-04 | 2015-11-05 | 2015-11-06 | 2015-11-07 | 2015-11-08 | 2015-11-09 | 2015-11-10 | 2015-11-11 | 2015-11-12 | 2015-11-13 | 2015-11-14 | 2015-11-16 | 2015-11-16 | 2015-11-17 | 2015-11-18 | 2015-11-19 | 2015-11-20 | 2015-11-21 | 2015-11-22 | 2015-11-23 | 2015-11-24 | 2015-11-25 | 2015-11-26 | 2015-11-27 | 2015-11-28 | 2015-11-29
Projects
Vodafone Qatar Retainer
iPhone 6S Preorder | 2nd October? | Ionut | 0
API trade In | 5 - 8 October? | Geani | 0
4g+ Revamp | 2015-09-30 | Geani | 0
BAU - Website updates ticket #5150 |  | Ionut | 0
Tickets, Bugs and Fixes, Regression |  | Ionut | 120 | 8 | 8 | 8 | 8 |  |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | [5 empty] | 8 | 8 | 8 | 8
Tickets, Bugs and Fixes, Regression |  | Geani | 34 | 4 | 4 |  |  | 2 |  |  | 8 | 4 | 4 | 4 | 4
Release to Production Support |  | Ionut | 0
Release to Production Support |  | Geani | 0
Release to Production Support |  | Adinel | 0
Redesign of store locator page | 5 - 8 October? | Ionut | 0
Sunday Support |  | Ionut | 16 | [6 empty] | 8 | [20 empty] | 8
Sunday Support |  | Adinel | 8 | [13 empty] | 8
Sunday Support |  | Geani | 8 | [20 empty] | 8
Other |  | TBC | 0
Vodafone Strategic
VFQ RA Express Project |  | Adinel | 4 | [16 empty] | 2 | 2
VFQ Enterprise Bill Template & VAS |  | Adinel | 30 | 2 | [14 empty] | 2 | 2 | 4 |  |  |  | 4 | 4 | 4 | 4 | 4
VFQ Real Time Sim Provisioning (ECR2) |  | Adinel | 8 | [15 empty] | 2 | 4 | 2
DTAC Retainer
Sort package prices | 2015-10-07 | Geani | 0
Delivery to store | 2015-10-07 | Geani | 0
Other |  | Geani | 0
DTAC Strategic
DTAC CR 17 |  | TBC | 0
DTAC CR 3 |  | Adinel | 4 | 4
DTAC CR 6 |  | Adinel | 12 | [14 empty] | 8 | 4
DTAC CR 18 |  | TBC | 0
DTAC CR16 |  | Adinel | 32 |  | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4
Tickets, Bugs and Fixes |  | Geani | 6 |  | 2 | 2 | 2
Tickets, Bugs and Fixes |  | Adinel | 0
Other |  | TBC | 0
Optimus
OMS |  | Adinel | 8 | [18 empty] | 8
Core |  | Adinel | 0
OMS |  | Geani | 32 | [8 empty] | 4 | 4 | 4 | 4 |  |  | 4 | 4 | 4 | 4
REFSITE |  | Adinel | 20 | [21 empty] | 4 | 4 | 4 | 4 | 4
OMS |  | Geani | 36 | [14 empty] | 4 | 4 | 4 | 4 |  |  |  | 4 | 4 | 4 | 4 | 4
PIM |  | Adinel | 46 |  | 4 | 4 | 4 | 4 |  |  | 4 | 2 | 2 | 2 | [10 empty] | 4 | 4 | 4 | 4 | 4
Google
Google - Reverse Logistics Carriers |  | Adinel | 6 | [8 empty] | 2 | 2 | 2
Google - EDI |  | Adinel | 0
Google - Weiss Rohlig Carrier |  | Adinel | 0
Google - EasyVan Development |  | Adinel | 0
Vodafone Turkey Interim
Internal testing/UAT Support |  | Geani | 24 | 4 | 2 | 6 | 6 | 6
Performance Testing |  | Adinel | 0
Samsung
Sabre - Exploratory Testing/Automation |  | Adinel | 0
Store Locator |  | Adinel | 0
Performance Testing |  | Adinel | 0
Digicel Phase 2
|  | TBC | 0
|  | TBC | 0
Digicel Retainer
|  | Adinel | 0
|  | TBC | 0
Innodoo
Translations |  | Geani | 0
Holiday |  | Adinel | 2 | 2
Holiday |  | Geani | 0
Holiday |  | Ionut | 24 | [16 empty] | 8 | 8 | 8
Total |  | Adinel (Total) | 0
Total |  | Geani (Total) | 0
Total |  | Ionut (Total) | 0
Grand Total |  |  | 0
Total Capacity |  |  |  | 24 | 24 | 24 | 24 | 16 | 0 | 8 | 24 | 24 | 24 | 24 | 16 | 0 | 8 | 24 | 24 | 24 | 24 | 16 | 0 | 8 | 24 | 24 | 24 | 24 | 16 | 0 | 8
Spare Capacity |  |  |  | 0 | 0 | 0 | 0 | N/A |  |  | 0 | 0 | 0 | 0 | N/A |  |  | 0 | 0 | 0 | 0 | N/A |  |  | 0 | 0 | 0 | 0 | N/A

## December 2015 (hidden)
Service Capacity Management (SCM)
Hours per day Legend: | Bold = confirmed |  | national holyday
Red = unconfirmed
SCM | Release Date | Tester | Total | 2015-11-30 | 2015-12-01 | 2015-12-02 | 2015-12-03 | 2015-12-04 | 2015-12-05 | 2015-12-06 | 2015-12-07 | 2015-12-08 | 2015-12-09 | 2015-12-10 | 2015-12-11 | 2015-12-12 | 2015-12-13 | 2015-12-14 | 2015-12-15 | 2015-12-16 | 2015-12-17 | 2015-12-18 | 2015-12-19 | 2015-12-20 | 2015-12-21 | 2015-12-22 | 2015-12-23 | 2015-12-24 | 2015-12-25 | 2015-12-26 | 2015-12-27 | 2015-12-28 | 2015-12-29 | 2015-12-30 | 2015-12-31 | 2016-01-01 | 2016-01-02 | 2016-01-03
Projects
Vodafone Qatar Retainer
Tickets, Bugs and Fixes, Regression |  | Ionut | 128 | 2015-12-02: 8; 2015-12-03: 8; 2015-12-04: 8; 2015-12-07: 8; 2015-12-08: 8; 2015-12-09: 8; 2015-12-10: 8; 2015-12-14: 8; 2015-12-15: 8; 2015-12-16: 8; 2015-12-17: 8; 2015-12-18: 8; 2015-12-21: 8; 2015-12-22: 8; 2015-12-23: 8; 2015-12-24: 8
Tickets, Bugs and Fixes, Regression |  | Geani | 8 | 2015-12-14: 4; 2015-12-16: 2; 2015-12-17: 2
Tickets, Bugs and Fixes, Regression |  | Stefan | 64 | 2015-12-14: 8; 2015-12-15: 4; 2015-12-16: 6; 2015-12-17: 6; 2015-12-18: 8; 2015-12-21: 8; 2015-12-22: 8; 2015-12-23: 8; 2015-12-24: 8
Release to Production Support |  | Ionut | 0
Release to Production Support |  | Geani | 0
Release to Production Support |  | Stefan | 0
Sunday Support |  | Ionut | 8 | 2015-12-13: 8; 2016-01-03: 8
Sunday Support |  | Geani | 24 | 2015-12-06: 8; 2015-12-20: 8; 2015-12-27: 8
Sunday Support |  | Stefan | 0
Other |  | TBC | 0
Vodafone Strategic
VFQ RA Express Project |  | Geani | 0
VFQ Enterprise Bill Template & VAS |  | Geani | 0
VFQ Real Time Sim Provisioning (ECR2) |  | Geani | 0
DTAC Retainer
Sort package prices |  | Geani | 0
Delivery to store |  | Geani | 0
Other |  | Geani | 0
DTAC Strategic
DTAC CR 17 |  | TBC | 0
DTAC CR 3 |  | Geani | 0
DTAC CR 6 |  | Geani | 0
DTAC CR 18 |  | TBC | 0
DTAC CR16 |  | Geani | 0
Tickets, Bugs and Fixes |  | Geani | 0
Tickets, Bugs and Fixes |  | Geani | 0
Other |  | TBC | 0
Optimus
OMS |  | Geani | 0
Core |  | Geani | 0
OMS |  | Geani | 0
REFSITE |  | Geani | 0
OMS |  | Stefan | 0
PIM |  | Geani | 48 | 2015-12-02: 4; 2015-12-03: 4; 2015-12-07: 2; 2015-12-08: 2; 2015-12-09: 2; 2015-12-10: 2; 2015-12-11: 2; 2015-12-15: 6; 2015-12-16: 4; 2015-12-17: 4; 2015-12-21: 4; 2015-12-22: 4; 2015-12-23: 4; 2015-12-24: 4
PIM |  | Stefan |  | 2015-12-15: 4; 2015-12-16: 2; 2015-12-17: 2
Google
Google - Reverse Logistics Carriers |  | Geani | 0
Google - EDI |  | Geani | 0
Google - Weiss Rohlig Carrier |  | Geani | 0
Google - EasyVan Development |  | Geani | 0
Vodafone Turkey Interim
Internal testing/UAT Support |  | Geani | 46 | 2015-12-07: 4; 2015-12-08: 4; 2015-12-09: 4; 2015-12-10: 4; 2015-12-11: 4; 2015-12-14: 4; 2015-12-15: 2; 2015-12-16: 2; 2015-12-17: 2; 2015-12-21: 4; 2015-12-22: 4; 2015-12-23: 4; 2015-12-24: 4
Performance Testing |  | Geani | 18 | 2015-12-02: 4; 2015-12-03: 4; 2015-12-07: 2; 2015-12-08: 2; 2015-12-09: 2; 2015-12-10: 2; 2015-12-11: 2
Samsung
Sabre - Exploratory Testing/Automation |  | N/A | 0
Store Locator |  | N/A | 0
Performance Testing |  | N/A | 0
Digicel Phase 2
|  | TBC | 0
|  | TBC | 0
Digicel Retainer
|  | TBC | 0
|  | TBC | 0
Innodoo
Translations |  | Geani | 0
Holiday |  | Geani | 0
Holiday |  | Ionut | 0
Total |  | Stefanl (Total) | 0
Total |  | Geani (Total) | 0
Total |  | Ionut (Total) | 0
Grand Total |  |  | 0
Total Capacity |  |  |  | 0 | 0 | 16 | 16 | 8 | 0 | 8 | 16 | 16 | 16 | 16 | 8 | 0 | 8 | 24 | 24 | 24 | 24 | 16 | 0 | 8 | 24 | 24 | 24 | 24 | 0 | 0 | 8
Spare Capacity |  |  |  | 2015-11-30: 16; 2015-12-01: 16; 2015-12-02: 0; 2015-12-03: 0; 2015-12-04: N/A; 2015-12-07: 0; 2015-12-08: 0; 2015-12-09: 0; 2015-12-10: 0; 2015-12-11: N/A; 2015-12-14: 0; 2015-12-15: 0; 2015-12-16: 0; 2015-12-17: 0; 2015-12-18: N/A; 2015-12-21: 0; 2015-12-22: 0; 2015-12-23: 0; 2015-12-24: 0; 2015-12-25: N/A

## Iulie 2017
Service Capacity Management (SCM) Test Team
SCM | Release Date | Tester | Total | 2017-07-03 | 2017-07-04 | 2017-07-05 | 2017-07-06 | 2017-07-07 | 2017-07-08 | 2017-07-09 | 2017-07-10 | 2017-07-11 | 2017-07-12 | 2017-07-13 | 2017-07-14 | 2017-07-15 | 2017-07-16 | 2017-07-17 | 2017-07-18 | 2017-07-19 | 2017-07-20 | 2017-07-21 | 2017-07-22 | 2017-07-23 | 2017-07-24 | 2017-07-25 | 2017-07-26 | 2017-07-27 | 2017-07-28 | 2017-07-29 | 2017-07-30 | 2017-05-01 | 2017-05-02 | 2017-05-03 | 2017-05-04 | 2017-05-05 | 2017-05-06 | 2017-05-07
Projects
Tester duminica | 2017-07-16 | Ionut | 8 | [6 empty] | 0 | [6 empty] | 8 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
|  | Geani | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
Vodafone Qatar Retainer
Tickets, Bugs and Fixes, Regression |  | Ionut | 40 | 8 | 8 | 8 | 8 | 8
Tickets, Bugs and Fixes, Regression |  | Geani | 0
Release to Production Support |  | Ionut | 0
Release to Production Support |  | Geani | 0
Sunday Support |  | Ionut | 24 | [13 empty] | 8 | [6 empty] | 8 | [6 empty] | 8
Sunday Support |  | Geani | 8 | [6 empty] | 8
Vodafone Strategic
VFQ RA Express Project |  | TBC | 0
VFQ Enterprise Bill Template & VAS |  | TBC | 0
VFQ Real Time Sim Provisioning (ECR2) |  | TBC | 0
Localised
DesiLaCol - tickets/general testing |  | Geani | 32 | 8 | 8 | 8 | 8
IMP/LPD - Tickets |  | Geani | 0
TBC |  | N/A | 0
TBC |  | N/A | 0
DTAC Retainer
Sort package prices |  | Geani | 0
Delivery to store |  | Geani | 0
Other |  | Geani | 0
DTAC Strategic
DTAC CR 17 |  | Geani | 0
DTAC CR 6 |  | Geani | 0
DTAC FLEXI |  | Stefan | 0
Tickets, Bugs and Fixes |  | Geani | 0
Other |  | Geani | 0
Samsung
Sabre 2.0 - Tickets Testing |  | Geani | 0
Performance Testing |  | N/A | 0
Sabre 2.0 - Go live preparation |  | Geani | 0
Saber 2.0 - UAT testing |  | Geani | 0
Saber 2.0 - Front End Testing |  | Geani | 0
Saber 2.0 - Test planing/Test cases |  | Geani | 0
Optimus
Core |  | Geani | 0
REFSITE |  | Geani | 0
OMS |  | Geani | 0
PIM |  | Geani | 0
Google
Google - Reverse Logistics Carriers |  | TBC | 0
Google - EDI |  | TBC | 0
Google - Weiss Rohlig Carrier |  | TBC | 0
Google - EasyVan Development |  | TBC | 0
Vodafone Turkey Interim
Internal testing/UAT Support |  | Geani | 0
Performance Testing |  | Geani | 0
Digicel Payment gateway
Payment gateway |  | Geani | 0
TBA |  | TBA | 0
Digicel Retainer
|  | Geani | 0
|  | Stefan | 0
Innodoo
Innodoo |  | Geani | 0
Holiday |  | Ionut | 0
|  | Geani | 0
Holiday Total (current week) |  | Ionut | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
|  | Geani | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
Total |  | Ionut (Total) | 136 | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | [6 empty] | 8
Total |  | Geani (Total) | 120 | 8 | 8 | 8 | 8 | 8 |  | 8 |  | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 | 8
Grand Total |  |  | 256
Total Capacity |  |  |  | 16 | 16 | 16 | 16 | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 |  | 8 | 0 | 0 | 0 | 0 | 0 |  | 8 | 0 | 0 | 0 | 0 | 0 |  | 8 | 0 | 0 | 0 | 0 | 0 |  | 0
Spare Capacity |  |  |  | 8 | 8 | 8 | 8 | 8 |  | 0 | 24 | 24 | 24 | 24 | 16 |  | 0 | 24 | 24 | 24 | 24 | 16 |  | 0 | 24 | 24 | 24 | 24 | 16 |  | 0 | 24 | 24 | 24 | 24 | 16 |  | 8
Hours per day Legend: |  | Bold = confirmed
Red = unconfirmed
national holyday

## Iunie 2017
Service Capacity Management (SCM) Test Team
SCM | Release Date | Tester | Total | 2017-05-29 | 2017-05-30 | 2017-05-31 | 2017-06-01 | 2017-06-02 | 2017-06-03 | 2017-06-04 | 2017-06-05 | 2017-06-06 | 2017-06-07 | 2017-06-08 | 2017-06-09 | 2017-06-10 | 2017-06-11 | 2017-06-12 | 2017-06-13 | 2017-06-14 | 2017-06-15 | 2017-06-16 | 2017-06-17 | 2017-06-18 | 2017-06-19 | 2017-06-20 | 2017-06-21 | 2017-06-22 | 2017-06-23 | 2017-06-24 | 2017-06-25 | 2017-05-01 | 2017-05-02 | 2017-05-03 | 2017-05-04 | 2017-05-05 | 2017-05-06 | 2017-05-07
Projects
Tester duminica | 2017-07-16 | Ionut | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
|  | Geani | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
|  | Stefan | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
Vodafone Qatar Retainer
Tickets, Bugs and Fixes, Regression |  | Ionut | 136 | 8 | 8 | 8 |  |  |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 |  |  |  | 8 | 8 | 8 | 8 | 8
Tickets, Bugs and Fixes, Regression |  | Geani | 0
Tickets, Bugs and Fixes, Regression |  | Stefan | 0
Release to Production Support |  | Ionut | 0
Release to Production Support |  | Geani | 0
Release to Production Support |  | Stefan | 0
Sunday Support |  | Ionut | 8 | [20 empty] | 8
Sunday Support |  | Geani | 8 | [13 empty] | 8
Sunday Support |  | Stefan | 8 | [27 empty] | 8
Vodafone Strategic
VFQ RA Express Project |  | TBC | 0
VFQ Enterprise Bill Template & VAS |  | TBC | 0
VFQ Real Time Sim Provisioning (ECR2) |  | TBC | 0
Localised
DesiLaCol - tickets/general testing |  | Geani | 112 | [7 empty] | 8 | 8 | 8 | 8 |  |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8
DesiLaCol - tickets/general testing |  | Stefan | 128 | 8 | 8 | 8 |  |  |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 |  | 8 | 8 |  |  | 8 | 8 | 8 | 8
IMP/LPD - Tickets |  | Geani | 0
IMP/LPD - Tickets |  | Stefan | 0
TBC |  | N/A | 0
TBC |  | N/A | 0
DTAC Retainer
Sort package prices |  | Geani | 0
Delivery to store |  | Geani | 0
Other |  | Stefan | 0
Other |  | Geani | 0
DTAC Strategic
DTAC CR 17 |  | Geani | 0
DTAC CR 17 |  | Stefan | 0
DTAC CR 6 |  | Geani | 0
DTAC FLEXI |  | Stefan | 0
DTAC FLEXI |  | Geani | 0
Tickets, Bugs and Fixes |  | Geani | 0
Tickets, Bugs and Fixes |  | Stefan | 0
Other |  | Geani | 0
Samsung
Sabre 2.0 - Tickets Testing |  | Geani | 0
Sabre 2.0 - Tickets Testing |  | Stefan | 0
Performance Testing |  | N/A | 0
Sabre 2.0 - Go live preparation |  | Geani | 0
Sabre 2.0 - Go live preparation |  | Stefan | 0
Saber 2.0 - UAT testing |  | Geani | 0
Saber 2.0 - UAT testing |  | Stefan | 0
Saber 2.0 - Front End Testing |  | Geani | 0
Saber 2.0 - Front End Testing |  | Stefan | 0
Saber 2.0 - Test planing/Test cases |  | Geani | 0
Optimus
Core |  | Geani | 0
REFSITE |  | Geani | 0
OMS |  | Geani | 0
OMS |  | Stefan | 0
PIM |  | Geani | 0
PIM |  | Stefan | 0
Google
Google - Reverse Logistics Carriers |  | TBC | 0
Google - EDI |  | TBC | 0
Google - Weiss Rohlig Carrier |  | TBC | 0
Google - EasyVan Development |  | TBC | 0
Vodafone Turkey Interim
Internal testing/UAT Support |  | Geani | 0
Internal testing/UAT Support |  | Stefan | 0
Performance Testing |  | Geani | 0
Digicel Payment gateway
Payment gateway |  | Geani | 0
Payment gateway |  | Stefan | 0
Digicel Retainer
|  | Geani | 0
|  | Stefan | 0
Innodoo
Innodoo |  | Geani | 0
Holiday |  | Ionut | 16 |  |  |  | 8 | 8
|  | Geani | 40 | 8 | 8 | 8 | 8 | 8
|  | Stefan | 24 |  |  |  | 8 | 8 | [11 empty] | 8
Holiday Total (current week) |  | Ionut | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
|  | Geani | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
|  | Stefan | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
Total |  | Ionut (Total) | 120 | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 |  |  | 8
Total |  | Geani (Total) | 112 | 8 | 8 | 8 | 8 | 8 |  |  |  | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 | 8
Total |  | Stefan(Total) | 120 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8
Grand Total |  |  | 352
Total Capacity |  |  |  | 24 | 24 | 24 | 24 | 24 |  | 0 | 24 | 24 | 24 | 24 | 16 |  | 8 | 24 | 24 | 24 | 24 | 16 |  | 8 | 24 | 24 | 24 | 24 | 16 |  | 8 | 0 | 0 | 0 | 0 | 0 |  | 0
Spare Capacity |  |  |  | 0 | 0 | 0 | 0 | -8 |  | 8 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 24 | 24 | 24 | 24 | 16 |  | 8
Hours per day Legend: |  | Bold = confirmed
Red = unconfirmed
national holyday

## Mai 2017
Service Capacity Management (SCM) Test Team
SCM | Release Date | Tester | Total | 2017-05-01 | 2017-05-02 | 2017-05-03 | 2017-05-04 | 2017-05-05 | 2017-05-06 | 2017-05-07 | 2017-05-08 | 2017-05-09 | 2017-05-10 | 2017-05-11 | 2017-05-12 | 2017-05-13 | 2017-05-14 | 2017-05-15 | 2017-05-16 | 2017-05-17 | 2017-05-18 | 2017-05-19 | 2017-05-20 | 2017-05-21 | 2017-05-22 | 2017-05-23 | 2017-05-24 | 2017-05-25 | 2017-05-26 | 2017-05-27 | 2017-05-28 | 2017-05-01 | 2017-05-02 | 2017-05-03 | 2017-05-04 | 2017-05-05 | 2017-05-06 | 2017-05-07
Projects
Tester duminica | 2017-07-16 | Ionut | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
|  | Geani | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
|  | Stefan | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
Vodafone Qatar Retainer
Tickets, Bugs and Fixes, Regression |  | Ionut | 136 |  | 8 | 8 | 8 |  |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 |  |  |  | 8 | 8 | 8 | 8 | 8
Tickets, Bugs and Fixes, Regression |  | Geani | 0
Tickets, Bugs and Fixes, Regression |  | Stefan | 0
Release to Production Support |  | Ionut | 0
Release to Production Support |  | Geani | 0
Release to Production Support |  | Stefan | 0
Sunday Support |  | Ionut | 8 | [20 empty] | 8
Sunday Support |  | Geani | 8 | [13 empty] | 8
Sunday Support |  | Stefan | 16 | [6 empty] | 8 | [20 empty] | 8
Vodafone Strategic
VFQ RA Express Project |  | TBC | 0
VFQ Enterprise Bill Template & VAS |  | TBC | 0
VFQ Real Time Sim Provisioning (ECR2) |  | TBC | 0
Localised
IMP/LPD - Tickets |  | Geani | 144 |  | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 |  |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8
IMP/LPD - Tickets |  | Stefan | 136 |  | 8 | 8 | 8 |  |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8
TBC |  | N/A | 0
TBC |  | N/A | 0
DTAC Retainer
Sort package prices |  | Geani | 0
Delivery to store |  | Geani | 0
Other |  | Stefan | 0
Other |  | Geani | 0
DTAC Strategic
DTAC CR 17 |  | Geani | 0
DTAC CR 17 |  | Stefan | 0
DTAC CR 6 |  | Geani | 0
DTAC FLEXI |  | Stefan | 0
DTAC FLEXI |  | Geani | 0
Tickets, Bugs and Fixes |  | Geani | 0
Tickets, Bugs and Fixes |  | Stefan | 0
Other |  | Geani | 0
Samsung
Sabre 2.0 - Tickets Testing |  | Geani | 0
Sabre 2.0 - Tickets Testing |  | Stefan | 0
Performance Testing |  | N/A | 0
Sabre 2.0 - Go live preparation |  | Geani | 0
Sabre 2.0 - Go live preparation |  | Stefan | 0
Saber 2.0 - UAT testing |  | Geani | 0
Saber 2.0 - UAT testing |  | Stefan | 0
Saber 2.0 - Front End Testing |  | Geani | 0
Saber 2.0 - Front End Testing |  | Stefan | 0
Saber 2.0 - Test planing/Test cases |  | Geani | 0
Optimus
Core |  | Geani | 0
REFSITE |  | Geani | 0
OMS |  | Geani | 0
OMS |  | Stefan | 0
PIM |  | Geani | 0
PIM |  | Stefan | 0
Google
Google - Reverse Logistics Carriers |  | TBC | 0
Google - EDI |  | TBC | 0
Google - Weiss Rohlig Carrier |  | TBC | 0
Google - EasyVan Development |  | TBC | 0
Vodafone Turkey Interim
Internal testing/UAT Support |  | Geani | 0
Internal testing/UAT Support |  | Stefan | 0
Performance Testing |  | Geani | 0
Digicel Payment gateway
Payment gateway |  | Geani | 0
Payment gateway |  | Stefan | 0
Digicel Retainer
|  | Geani | 0
|  | Stefan | 0
Innodoo
Innodoo |  | Geani | 0
Holiday |  | Ionut | 8 |  |  |  |  | 8
|  | Geani | 0
|  | Stefan | 0
Holiday Total (current week) |  | Ionut | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
|  | Geani | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
|  | Stefan | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0 | [6 empty] | 0
Total |  | Ionut (Total) | 120 | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 |  |  | 8
Total |  | Geani (Total) | 112 | 8 | 8 | 8 | 8 | 8 |  |  |  | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 | 8
Total |  | Stefan(Total) | 120 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8
Grand Total |  |  | 352
Total Capacity |  |  |  | 0 | 24 | 24 | 24 | 16 |  | 8 | 24 | 24 | 24 | 24 | 16 |  | 8 | 24 | 24 | 24 | 24 | 16 |  | 8 | 24 | 24 | 24 | 24 | 16 |  | 8 | 0 | 0 | 0 | 0 | 0 |  | 0
Spare Capacity |  |  |  | 24 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 24 | 24 | 24 | 24 | 16 |  | 8
Hours per day Legend: |  | Bold = confirmed
Red = unconfirmed
national holyday

## Aprilie 2017
Service Capacity Management (SCM) Test Team
SCM | Release Date | Tester | Total | 2017-04-03 | 2017-04-04 | 2017-04-05 | 2017-04-06 | 2017-04-07 | 2017-04-08 | 2017-04-09 | 2017-04-10 | 2017-04-11 | 2017-04-12 | 2017-04-13 | 2017-04-14 | 2017-04-15 | 2017-04-16 | 2017-04-17 | 2017-04-18 | 2017-04-19 | 2017-04-20 | 2017-04-21 | 2017-04-22 | 2017-04-23 | 2017-04-24 | 2017-04-25 | 2017-04-26 | 2017-04-27 | 2017-04-28 | 2017-04-29 | 2017-04-30 | 2017-05-01 | 2017-05-02 | 2017-05-03 | 2017-05-04 | 2017-05-05 | 2017-05-06 | 2017-05-07
Projects
Tester duminica | 2017-07-16 | Ionut | 0 | 2017-04-09: 0; 2017-04-16: 0; 2017-04-23: 0; 2017-04-30: 0; 2017-05-07: 0
|  | Geani | 0 | 2017-04-09: 0; 2017-04-16: 0; 2017-04-23: 0; 2017-04-30: 0; 2017-05-07: 0
|  | Stefan | 0 | 2017-04-09: 0; 2017-04-16: 0; 2017-04-23: 0; 2017-04-30: 0; 2017-05-07: 0
Vodafone Qatar Retainer
Tickets, Bugs and Fixes, Regression |  | Ionut | 144 | 2017-04-03: 8; 2017-04-04: 8; 2017-04-05: 8; 2017-04-06: 8; 2017-04-10: 8; 2017-04-11: 8; 2017-04-12: 8; 2017-04-13: 8; 2017-04-14: 8; 2017-04-17: 8; 2017-04-18: 8; 2017-04-19: 8; 2017-04-20: 8; 2017-04-21: 8; 2017-04-24: 8; 2017-04-25: 8; 2017-04-26: 8; 2017-04-27: 8
Tickets, Bugs and Fixes, Regression |  | Geani | 0
Tickets, Bugs and Fixes, Regression |  | Stefan | 0
Release to Production Support |  | Ionut | 0
Release to Production Support |  | Geani | 0
Release to Production Support |  | Stefan | 0
Sunday Support |  | Ionut | 16 | 2017-04-09: 8; 2017-04-30: 8
Sunday Support |  | Geani | 8 | 2017-04-23: 8
Sunday Support |  | Stefan | 0
Vodafone Strategic
VFQ RA Express Project |  | TBC | 0
VFQ Enterprise Bill Template & VAS |  | TBC | 0
VFQ Real Time Sim Provisioning (ECR2) |  | TBC | 0
Localised
IMP/LPD - Tickets |  | Geani | 120 | 2017-04-03: 8; 2017-04-04: 8; 2017-04-05: 8; 2017-04-06: 8; 2017-04-07: 8; 2017-04-10: 8; 2017-04-11: 8; 2017-04-12: 8; 2017-04-13: 8; 2017-04-14: 8; 2017-04-24: 8; 2017-04-25: 8; 2017-04-26: 8; 2017-04-27: 8; 2017-04-28: 8
IMP/LPD - Tickets |  | Stefan | 160 | 2017-04-03: 8; 2017-04-04: 8; 2017-04-05: 8; 2017-04-06: 8; 2017-04-07: 8; 2017-04-10: 8; 2017-04-11: 8; 2017-04-12: 8; 2017-04-13: 8; 2017-04-14: 8; 2017-04-17: 8; 2017-04-18: 8; 2017-04-19: 8; 2017-04-20: 8; 2017-04-21: 8; 2017-04-24: 8; 2017-04-25: 8; 2017-04-26: 8; 2017-04-27: 8; 2017-04-28: 8
TBC |  | N/A | 0
TBC |  | N/A | 0
DTAC Retainer
Sort package prices |  | Geani | 0
Delivery to store |  | Geani | 0
Other |  | Stefan | 0
Other |  | Geani | 0
DTAC Strategic
DTAC CR 17 |  | Geani | 0
DTAC CR 17 |  | Stefan | 0
DTAC CR 6 |  | Geani | 0
DTAC FLEXI |  | Stefan | 0
DTAC FLEXI |  | Geani | 0
Tickets, Bugs and Fixes |  | Geani | 0
Tickets, Bugs and Fixes |  | Stefan | 0
Other |  | Geani | 0
Samsung
Sabre 2.0 - Tickets Testing |  | Geani | 0
Sabre 2.0 - Tickets Testing |  | Stefan | 0
Performance Testing |  | N/A | 0
Sabre 2.0 - Go live preparation |  | Geani | 0
Sabre 2.0 - Go live preparation |  | Stefan | 0
Saber 2.0 - UAT testing |  | Geani | 0
Saber 2.0 - UAT testing |  | Stefan | 0
Saber 2.0 - Front End Testing |  | Geani | 0
Saber 2.0 - Front End Testing |  | Stefan | 0
Saber 2.0 - Test planing/Test cases |  | Geani | 0
Optimus
Core |  | Geani | 0
REFSITE |  | Geani | 0
OMS |  | Geani | 0
OMS |  | Stefan | 0
PIM |  | Geani | 0
PIM |  | Stefan | 0
Google
Google - Reverse Logistics Carriers |  | TBC | 0
Google - EDI |  | TBC | 0
Google - Weiss Rohlig Carrier |  | TBC | 0
Google - EasyVan Development |  | TBC | 0
Vodafone Turkey Interim
Internal testing/UAT Support |  | Geani | 0
Internal testing/UAT Support |  | Stefan | 0
Performance Testing |  | Geani | 0
Digicel Payment gateway
Payment gateway |  | Geani | 0
Payment gateway |  | Stefan | 0
Digicel Retainer
|  | Geani | 0
|  | Stefan | 0
Innodoo
Innodoo |  | Geani | 0
Holiday |  | Ionut | 0
|  | Geani | 24 | 2017-04-18: 8; 2017-04-19: 8; 2017-04-20: 8
|  | Stefan | 40 | 2017-04-10: 8; 2017-04-11: 8; 2017-04-12: 8; 2017-04-13: 8; 2017-04-14: 8
Holiday Total (current week) |  | Ionut | 0 | 2017-04-09: 0; 2017-04-16: 0; 2017-04-23: 0; 2017-04-30: 0; 2017-05-07: 0
|  | Geani | 0 | 2017-04-09: 0; 2017-04-16: 0; 2017-04-23: 0; 2017-04-30: 0; 2017-05-07: 0
|  | Stefan | 0 | 2017-04-09: 0; 2017-04-16: 0; 2017-04-23: 0; 2017-04-30: 0; 2017-05-07: 0
Total |  | Ionut (Total) | 160 | 2017-04-03: 8; 2017-04-04: 8; 2017-04-05: 8; 2017-04-06: 8; 2017-04-07: 8; 2017-04-10: 8; 2017-04-11: 8; 2017-04-12: 8; 2017-04-13: 8; 2017-04-14: 8; 2017-04-17: 8; 2017-04-18: 8; 2017-04-19: 8; 2017-04-20: 8; 2017-04-24: 8; 2017-04-25: 8; 2017-04-26: 8; 2017-04-27: 8; 2017-04-28: 8; 2017-04-30: 8
Total |  | Geani (Total) | 160 | 2017-04-03: 8; 2017-04-04: 8; 2017-04-05: 8; 2017-04-06: 8; 2017-04-07: 8; 2017-04-10: 8; 2017-04-11: 8; 2017-04-12: 8; 2017-04-13: 8; 2017-04-17: 8; 2017-04-18: 8; 2017-04-19: 8; 2017-04-20: 8; 2017-04-21: 8; 2017-04-23: 8; 2017-04-24: 8; 2017-04-25: 8; 2017-04-26: 8; 2017-04-27: 8; 2017-04-28: 8
Total |  | Stefan(Total) | 152 | 2017-04-03: 8; 2017-04-04: 8; 2017-04-05: 8; 2017-04-06: 8; 2017-04-09: 8; 2017-04-10: 8; 2017-04-11: 8; 2017-04-12: 8; 2017-04-13: 8; 2017-04-14: 8; 2017-04-17: 8; 2017-04-18: 8; 2017-04-19: 8; 2017-04-20: 8; 2017-04-21: 8; 2017-04-24: 8; 2017-04-25: 8; 2017-04-26: 8; 2017-04-27: 8
Grand Total |  |  | 472
Total Capacity |  |  |  | 24 | 24 | 24 | 24 | 16 |  | 8 | 32 | 32 | 32 | 32 | 32 |  | 0 | 16 | 24 | 24 | 24 | 16 |  | 8 | 24 | 24 | 24 | 24 | 16 |  | 8 | 0 | 0 | 0 | 0 | 0 |  | 0
Spare Capacity |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | -8 | -8 | -8 | -8 | -16 |  | 8 | 8 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 24 | 24 | 24 | 24 | 16 |  | 8
Hours per day Legend: |  | Bold = confirmed
Red = unconfirmed
national holyday

## Mar 2017
Service Capacity Management (SCM) Test Team
SCM | Release Date | Tester | Total | 2017-02-27 | 2017-02-28 | 2017-03-01 | 2017-03-02 | 2017-03-03 | 2017-03-04 | 2017-03-05 | 2017-03-06 | 2017-03-07 | 2017-03-08 | 2017-03-09 | 2017-03-10 | 2017-03-11 | 2017-03-12 | 2017-03-13 | 2017-03-14 | 2017-03-15 | 2017-03-16 | 2017-03-17 | 2017-03-18 | 2017-03-19 | 2017-03-20 | 2017-03-21 | 2017-03-22 | 2017-03-23 | 2017-03-24 | 2017-03-25 | 2017-03-26 | 2017-03-27 | 2017-03-28 | 2017-03-29 | 2017-03-30 | 2017-03-31 | 2017-04-01 | 2017-04-02
Projects
Tester duminica | 2017-07-16 | Ionut | 0 | 2017-03-05: 0; 2017-03-12: 0; 2017-03-19: 0; 2017-03-26: 0; 2017-04-02: 0
|  | Geani | 0 | 2017-03-05: 0; 2017-03-12: 0; 2017-03-19: 0; 2017-03-26: 0; 2017-04-02: 0
|  | Stefan | 0 | 2017-03-05: 0; 2017-03-12: 0; 2017-03-19: 0; 2017-03-26: 0; 2017-04-02: 0
Vodafone Qatar Retainer
Tickets, Bugs and Fixes, Regression |  | Ionut | 192 | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 |  |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8
Tickets, Bugs and Fixes, Regression |  | Geani | 0
Tickets, Bugs and Fixes, Regression |  | Stefan | 0
Release to Production Support |  | Ionut | 0
Release to Production Support |  | Geani | 0
Release to Production Support |  | Stefan | 0
Sunday Support |  | Ionut | 8 | 2017-03-19: 8
Sunday Support |  | Geani | 16 | 2017-03-12: 8; 2017-04-02: 8
Sunday Support |  | Stefan | 16 | 2017-03-05: 8; 2017-03-26: 8
Vodafone Strategic
VFQ RA Express Project |  | TBC | 0
VFQ Enterprise Bill Template & VAS |  | TBC | 0
VFQ Real Time Sim Provisioning (ECR2) |  | TBC | 0
Localised
IMP/LPD - Tickets |  | Geani | 184 | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 |  |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8
IMP/LPD - Tickets |  | Stefan | 144 | 2017-02-27: 8; 2017-02-28: 8; 2017-03-01: 8; 2017-03-02: 8; 2017-03-13: 8; 2017-03-14: 8; 2017-03-15: 8; 2017-03-16: 8; 2017-03-17: 8; 2017-03-20: 8; 2017-03-21: 8; 2017-03-22: 8; 2017-03-23: 8; 2017-03-27: 8; 2017-03-28: 8; 2017-03-29: 8; 2017-03-30: 8; 2017-03-31: 8
TBC |  | N/A | 0
TBC |  | N/A | 0
DTAC Retainer
Sort package prices |  | Geani | 0
Delivery to store |  | Geani | 0
Other |  | Stefan | 0
Other |  | Geani | 0
DTAC Strategic
DTAC CR 17 |  | Geani | 0
DTAC CR 17 |  | Stefan | 0
DTAC CR 6 |  | Geani | 0
DTAC FLEXI |  | Stefan | 0
DTAC FLEXI |  | Geani | 0
Tickets, Bugs and Fixes |  | Geani | 0
Tickets, Bugs and Fixes |  | Stefan | 0
Other |  | Geani | 0
Samsung
Sabre 2.0 - Tickets Testing |  | Geani | 0
Sabre 2.0 - Tickets Testing |  | Stefan | 0
Performance Testing |  | N/A | 0
Sabre 2.0 - Go live preparation |  | Geani | 0
Sabre 2.0 - Go live preparation |  | Stefan | 0
Saber 2.0 - UAT testing |  | Geani | 0
Saber 2.0 - UAT testing |  | Stefan | 0
Saber 2.0 - Front End Testing |  | Geani | 0
Saber 2.0 - Front End Testing |  | Stefan | 0
Saber 2.0 - Test planing/Test cases |  | Geani | 0
Optimus
Core |  | Geani | 0
REFSITE |  | Geani | 0
OMS |  | Geani | 0
OMS |  | Stefan | 0
PIM |  | Geani | 0
PIM |  | Stefan | 0
Google
Google - Reverse Logistics Carriers |  | TBC | 0
Google - EDI |  | TBC | 0
Google - Weiss Rohlig Carrier |  | TBC | 0
Google - EasyVan Development |  | TBC | 0
Vodafone Turkey Interim
Internal testing/UAT Support |  | Geani | 0
Internal testing/UAT Support |  | Stefan | 0
Performance Testing |  | Geani | 0
Digicel Payment gateway
Payment gateway |  | Geani | 0
Payment gateway |  | Stefan | 0
Digicel Retainer
|  | Geani | 0
|  | Stefan | 0
Innodoo
Innodoo |  | Geani | 0
Holiday |  | Ionut | 0
|  | Geani | 0
|  | Stefan | 40 | 2017-03-06: 8; 2017-03-07: 8; 2017-03-08: 8; 2017-03-09: 8; 2017-03-10: 8
Holiday Total (current week) |  | Ionut | 0 | 2017-03-05: 0; 2017-03-12: 0; 2017-03-19: 0; 2017-03-26: 0; 2017-04-02: 0
|  | Geani | 0 | 2017-03-05: 0; 2017-03-12: 0; 2017-03-19: 0; 2017-03-26: 0; 2017-04-02: 0
|  | Stefan | 0 | 2017-03-05: 0; 2017-03-12: 0; 2017-03-19: 0; 2017-03-26: 0; 2017-04-02: 0
Total |  | Ionut (Total) | 160 | 2017-02-27: 8; 2017-02-28: 8; 2017-03-01: 8; 2017-03-02: 8; 2017-03-03: 8; 2017-03-06: 8; 2017-03-07: 8; 2017-03-08: 8; 2017-03-09: 8; 2017-03-10: 8; 2017-03-13: 8; 2017-03-14: 8; 2017-03-15: 8; 2017-03-16: 8; 2017-03-19: 8; 2017-03-20: 8; 2017-03-21: 8; 2017-03-22: 8; 2017-03-23: 8; 2017-03-24: 8
Total |  | Geani (Total) | 168 | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 | [8 empty] | 8
Total |  | Stefan(Total) | 160 | 2017-02-27: 8; 2017-02-28: 8; 2017-03-01: 8; 2017-03-02: 8; 2017-03-05: 8; 2017-03-06: 8; 2017-03-07: 8; 2017-03-08: 8; 2017-03-09: 8; 2017-03-10: 8; 2017-03-13: 8; 2017-03-14: 8; 2017-03-15: 8; 2017-03-16: 8; 2017-03-17: 8; 2017-03-20: 8; 2017-03-21: 8; 2017-03-22: 8; 2017-03-23: 8; 2017-03-26: 8
Grand Total |  |  | 488
Total Capacity |  |  |  | 24 | 24 | 24 | 24 | 16 |  | 8 | 24 | 24 | 24 | 24 | 16 |  | 8 | 24 | 24 | 24 | 24 | 16 |  | 8 | 24 | 24 | 24 | 24 | 16 |  | 8 | 24 | 24 | 24 | 24 | 16 |  | 8
Spare Capacity |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Hours per day Legend: |  | Bold = confirmed
Red = unconfirmed
national holyday

## Feb 2017
Service Capacity Management (SCM)
SCM | Release Date | Tester | Total | 2017-01-30 | 2017-01-31 | 2017-02-01 | 2017-02-02 | 2017-02-03 | 2017-02-04 | 2017-02-05 | 2017-02-06 | 2017-02-07 | 2017-02-08 | 2017-02-09 | 2017-02-10 | 2017-02-11 | 2017-02-12 | 2017-02-13 | 2017-02-14 | 2017-02-15 | 2017-02-16 | 2017-02-17 | 2017-02-18 | 2017-02-19 | 2017-02-20 | 2017-02-21 | 2017-02-22 | 2017-02-23 | 2017-02-24 | 2017-02-25 | 2017-02-26
Projects
Vodafone Qatar Retainer
Tickets, Bugs and Fixes, Regression |  | Ionut | 128 | 2017-01-30: 8; 2017-01-31: 8; 2017-02-01: 8; 2017-02-02: 8; 2017-02-06: 8; 2017-02-07: 8; 2017-02-08: 8; 2017-02-09: 8; 2017-02-13: 8; 2017-02-14: 8; 2017-02-15: 8; 2017-02-16: 8; 2017-02-20: 8; 2017-02-21: 8; 2017-02-22: 8; 2017-02-23: 8
Tickets, Bugs and Fixes, Regression |  | Geani | 0 | [29 empty] | Next Sunday
Tickets, Bugs and Fixes, Regression |  | Stefan | 0 | [29 empty] | 2017-07-16
Release to Production Support |  | Ionut | 0 | [28 empty] | Ionut | #N/A
Release to Production Support |  | Geani | 0 | [28 empty] | Geani | #N/A
Release to Production Support |  | Stefan | 0 | [28 empty] | Stefan | #N/A
Sunday Support |  | Ionut | 16 | 2017-02-05: 8; 2017-02-26: 8
Sunday Support |  | Geani | 8 | 2017-02-19: 8 | initial formula | 0
Sunday Support |  | Stefan | 8 | 2017-02-12: 8
Vodafone Strategic
VFQ RA Express Project |  | TBC | 0
VFQ Enterprise Bill Template & VAS |  | TBC | 0
VFQ Real Time Sim Provisioning (ECR2) |  | TBC | 0
Localised
IMP/LPD - Tickets |  | Geani | 54 | 2017-02-13: 6; 2017-02-14: 6; 2017-02-15: 6; 2017-02-16: 6; 2017-02-20: 6; 2017-02-21: 6; 2017-02-22: 6; 2017-02-23: 6; 2017-02-24: 6
IMP/LPD - Tickets |  | Stefan | 58 | 2017-02-13: 6; 2017-02-14: 6; 2017-02-15: 6; 2017-02-16: 6; 2017-02-17: 6; 2017-02-20: 4; 2017-02-21: 6; 2017-02-22: 6; 2017-02-23: 6; 2017-02-24: 6
TBC |  | N/A | 0
TBC |  | N/A | 0
Samsung
Sabre 2.0 - Tickets Testing |  | Geani | 98 | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 2 | 2 | 2 | 2 |  |  |  | 2 | 2 | 2 | 2 | 2
Sabre 2.0 - Tickets Testing |  | Stefan | 92 | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 |  |  |  | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2
Performance Testing |  | N/A | 0
Sabre 2.0 - Go live preparation |  | Geani | 0
Sabre 2.0 - Go live preparation |  | Stefan | 0
Saber 2.0 - UAT testing |  | Geani | 0
Saber 2.0 - UAT testing |  | Stefan | 0
Saber 2.0 - Front End Testing |  | Geani | 0
Saber 2.0 - Front End Testing |  | Stefan | 0
Saber 2.0 - Test planing/Test cases |  | Geani | 0
Optimus
Core |  | Geani | 0
REFSITE |  | Geani | 0
OMS |  | Geani | 0
OMS |  | Stefan | 0
PIM |  | Geani | 0
PIM |  | Stefan | 0
DTAC Retainer
Sort package prices |  | Geani | 0
Delivery to store |  | Geani | 0
Other |  | Stefan | 2 | 2017-02-20: 2
Other |  | Geani | 0
DTAC Strategic
DTAC CR 17 |  | Geani | 0
DTAC CR 17 |  | Stefan | 0
DTAC CR 6 |  | Geani | 0
DTAC FLEXI |  | Stefan | 0
DTAC FLEXI |  | Geani | 0
Tickets, Bugs and Fixes |  | Geani | 0
Tickets, Bugs and Fixes |  | Stefan | 0
Other |  | Geani | 0
Google
Google - Reverse Logistics Carriers |  | TBC | 0
Google - EDI |  | TBC | 0
Google - Weiss Rohlig Carrier |  | TBC | 0
Google - EasyVan Development |  | TBC | 0
Vodafone Turkey Interim
Internal testing/UAT Support |  | Geani | 0
Internal testing/UAT Support |  | Stefan | 0
Performance Testing |  | Geani | 0
Digicel Payment gateway
Payment gateway |  | Geani | 0
Payment gateway |  | Stefan | 0
Digicel Retainer
|  | Geani | 0
|  | Stefan | 0
Innodoo
Innodoo |  | Geani | 0
Holiday |  | Geani | 0
Holiday |  | Sefan | 0
Holiday |  | Ionut | 16 | 2017-02-10: 8; 2017-02-17: 8
Total |  | Ionut (Total) | 176 | 8 | 8 | 8 | 8 | 8 |  | 8 | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  | 8
Total |  | Geani (Total) | 168 | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  | 8 | 8 | 8 | 8 | 8 | 8
Total |  | Stefan(Total) | 168 | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  | 8 | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8
Grand Total |  |  | 512
Total Capacity |  |  |  | 24 | 24 | 24 | 24 | 16 |  | 8 | 24 | 24 | 24 | 24 | 16 |  | 8 | 24 | 24 | 24 | 24 | 16 |  | 8 | 24 | 24 | 24 | 24 | 16 |  | 8
Spare Capacity |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Hours per day Legend: | Bold = confirmed
Red = unconfirmed
national holyday

## Jan 2017
Service Capacity Management (SCM)
SCM | Release Date | Tester | Total | 2017-01-02 | 2017-01-03 | 2017-01-04 | 2017-01-05 | 2017-01-06 | 2017-01-07 | 2017-01-08 | 2017-01-09 | 2017-01-10 | 2017-01-11 | 2017-01-12 | 2017-01-13 | 2017-01-14 | 2017-01-15 | 2017-01-16 | 2017-01-17 | 2017-01-18 | 2017-01-19 | 2017-01-20 | 2017-01-21 | 2017-01-22 | 2017-01-23 | 2017-01-24 | 2017-01-25 | 2017-01-26 | 2017-01-27 | 2017-01-28 | 2017-01-29
Projects
Vodafone Qatar Retainer
Tickets, Bugs and Fixes, Regression |  | Ionut | 136 |  | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 |  |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 |  | 8 | 8 | 8
Tickets, Bugs and Fixes, Regression |  | Geani | 0
Tickets, Bugs and Fixes, Regression |  | Stefan | 0
Release to Production Support |  | Ionut | 0
Release to Production Support |  | Geani | 0
Release to Production Support |  | Stefan | 0
Sunday Support |  | Ionut | 8 | 2017-01-15: 8
Sunday Support |  | Geani | 16 | 2017-01-08: 8; 2017-01-29: 8
Sunday Support |  | Stefan | 8 | 2017-01-22: 8
Other |  | TBC | 0
Vodafone Strategic
VFQ RA Express Project |  | TBC | 0
VFQ Enterprise Bill Template & VAS |  | TBC | 0
VFQ Real Time Sim Provisioning (ECR2) |  | TBC | 0
Samsung
Sabre 2.0 - Tickets Testing |  | Geani | 94 | 2017-01-09: 6; 2017-01-10: 6; 2017-01-11: 6; 2017-01-12: 6; 2017-01-13: 6; 2017-01-16: 8; 2017-01-17: 8; 2017-01-18: 8; 2017-01-19: 8; 2017-01-20: 8; 2017-01-23: 8; 2017-01-25: 8; 2017-01-26: 8
Sabre 2.0 - Tickets Testing |  | Stefan | 110 | 2017-01-03: 8; 2017-01-04: 8; 2017-01-05: 8; 2017-01-06: 8; 2017-01-09: 6; 2017-01-10: 6; 2017-01-11: 6; 2017-01-12: 6; 2017-01-13: 6; 2017-01-16: 8; 2017-01-17: 8; 2017-01-18: 8; 2017-01-25: 8; 2017-01-26: 8; 2017-01-27: 8
Performance Testing |  | N/A | 0
Sabre 2.0 - Go live preparation |  | Geani | 0
Sabre 2.0 - Go live preparation |  | Stefan | 0
Saber 2.0 - UAT testing |  | Geani | 0
Saber 2.0 - UAT testing |  | Stefan | 0
Saber 2.0 - Front End Testing |  | Geani | 0
Saber 2.0 - Front End Testing |  | Stefan | 0
Saber 2.0 - Test planing/Test cases |  | Geani | 0
Optimus
Core |  | Geani | 0
REFSITE |  | Geani | 0
OMS |  | Geani | 0
OMS |  | Stefan | 0
PIM |  | Geani | 0
PIM |  | Stefan | 0
DTAC Retainer
Sort package prices |  | Geani | 0
Delivery to store |  | Geani | 0
Other |  | Stefan | 10 | 2017-01-09: 2; 2017-01-10: 2; 2017-01-11: 2; 2017-01-12: 2; 2017-01-13: 2
Other |  | Geani | 10 | 2017-01-09: 2; 2017-01-10: 2; 2017-01-11: 2; 2017-01-12: 2; 2017-01-13: 2
DTAC Strategic
DTAC CR 17 |  | Geani | 0
DTAC CR 17 |  | Stefan | 0
DTAC CR 6 |  | Geani | 0
DTAC FLEXI |  | Stefan | 0
DTAC FLEXI |  | Geani | 0
Tickets, Bugs and Fixes |  | Geani | 0
Tickets, Bugs and Fixes |  | Stefan | 0
Other |  | Geani | 0
Google
Google - Reverse Logistics Carriers |  | TBC | 0
Google - EDI |  | TBC | 0
Google - Weiss Rohlig Carrier |  | TBC | 0
Google - EasyVan Development |  | TBC | 0
Vodafone Turkey Interim
Internal testing/UAT Support |  | Geani | 0
Internal testing/UAT Support |  | Stefan | 0
Performance Testing |  | Geani | 0
Digicel Payment gateway
Payment gateway |  | Geani | 0
Payment gateway |  | Stefan | 0
Digicel Retainer
|  | Geani | 0
|  | Stefan | 0
Innodoo
Innodoo |  | Geani | 0
Holiday |  | Geani | 24 | 2017-01-03: 8; 2017-01-04: 8; 2017-01-05: 8
Holiday |  | Sefan | 16 | 2017-01-19: 8; 2017-01-23: 8
Holiday |  | Ionut | 0
Total |  | Stefan (Total) | 152 |  | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  | 8 | 8 |  | 8 | 8 | 8
Total |  | Geani (Total) | 160 |  | 8 | 8 | 8 | 8 |  | 8 | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  |  | 8 |  | 8 | 8 | 8 |  | 8
Total |  | Ionut (Total) | 152 |  | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 |  | 8 | 8 | 8 | 8 | 8 | 8 |  |  | 8 |  | 8 | 8 | 8
Grand Total |  |  | 464
Total Capacity |  |  |  | 0 | 24 | 24 | 24 | 16 |  | 8 | 24 | 24 | 24 | 24 | 16 |  | 8 | 24 | 24 | 24 | 24 | 16 |  | 8 | 24 | 0 | 24 | 24 | 16 |  | 8
Spare Capacity |  |  |  | 24 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 24 | 0 | 0 | 0 |  | 0
Hours per day Legend: | Bold = confirmed
Red = unconfirmed
national holyday