## PIM Bug List
Bug ID | Description | Assigned To | Status | Priority (L/M/H) | Testing Status/Comment | Date Raised | Date Closed | Responsible | Status | Prio
1 | Product drafts can't be published. The message that the publish is completed appear, but the draft is not published. Note: Because of this issue, new products can't be added. |  | Closed | H | 15/01/2016 maciejs: validation method changed in the db for the properties "MEMORY" and "NETWORK". products can be published now (after adding at least one asset). 18/01/2016 Geani: Product drafts still can't be saved. After i press "publish" the page refresh but the product is not published. 21/01/2016 maciejs: product publishing works fine on dev. may be a test db related issue. need to be verified on test. 26/01/2016 Geani: Publish still not working on test server ERROR [com.brandpath.pim.business.manager.product.ProductPublishingManager] (default task-25) com.brandpath.commons.business.exception.ServiceException: com.brandpath.commons.model.exception.DataAccessException: javax.persistence.PersistenceException: org.hibernate.exception.GenericJDBCException: Could not open connection ERROR [org.hibernate.engine.jdbc.spi.SqlExceptionHelper] (default task-25) javax.resource.ResourceException: IJ000460: Error checking for a transaction ERROR [com.brandpath.pim.business.manager.product.ProductPublishingManager] (default task-25) com.brandpath.commons.business.exception.ServiceException: com.brandpath.commons.model.exception.DataAccessException: javax.persistence.PersistenceException: org.hibernate.exception.GenericJDBCException: Could not open connection | 16/12/2015 | 2016-05-02 |  | Open | High
2 | Drafts in "Edit" mode can't be Saved. After editing an draft and clicking on "Save" button, lots of validation error appear. Note: The data introduced in the filed for validation are deled after clicking "Save" |  | Closed | H | 04/01/2016 Geani : No validation error appreas, but the product is not saved. "Note: The data introduced in the filed for validation are deled after clicking "Save" "still occurs. 12/01/2016 maciejs: when saving a draft, no validation should take place. validation is triggered when publishing product only (as per SDD) 12/01/2016 Geani: Ok, so no validation error should apprear. But the imput data (for example Skucode, Description, Weight, Height..) are deleted (or revet to initial state) after clicking "Save" and the draft remains in "Edit" mode. 12/16/2016 maciejs: existing input should not be wiped out of edit boxes when validation fails - this is current behaviour in case when user attempts to publish product with insufficient input. I think the old version remains on the test server. will be verifying that. 13/01/2016 maciejs: confirmed that this happens only on test environment | 15/12/2015 | 14/01/2016 |  | Closed | Medium
3 | Buttons overlap image in product view page. Please see exreenshot. |  | Closed | L | 13/01/2016 Geani: issue fixed | 16/12/2015 | 13/01/2016 |  | Dev Completed | Low
4 | Dashboard links refresh the page or do nothing |  | Closed | M |  | 16/12/2015 |  |  | To Test
5 | Dashboard "Latest added" doesn't display images for produts. Please see screenshot. |  | Closed | M | fixed | 16/12/2015 | 22/12/2015 |  | Rejected
6 | Draft produs have corrupt image display. Please see screenshot. |  | Suggestion | L | 21.01.2016 Geani: We should have an default image for all products that are in draft mode. An place holder image untill the produt is published. | 16/12/2015 |  |  | Moved to the next Phase
7 | Prdoct tab - Filter "search" text is not visible on any category. Please see screenshot for detailed location. |  | Closed | L | 04/01/2016 Geani: Reopen as the issue is half back. On filters with drop-down list, while the mouse is over the imput box, the text becomes invisible. | 16/12/2015 | 27/01/2016 |  | Question
8 | Product tab - "Type" filter has no option to select. |  | Closed | L |  | 16/12/2015 | 27/01/2016
9 | Product tab - Name filter doesn't work unless selecting product from the list. Please see screenshot. 26/01/2016 Geani: Please see comments |  | Open | M | 04/01/2016 Geani: The filter is case senzitive "nokia" doesn't generate drop down list but "Nokia" does. 26/01/2016: Geani Search now works but previous note still valid. " The filter is case senzitive "nokia" doesn't generate drop down list but "Nokia" does." 25/02/2016 Geani: Name search only display PUBLISHED prodcuts | 16/12/2015
10 | Product tab - SKU code filter works only for exact sku code. Please see screenshot for clarification. |  | Closed | L |  | 16/12/2015 | 27/01/2016
11 | Product Version View - Abort and save icons are inverted. Please see screenshot. |  | Closed | L |  | 16/12/2015 | 27/01/2016
12 | "Add" button is missing on Offerings tab. Question: Is there another way to create offerings? |  | Closed | H | fixed | 17/12/2015 | 23/12/2015
13 | "Administration" tab button gives the following error : "/pim/offerings/versionView/index.xhtml Not Found in ExternalContext as a Resource" |  | Closed | M | 13/01/2016 Geani : new error is displaed on PIM page. log: WARNING [javax.enterprise.resource.webcontainer.jsf.application] (default task-20) JSF1064: Unable to find or serve resource, /pim/administration/media/size/index.xhtml. | 17/12/2015 | 2016-09-03
14 | Product details - The "+" button does nothing. |  | Closed | L | fixed | 17/12/2015 | 2016-04-01
15 | Offerings listing is empty |  | Closed | M |  | 23/12/2015 | 19/01/2016
16 | Offerings can't be created. After inserting name, skucode and selecting type and then clicking "save" nothing happens. Note: The name of the offering is updated but the offerign doesn't appear in list. Note: 26/01/2016 Geani: Offerings still can't be published 19/02/2016 Geani: Has this fix been deployed? 24/02/2016 Geani : Offerins still can't be published. Will pressing publish the message INFO THE OFFERING VERSION HAS BEEN CHANGED TO STATUS PUBLISHED appears. Lots of messageas appear in the logs. 2016-02-24 10:19:48,060 ERROR [com.brandpath.pim.business.manager.offering.GenericOfferingPropertyManager] NOTE: When offering in EDIT mode, pressing save generates lots of messages in the log, but noting happes (if fields are empty) NOTE: Might be related to issue 62? |  | Closed | H | 18/01/2016 Geani: Offernigs Draft can be created now, but publish doesn't work. ERROR [org.hibernate.engine.jdbc.spi.SqlExceptionHelper] (default task-22) javax.resource.ResourceException: IJ000460: Error checking for a transaction 2016-01-18 16:56:12,819 ERROR [com.brandpath.pim.business.manager.offering.OfferingPublishingManager] (default task-22) com.brandpath.commons.business.exception.ServiceException: com.brandpath.commons.model.exception.DataAccessException: javax.persistence.PersistenceException: org.hibernate.exception.GenericJDBCException: Could not open connection 26/01/2016 Geani: Offerings still can't be published 19/02/2016 Geani: Has this fix been deployed? 24/02/2016 Geani : Offerins still can't be published. Will pressing publish the message INFO THE OFFERING VERSION HAS BEEN CHANGED TO STATUS PUBLISHED appears. Lots of messageas appear in the logs. 2016-02-24 10:19:48,060 ERROR [com.brandpath.pim.business.manager.offering.GenericOfferingPropertyManager] NOTE: When offering in EDIT mode, pressing save generates lots of messages in the log, but noting happes (if fields are empty) NOTE: Might be related to issue 62? | 23/12/2015 | 25/02/2016
17 | Offerings Creation Tabs can't be clicked. |  | Closed | H |  | 23/12/2015 | 18/01/2016
18 | Dashboard is missing/empty |  | Closed | M | fixed | 23/12/2015 | 2016-04-01
19 | Media Asset tab - Pressing "Add" button generates error. Please see screenshot. |  | Closed | M |  | 2016-04-01 | 22/01/2016 Stefanc
20 | Create Offering Price List - Currency selector is empty and ca't be selected. Note: Pressing "Save" nothing happens. It should display error. Please see screenshot. |  | Closed | M |  | 2016-04-01 | 13/01/2016
21 | Offering Price list - "May not be null" error appear while trying to edit an already created offering price list and "Status" is not selected". Please see screeenshot. |  | Closed | L |  | 2016-04-01 | 13/01/2016
22 | Product Assests "+" button doesn't work in Edit mode. Because of this issue new products can't be created. |  | Closed | H |  | 2016-04-01 | 13/01/2016
23 | Product creation - "Default Categories" and "Catalogue" drop down buttons are not working before clicking "Save". |  | Closed | L | Arvind: you are only allowed to make catalogue & category changes after you saved them | 2016-04-01
24 | Product edit - SEO Tab has missing content. Please see screenshot |  | Closed | M | 05/02/2016 Issue still occurs | 2016-04-01
25 | Pressing Tab button from the top list, doesn't oppen the sublist from the left screen. Please see screenshot for clarification of what is not oppen. |  | Closed | L |  | 2016-04-01 | 21/01/2016
26 | Product Catalogues - New catalogues created doesn't appear in list |  | Closed | M |  | 2016-04-01 | 13/01/2016
27 | Product Asset Creation - After pressing "actual size" java.lang.NullPointerException is displayed |  | Closed | H |  | 2016-06-01 | 2016-05-02
28 | Offering Price list - "Tag not available" for "site" and "status" message appears Please see screenshot Note: This issue occurs simmilary for Product Catalogues |  | Closed | L | Dev Completed | 2016-06-01 | 27/01/2016
29 | NullPointerException when creating new product com.brandpath.pim.web.controller.product.version.AssetVersion.initNewAsset(AssetVersion.java:383) com.brandpath.pim.web.controller.product.version.AssetVersion.showDimensionMin(AssetVersion.java:198) [:] |  | Question | M | 5/02/2016 Geani: I didn't add this and I don't know how to retest this. It' doesn't reprodus on my side, or i don't test is correctely. 09/03/2016 Geani: Who added this? It was makred "To Test". I don't know who te retest this | 2016-12-01
30 | Log out option doesn't work |  | Closed | M |  | 13/01/2016 | 13/01/2016
31 | Offerings Price list - The text almost overlats imput fileds. More spaces betwwen imput fileds and text under them is needed. Please see screenshot. |  | Closed | L |  | 13/01/2016 | 24/02/2016
32 | Offerings Price list - Default currency is an imput field. Should be like this? Or should be an drop down selector list like before? |  | Closed | L |  | 13/01/2016 | 21/01/2016
33 | Offerings Price list - Validation error goes out of error box. Please see screenshot 33. |  | Open | M | PRICELISTTABSFORM:PRICELISTTABVIEWID:PRICELISTGENERALFORM:TYPE: VALIDATION ERROR: VALUE IS NOT VALID PRICELISTTABSFORM:PRICELISTTABVIEWID:PRICELISTGENERALFORM:TYPE: VALIDATION ERROR: VALUE IS NOT VALID | 13/01/2016
34 | Natalie Geary : There is a typographical spelling error on the Dashboard page title; Merchendising should be corrected to read: Merchandising. It is in the Product Catalogue section. This should be corrected on all screens where Merchandising is used. I think it is spelled incorrectly throughout. |  | Closed | L | 26/01/2016 Geani: Can't find the text. I think it is fixed. | 13/01/2016 | 26/01/2016
35 | After some time (usuallty after being idle for 5 or so minutes) everything will stop working. To work again I need to refresh the page and log in again. then this error is displayed. After another refres everythig is working. This XML file does not appear to have any style information associated with it. The document tree is shown below. <partial-response id="j_id1"> <error> <error-name>class javax.faces.application.ViewExpiredException</error-name> <error-message> <![CDATA[ viewId:/pim/products/versionView/tabs/productTabs.xhtml - View /pim/products/versionView/tabs/productTabs.xhtml could not be restored. ]]> </error-message> </error> </partial-response> |  | Open | M | ERROR [org.keycloak.adapters.RefreshableKeycloakSecurityContext] (default task-30) Refresh token failure status: 400 {"error_description":"Refresh token expired","error":"invalid_grant"} 08/02/2016 Geani: Reopen as the issue still occurs | 18/01/2016
36 | Product creation - Trying to publish a draft without "Introduced" date set an error appear but is not clear enough. Error displayed is "May not be null May not be null." A more clear validation message should be displyed. |  | Closed | L | 08/02/2016 Geani: Can Not Test due to issue 55 24/02/2016 Geani : Can not test due to issue 60 25/02/02016 Geani: Can not test due to issue 71 15/03/2016 Geani Date is automatically added | 18/01/2016 | 15/03/2016
37 | Product creations - Assest images can't be uploaded. Selecting an immage from PC will be displayed for a brief second then dissapear. Because of this issue products can't be created. ERROR [org.keycloak.adapters.RefreshableKeycloakSecurityContext] (default task-19) Refresh token failure status: 400 {"error_description":"Refresh token expired","error":"invalid_grant"} |  | Closed | H | 19/01/2016 Geani : Fixed. | 18/01/2016 | 19/01/2016
38 | On leftside panel on Administration tab > Products tab > Category types, Properties and Property types end up with error when you try to add a product |  | Closed | M |  | 18/01/2016 Stefanc | 22/01/2016 Stefanc
39 | On leftside panel Administration tab > Offerings tab > Properties and Price list types tabs end up with error when you try to add a product |  | Closed | M |  | 18/01/2016 Stefanc | 22/01/2016 Stefanc
40 | On leftside panel on Media tab , all subtabs end up with error when you add a product |  | Closed | M |  | 18/01/2016 Stefanc | 22/01/2016 Stefanc
41 | Products - After retiring a product, there should be an option to reaactivate the product. Note: "Back to listing" button is not working after the product is retired. Note2: No error is displayed in the logs |  | Open | M | 08/02/2016 Geani: Can Not Test due to issue 55 22/02/2016 Geani : Reopen, issue still occurs | 18/01/2016
42 | The "plus" button allowing to add multi-valued properties is no longer available on product detail page. The same applies to minus buttons which allowed to remove given property value. |  | Closed | H | 22/02/2016 Geani: Reopen as this issue still occurs | 18/01/2016 | 25/02/06
43 | Product variant creation doesn't work. Clicking "create" does nothing. Later update: The variant is created in product list but no message is displayed at creation, and the "related product" list is not updated/remains empty. This issue can generate duplicate products. | Maciej | Dev Completed | H | On logs, after this line SEVERE [javax.enterprise.resource.webcontainer.jsf.context] (default task-18) javax.faces.el.EvaluationException: javax.ejb.EJBException: java.lang.ClassCastException: java.lang.String cannot be cast to com.brandpath.pim.model.template.TemplateProductPropertyValue lots of message appears | 18/01/2016 |  | Maciej
44 | After clicking "Actual size" button in add asset dialog and closing the popup window, the asset dialog closes, user is redirected to the main product page where error message is displayed. |  | Closed | H | 08/02/2016 Geani: Can Not Test due to issue 55 22/02/2016 Geani: Seems fixed, but there other issue at this momments that can simulate a fix for this issue. Needs more investigation. (Issue 55,56,57,58) 24/02/2016 Geani : Can no test due to issue 60 | 21/01/2016 | 25/02/2016
45 | The following warning is displayed in growl when product details page is loaded: The form component needs to have a UIForm in its ancestry. Suggestion: enclose the necessary components within <h:form> |  | Open | M | Probably due to lack of standard html namespace declaration in the page header or missing <h:form> tag. Should not be solved by setting "severity" parameter on growl component | 21/01/2016
46 | Exception while trying to navigate to the last page on the list of products |  | Closed | M | 2016-01-21 14:24:11,907 ERROR [org.jboss.as.ejb3.invocation] (default task-6) JBAS014134: EJB Invocation failed on component ProductDAO for method public com.brandpath.commons.reference.Identifiable com.brandpath.commons.model.dao.AbstractDAO.find(java.lang.Class,java.lang.Object) throws com.brandpath.commons.model.exception.DataAccessException: javax.ejb.EJBTransactionRolledbackException: id to load is required for loading 5/02/2016 Geani: I didn't add this and I don't know how to retest this. It' doesn't reproduce on my side, or i don't test it correctely. | 21/01/2016
47 | Messaging service corrupted in PIM - list of recipients not being loaded. |  | Open | M |  | 22/01/2016
48 | Administration tab, clicking on administration tab result in 404 error |  | Closed | M |  | 22/01/2016 Stefanc | 2016-05-02
49 | Offerings - Promotions - Vouchers - There is no "Add" button Should there be an "Add" button? Is there another way to create vouchers? 08/02/2016 Geani: The button appeared, but the it doesn't work |  | Closed | H | 08/02/2016 Geani: The button appeared, but the it doesn't work | 26/01/2016 | 25/02/2016
50 | After creating a price list, the default currency can't be changed. |  | Open | L | 24/02/2016 Geani : Can not retest due to issue 63 | 28/01/2016
51 | Product Creation - Assets can't be uploaded. Afer pressing "add" nothing happens, the the log generates this long (the text is too long to paste it here) error ERROR [com.brandpath.pim.web.controller.product.version.AssetVersion] (default task-8) ERROR: java.lang.NullPointerException 19/02/2016 Geani: Has this fix been deployed? | Maciej | Dev Completed | H | 19/02/2016 Geani: Has this fix been deployed? 24/02/2016 Geani : Can not test due to issue 60 25/02/2016 Geani: Please see issue 71 07/03/2016 PiotrI: Short investigation shows a problem with Calendar validation | 2016-05-02 |  | Maciej
52 | Design broken in PIM/OMS while using default zoom. At 75% zoom everything looks ok. Note: The resolution I use is 1366x768 Note: Same issue occurs at 75% zoom while editing an product. Note: This issue can be seen in product details, but can be seen in other places as well. Please see screenhots |  | Closed | H | 08/02/2016 Geani: The issue is fixed | 2016-05-02 | 2016-08-02
53 | Product Draft Edit - Pressing "edit" under the first asset image does nothing |  | Open | M | 24/02/2016 Geani : Can not retest due to issue 60 | 2016-05-02
54 | Product Draft Edit - While editing an already uploaded asset and changing the image, then pressing "Save" Nothing will happen and lots of errors appear in the log (too many to paste them here) | Arvind | Open | H | 24/02/2016 Geani : Can not retest due to issue 60 25/02/2016 Geani: I need to retest this 09/03/2016 Geani: Issue still occurs | 2016-05-02 |  | Arvind
55 | There are no save/publish/edit buttons for Offerings and Products. 19/02/2016 Geani: Has this fix been deployed? |  | Closed | H | 19/02/2016 Geani: Has this fix been deployed? | 2016-08-02 | 24/02/2016
56 | All navigation button are missing and no ptoduct can be open because it results in error page |  | Closed | H | [11:39:32] Emil Posmyk: wildfly with pim core and cimpl restarted [11:39:52] Emil Posmyk: all should works now, DB was stopped for a while | 15/02/2016 | 15/02/2016
56 | All drop down list doesn't work |  | Closed | H |  | 19/02/2016 | 24/02/2016
57 | Save button from product creation and offering creation does nothing Note: Might me related to issue 55 and 56? |  | Closed | H | ERROR [com.brandpath.pim.web.controller.product.version.ProductVersionController] (default task-3) javax.ejb.EJBTransactionRolledbackException: Validation failed for classes [com.brandpath.pim.model.product.ProductVersion] during persist time for groups [javax.validation.groups.Default, ] List of constraint violations:[ ConstraintViolationImpl{interpolatedMessage='may not be null', propertyPath=productId, rootBeanClass=class com.brandpath.pim.model.product.ProductVersion, messageTemplate='{javax.validation.constraints.NotNull.message}'} | 19/02/2016 | 24/02/2016
58 | PIM pages are loading slow. Betwwen 5-15 seconds |  | Closed | M |  | 19/02/2016 | 24/02/2016
59 | Product/Offerings to be able to open in browser tabs |  | Suggestion | L |  | 22/02/2016
60 | Product drafts can't enter in EDIT mode. Two errors "May not be null" appear when pressing EDIT. Because of this issue new prodcuts can't be created. No ERROR apprear in the logs. NOTE THIS ISSUE ONLY OCCURS IN TYPE "MOBILE" | Maciej | Open | L | 25/02/2016 Geani : THIS ISSUE OCCURS ONLY ON TYPE "MOBILE" 07/03/2016 Piotri: The issue is related with Product Template configuration - there are dropdown properties with no values pre-populated. This should be handled gracefully, but it's not actually an error. | 24/02/2016 |  | Maciej
61 | "Back to listing" button doesn't work |  | Closed | M |  | 24/02/2016 | Stefan : 15/3/2016
62 | Offerings - Offerings creation price list - There is no price list to select and there is not option to add one Schedule has display errors NOTE: Might affect issue 16 |  | Closed | H |  | 24/02/2016
63 | Offerings - price list creation - pressing save generates lots of messages in the log but no validation error appears. Nothign happens on the site. Note: Price list can't be created |  | Closed | H | 2016-02-24 10:34:18,804 ERROR [com.brandpath.pim.web.controller.offering.OfferingPriceList] (default task-7) javax.ejb.EJBTransactionRolledbackException: Validation failed for classes [com.brandpath.pim.model.offering.PriceList] during persist time for groups [javax.validation.groups.Default, ] List of constraint violations:[ ConstraintViolationImpl{interpolatedMessage='may not be null', propertyPath=defaultCurrency, rootBeanClass=class com.brandpath.pim.model.offering.PriceList, messageTemplate='{javax.validation.constraints.NotNull.message}'} ConstraintViolationImpl{interpolatedMessage='may not be null', propertyPath=siteId, rootBeanClass=class com.brandpath.pim.model.offering.PriceList, messageTemplate='{javax.validation.constraints.NotNull.message}'} ConstraintViolationImpl{interpolatedMessage='may not be null', propertyPath=description, rootBeanClass=class com.brandpath.pim.model.offering.PriceList, messageTemplate='{javax.validation.constraints.NotNull.message}'} ConstraintViolationImpl{interpolatedMessage='may not be null', propertyPath=name, rootBeanClass=class com.brandpath.pim.model.offering.PriceList, messageTemplate='{javax.validation.constraints.NotNull.message}'} ConstraintViolationImpl{interpolatedMessage='may not be null', propertyPath=tag, rootBeanClass=class com.brandpath.pim.model.offering.PriceList, messageTemplate='{javax.validation.constraints.NotNull.message}'} | 24/02/2016 | 26/02/2016
64 | Export buttons doesn't work |  | Open | M |  | 24/02/2016
65 | Products - manufacturer - creating a too long name result in a "null" value message Name i tried : geani test manufacturere tag Message : MAXIMUM LENGTH FOR THE PROPERTY "NULL": 1 |  | Open | M |  | 24/02/2016 | Stefan : 15/3/2016
66 | Media Asset Tab is empty |  | Open | M |  | 24/02/2016
67 | Administraction - products - catalogue type descprion generates this message MAXIMUM LENGTH FOR THE PROPERTY "NULL": 1 Descprion used : adm geani test catalogue type |  | Open | M |  | 24/02/2016
68 | Validation error when attempting to modify a set of voucher instances |  | Closed | H | 25/02/2016 Geani : Issue still occurs | 24/02/2016
69 | Voucher Instancces - Pressing the box to select all visible voucer instances doesn't activate buttons to delete or modify the vouchers |  | Open | M |  | 25/02/2016
70 | Offerings details - After creating an ofering, entering on draft mode will remove all details. Also not all fiels added by the "+" have the option to be removed If an filed is left empy after saving the draft, trying to publish it will give validation error. But if in this state text is introduced (without editing the draft) the validation error doesn't occur but the offering is published with an empty field |  | Open | M | 25/02/2016 Geani: If it isn't clear please call me on skype | 25/02/2016
71 | Product creation - Selecting different TYPE while creating a new product, various issues occurs. e.g Selecting PHYSICAL type - details field is empty - assets can't be uploaded Selecting MOBILE - Product draft can't enter in edit mode Selecting HANDSET - Assets can't be added untill "Introduced date" is added NOTE - NEEDS MORE INVESTIGATION | Arvind | Closed | H | Opening a prodcut affected by this issue generates the following error : ERROR [com.brandpath.pim.web.controller.product.version.AssetVersion] (default task-2) ERROR: java.lang.NullPointerException the error is longer 09/03/2016 : Geani I will brake this into separate issues | 25/02/2016 |  | Arvind
72 | After creating a product, changing its type doesn't actually chage it. It has to be created on that type, or published at least once | Cristian | Closed | H | You can change it's status to draft to make the change. Is this desired behaviour? 08/04/2016 Geani: There was a issue not beeing able to enter in edit mode. It is fixed now, and this issue was fixed along with it. Thank you. | 26/02/2016 |  | Cristian
73 | Offerings price list - Why only pricelist without offerings are displayed? |  | Question | M |  | 26/02/2016
74 | Offerings - publishing offerings doesn't update the title untill refreshign the page : (geani offering 2602 1410 [Draft v.1)]) STATUS PUBLISHED (V.1) |  | Open | H |  | 26/02/2016
75 | Offering creation - In orde to create an offering you must add the the device and click save enter in edit mode, add details, save enter edit mode again, add price list, save, publish Everythign should be done in one EDIT,SAVE,PUBLISH 8/4/2016 Geani: Please see comments |  | Open | H | 8/4/2016 Geani: After entering in edit mode, select "Testlist2" add a price list THEN add a product to the offering, the details and the price list will be rest if the draft was not saved before adding the product. ## Cristian: To approve if not auto refreshing of product add is an accepted solution. Details and Pricelist tabs are not cleaned anymore before Save. 14/03/2016 Geani: After adding product it cant be see in Draft Edit mode. After pressing save a null offering is displayed | 26/02/2016 |  | Cristian
76 | Offerings price list - assigned pricelist can't be removed |  | Open | M |  | 26/02/2016
77 | Offerings creation - price llist price doesn't update |  | Closed | H | As I see, price list price is saved at Save button press. Need confirmation. 14/03/2016 Geani: After offering is created and published the price doesn't appear. Please see offering 14/03/2016 15/03/2016 Geani : updated with issue 109 | 26/02/2016 | 15/03/2016 | Cristian
78 | Created offerings don't appear on reftest |  | Closed | H | Offerings should be first assigned to a price list for RefSite to be visible and cachce needs to be refreshed Offerings appeard on reftest | 26/02/2016
79 | Product name search - Search vor a text in the middle of a name displays 0 result |  | Open | M |  | 26/02/2016
80 | Offerings - assigned products can't be removed or edited after publisching Note: new produts can't be added to the offering | Maciej | Question | H |  | 2016-01-03 |  | Maciej
81 | Default status filter only show Published prodcuts |  | Open | M |  | 2016-01-03
82 | Offering variant - after pressing "create" button the form is closed but the variant is not created | Maciej | Dev Completed | H | 10/3/2016 maciejs: offering variant can be created after filling in all mandatory input filelds. Offering variants list is updated as well. | 2016-01-03 |  | Maciej
83 | Product history - no mouse over descriop for copy button |  | Open | L |  | 2016-02-03
84 | Prodcut history - According to HLR search/filters for prodcut history is missing. Also details about prodcut drodcut details is missing from history tab |  | Open | L |  | 2016-02-03
86 | According to HLR - HTML description is missing from prodcuts/offerings/bundles | Piotr | Open | H | 7/3/2016 PiotrI: Configuration issue | 2016-02-03 |  | Piotr
87 | According to HLR - Offerings (bundles) option for uploading images is missing | Arvind | Open | H | 07/03/2016: Functionality is underdevlopment | 2016-02-03 |  | Arvind
88 | Redirects (to OMS/CAI from the upper tab buttons) are invallid |  | Open | L |  | 2016-02-03
89 | According to HLR (rediness) - Ratings & Reviews functionalilty is missing from PIM |  | Open | M |  | 2016-02-03
90 | According to HLR (rediness) - Assigning accesory to prodcuts functionality is missing |  | Open | M |  | 2016-02-03
91 | Offerings tab, while you are on edit mode, in price listing tab, when you try to schedule the product there is a display issue on "Select time" category ( check screenshot 53 ) |  | Open | L |  | 2016-02-03
92 | According to HLR (rediness) - Option to clone product is missing |  | Open | M |  | 2016-02-03
93 | According to HLR (rediness) - Services are missing |  | Open | M |  | 2016-02-03
94 | According to HLR (rediness) - Trade-in checkbox/field is missing |  | Open | M |  | 2016-02-03
95 | Offerings tab - Edit the product - Price list tab, when you set a schedule date and hour, that information is not listed anywhere. Option to edit/cancel the schedule should also be available |  | Open | M |  | 2016-02-03
96 | Abort draft doesnt work unless you complete the "Date" field, "May not be null" validation error appears. |  | Open | H | 07/03/2016: Should be fixed with Bug#51 | 2016-02-03
97 | Price list details, history is empty. |  | Open | L |  | 2016-02-03
98 | No Popup message on product workflow actions (i.e. Save, Publish etc). |  | Open | L |  | 2016-07-03
99 | Errors in logs when Saving Offerings (functionality seems to be working) | Arvind | Open | M | 2016-03-07 13:27:14,078 ERROR [org.jboss.as.ejb3.invocation] (default task-13) JBAS014134: EJB Invocation failed on component ProductVersionService for method public com.brandpath.pim.model.product.ProductVersion com.brandpath.pim.business.service.product.ProductVersionService.findProductVersionWithInitialization(java.lang.Integer) throws com.brandpath.commons.business.exception.ServiceException: javax.ejb.EJBException: javax.persistence.NoResultException: No entity found for query | 2016-07-03 |  | Arvind
100 | Price List at offerings can't be searched | Arvind | Open | H | 2016-03-07 13:29:31,596 ERROR [org.jboss.as.ejb3] (default task-17) javax.ejb.EJBTransactionRolledbackException: Parameter value [1, BPCREFSITE, BPC Reference Site] did not match expected type [com.brandpath.pim.model.offering.PriceListType (n/a)] | 2016-07-03 |  | Arvind
101 | Performance of the product details page - over 900 queries executed when opening this page | Maciej | Open | M |  | 2016-07-03 |  | Maciej
102 | In Related offerings tab - exception occurs - can't view the offering (if related offerings exists) | Maciej | Dev Completed | H |  | 2016-07-03 |  | Maciej
103 | Price list - cannot view more than 1 price type | Maciej | Open | M |  | 2016-07-03 |  | Arvind
104 | Offerings listing - cannot change paging | Cristian Uta | Dev Completed | L | Fixed, paging is now available. Cristian | 2016-07-03 | 15/3/2016 | Cristian Uta
105 | Images are not visible in the offerings | Piotr | Open | M | 3/7/2016 PiotrI: We need to change the logic on how images are viewed for offerings | 2016-07-03 |  | Piotr
106 | Prodcut creation - Led Lamp - Error generated in the logs Details are missing Assets can't be uploaded. "Choose" button is missing Product can't be published. |  | Open | H | 2016-03-10 10:30:42,940 ERROR [com.brandpath.pim.web.controller.product.version.AssetVersion] (default task-31) ERROR: java.lang.NullPointerException | 2016-10-03
107 | Offerings - Assets can't be uploaded. "Choose" button is missing |  | Open | M |  | 14/03/2016
108 | Offerings - The view/edit button is missing on some resolutions, tested on 1280x1024 resolution and 1366x768 |  | Open | H |  | 14/03/2016
109 | Offerings - Adding multiple price list to an offering will display "Price 0" on offering listing page |  | Open | H |  | 14/03/2016
110 | Product - Asset - when you add an asset there is a blue square, which if you click it and try to add another image you get the following error : Maximum number of files exceeded, please check ( screenshot 54 ) |  | Open | L |  | 14/03/2016
111 | Product creation - Mobile type creates duplicate prodcuts |  | Dev Completed | H | As tested in pimtest(15mar.) mobile type product creation creates the right number of products - only one. ## Can someone please check if bug is reproducible elsewhere? 15/03/2016 13:57 Geani: Pleasee product geani duplicate test 15032015 1325 v1, in prodcut listing appear two of them) Screenshot for confrimation attached. Please see screenshot 111 | 15/03/2016 |  | Cristian Uta
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294

## PIM Screenshots
ID | Screenshot
Bug id 3
Bug ID 5
Bug ID 6
Bug ID 7
Bug ID 8
Bug ID 10
Bug ID 11
Bug ID 19
Bug ID 20
Bug ID 22
Bug ID 24
Bug ID 25
Bug ID 28
Bug ID 31
Bug ID 33
52
53
54
111

## OMS Bug List
Bug ID | Description | Assigned To | Status | Priority (L/M/H) | Testing Status/Comment | Date Raised | Date Closed | Status | Prio
13 | "Administration" tab button gives the following error : "/pim/offerings/versionView/index.xhtml Not Found in ExternalContext as a Resource" |  | Open | M | 13/01/2016 Geani : new error is displaed on PIM page. log: WARNING [javax.enterprise.resource.webcontainer.jsf.application] (default task-20) JSF1064: Unable to find or serve resource, /pim/administration/media/size/index.xhtml. | 17/12/2015
1 | Internal server error on every page except dashboard, and sales orders (pressing from the upper link) |  | Closed | H | Permission issue, fixed now | 2016-01-03 | 2016-04-03
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34 | .
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59

## RefTest Bug List
Bug ID | Description | Assigned To | Status | Priority (L/M/H) | Testing Status/Comment | Date Raised | Date Closed | Status | Prio
13 | "Administration" tab button gives the following error : "/pim/offerings/versionView/index.xhtml Not Found in ExternalContext as a Resource" |  | Open | M | 13/01/2016 Geani : new error is displaed on PIM page. log: WARNING [javax.enterprise.resource.webcontainer.jsf.application] (default task-20) JSF1064: Unable to find or serve resource, /pim/administration/media/size/index.xhtml. | 17/12/2015
1 | Oders can't be completed. After pressing "Proceed to PayPal" error is displayed INTERNAL SERVER ERROR It seems there was a problem with that request |  | Open | H |  | 25/02/2016
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
.
33
34
35
56
Open
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52