## Release Summary
Release Summary
Brandpath are currently reviewing the checklist to be supplied to Samsung stakeholders to enable checks & balances to be performed.
Environment | Sabre 2.0 Production
Release Date: | 10th January 2016
Release Time: | 10am
Downtime: |  | Email |  |  |  | Please advise of any concerns at least 1 hour prior to release time. Otherwise Brandpath will assume all stakeholders (Internal & External) are in agreement.
Implementation Lead: | Kathryn Ward-Gittos | Kathryn.WardGittos@brandpath.com
Dev Lead: | Victor Sarateanu | victor.sarateanu@brandpath.com | Phone Number
Issue Contact: | NOC (24/7) | support@brandpath.com | 0044 (0) 162 891 8136
Issue Escalation: | NOC Escalation | support@brandpath.com | 0044 (0) 1628 539 470
External Comms: | Customer distribution list | Paul Bolton, Jane Aitken, Andy Gill, Gabriel
Internal Comms: | Internal distribution list | Account Manager, NOC, Dev Teams, Stakeholders, Testers, David, Piotr, Victor, Laviniu
Issues for Deployment in this Release
Issue Type | Jira Issue key | Jira Summary | Module | Owner | Tested By | Front End Effected? | Risk | PVT Owner * | Comments
Story | SCR-687 | End of Sale - offers amended removal of LPs and page | WS | Kathryn | Geani | Y | Small | Geani
Sub-task | SCR-691 | End of Sale- offers banner update | WS | Kathryn | Geani | Y | Small | Geani
Story | SCR- 646 | Reshuffle of online exclusive accessories | WS | Kathryn | Geani | Y | Small | Geani
Story | SCR-650 | Insurance relaunch - DnG | WS | Kathryn | Geani | Y | Small | Geani
Sub-task | SCR-589 | Fitness page link and info correction | WS | Killian | Geani | Y | Small | Geani
* See tasks on next Tab
Note: For back-end releases: a sign-off meeting is required with David McLean prior to release.

## Deployment Plan
Front End Deployment Plan (owner = Implementation Team) |  | Tuesday 10th Jan | [9 empty] | Deployment Day
| UK Time |  |  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 |  |  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
| Romania Time |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Circulate Release Summary | 48 hrs prior | [23 empty] | Release Summary
Marketing sign-off (no changes) | Marketing
Int UAT | Marketing
Merge Code for STG & Test merged code | Victor
Deploy to STG | Victor
Regresion Test | Test Team
Ext UAT (Samsung Sign-off) | Marketing
Governance / Sign-off Mtg | with David
Deploy to Live | Victor
PVT | Tester
Regression Testing | Tester
Deployment Window

## PVT & Regression
|  |  | Functional Change | Marketing / Promotional Change
PVT Checklist | 1 | Test functional changes of the deployment / new products | y | y
(Production Verification Testing) |  | Visual checks: cosmetics, content, pricing, checkout | y | y
|  | Functional - confirm flow is working & test order (bank transfer) | y | n
1.1 SCR-687 - homepage check baner / cross browser
1.2 - homepage check right tile for removing chritmas theme / cross browser
1.3 - check SerifTV tile / cross browser
2.1 SCR-691 - check tile for removing chritmas theme / cross browser
3.1 SCR-646 - visual checks / cross browser
3.2 - Functional testing (add to basket / find out more) / cross browser
4.1 SCR-650 - visual checks / cross browser
4.2 - Functional testing (add to basket / various buttons on page) / cross browser
5.1 SCR-589 - Functional testing (add to basket / various buttons on page) / cross browser
5.2 - Check Content box titles at tile rotation
PPVT Checklist | 2 | Monitor active data against those products (extended period ie. 24hr check) | y | y
(Post Production Verification Testing)
Regression Checklist | 3a | Front End checks
(ideally also on merged code within staging first, prior to deployment) |  | Image, pricing, sku code, product name, on sale button, etc.) | y | n
|  | Test Order - bank transfer, Worldpay, Paypal | y | y
|  | Check web sales reports for sales & details | y | n
|  | Check 3B13 (plus ensure FOC item is not in 3B13) | y | n
|  | Google Product Feed | y | y
|  | Adobe Tagging | y | n
|  | Google analytics site catalyst | y | n
| 3b | Back End Checks
|  | PIM (ie. products, offerings, pricing, performance, creation, updating, imagery, promotional content) | y | n
|  | OMS (ie. orders reaching OMS, order detail visable, order progression, cancelling, refunds, searching) | y | n