## Release Summary
Release Summary
Brandpath are currently reviewing the checklist to be supplied to Samsung stakeholders to enable checks & balances to be performed.
Environment | Sabre 2.0 Production
Release Date: | 2017-02-03
Release Time:
Downtime: |  | Email |  |  |  | Please advise of any concerns at least 1 hour prior to release time. Otherwise Brandpath will assume all stakeholders (Internal & External) are in agreement.
Implementation Lead: | Kathryn Ward-Gittos | Kathryn.WardGittos@brandpath.com
Dev Lead: | Dragos Cirjan | dragos.cirjan@brandpath.com | Phone Number
Issue Contact: | NOC (24/7) | support@brandpath.com | 0044 (0) 162 891 8136
Issue Escalation: | NOC Escalation | support@brandpath.com | 0044 (0) 1628 539 470
External Comms: | Customer distribution list | TBC
Internal Comms: | Internal distribution list | Account Manager, NOC, Dev Teams, Stakeholders, Testers, David, Piotr, Victor, Laviniu
Issues for Deployment in this Release
Issue Type | Jira Issue key | Jira Summary | Module | Owner | Tested By | Front End Effected? | Risk | PVT Owner * | Comments
Story | SCR-779 | Homepage banners | SABPRD - SITE | Kathryn | Geani | Y | Small | Geani
Task | SCR-786 | Memory Month - 128 gb memory card with all tablet devices | SABPRD - SITE | Kathryn | Geani | Y | Small | Geani
Bug | SCR-790 | Valentines Home Appliance Cashback | SABPRD - SITE | Kathryn | Geani | Y | Small | Geani
Note: For back-end releases: a sign-off meeting is required with David McLean prior to release. | [7 empty] | * See tasks on next Tab

## Deployment Plan
Front End Deployment Plan (owner = Implementation Team) |  | Thursday 2nd of Feb | [9 empty] | Friday 3rd of Feb
| UK Time |  |  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 |  |  | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
| Romania Time |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 |  | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Circulate Release Summary | 48 hrs prior | [23 empty] | Release Summary
Marketing sign-off (no changes) | Marketing
Int UAT | Marketing
Merge Code for STG & Test merged code | Victor
Deploy to STG | Victor
Regresion Test | Test Team
Ext UAT (Samsung Sign-off) | Marketing
Deploy to Live | Victor | bar: 9 11
PVT | Tester | bar: 9 11
Regression Testing | Tester | bar: 9 11
Deployment Window

## PVT & Regression
|  |  | Functional Change | Marketing / Promotional Change
PVT Checklist | 1 | Test functional changes of the deployment / new products | y | y
(Production Verification Testing) |  | Visual checks: cosmetics, content, pricing, checkout | y | y
|  | Functional - confirm flow is working & test order (bank transfer) | y | y
|  | 1.a SCR-779 - homepage banners / cross browser | n | Y
|  | 1.b Check offers tile / cross browser | n | Y
|  | 2. SCR-786 - Check offers tile / cross browser | n | Y
|  | 3. SCR-790 - Check link redirect from banner | n | Y
|  |  | n | Y
|  |  | n | Y
|  |  | n | Y
|  |  | n | Y
|  |  | n | Y
|  |  | n | Y
|  |  | n | Y
|  |  | n | Y
PPVT Checklist | 2 | Monitor active data against those products (extended period ie. 24hr check) | y | y
(Post Production Verification Testing)
Regression Checklist | 3a | Front End checks
(ideally also on merged code within staging first, prior to deployment) |  | Image, pricing, sku code, product name, on sale button, etc.) | y | n
|  | 1.a SCR-779 - homepage banners / cross browser | n | y
|  | 1.b Check offers tile / cross browser | n | y
|  | 2. SCR-786 - Check offers tile / cross browser | n | y
|  | 3. SCR-790 - Check link redirect from banner | n | y
|  |  | n | y
|  |  | n | y
|  |  | n | y
|  |  | n | y
|  |  | n | y
|  |  | n | y
|  |  | n | y
|  |  | n | y
|  |  | n | y
|  |  | n | y
|  | Test Order - bank transfer, Worldpay, Paypal | y | y
|  | Check web sales reports for sales & details | y | n
|  | Check 3B13 (plus ensure FOC item is not in 3B13) | y | n
|  | Google Product Feed | y | y
|  | Adobe Tagging | y | n
|  | Google analytics site catalyst | y | n
| 3b | Back End Checks
|  | PIM (ie. products, offerings, pricing, performance, creation, updating, imagery, promotional content) | y | n
|  | OMS (ie. orders reaching OMS, order detail visible, order progression, cancelling, refunds, searching) | y | n

## NFR
Category | NFR | CheckList
Security | Login / Access levels | not applicable
(and PCI compliance) | Create, Read, Update, and Delete (CRUD) levels. | not applicable
| Access permissions for application data may only be changed by the system’s data administrator | not applicable
| Password requirements – length, special characters, expiry, recycling policies, 2FA | not applicable
| Inactivity timeouts – durations, actions, traceability | not applicable
| System data backed up every x hours and copies stored in a secure off-site location | not applicable
| Encryption (data in flight and at rest) – All external communications between the system’s data server and clients must be encrypted | not applicable
| Data Classification / System Accreditation: All Data must be protectively marked and stored / protected. | not applicable
Audit | System must maintain full traceability of transactions | not applicable
(Define the level of traceability for transactions required) | Audited Objects are defined | not applicable
| Audited database fields – which data fields require audit info? | not applicable
| File characteristics – size before, size after, structure | not applicable
| User and transactional time stamps, etc | not applicable
Capacity | Throughput – how many transactions at peak time does the system need to be able to handle | not applicable
(Provisioning for growth) | Storage – (memory/disk) – volume of data the system will page / persist at run time to disk | not applicable
| Year-on-year growth requirements (users, processing & storage) | not applicable
| e-channel growth projections | not applicable
Performance | Response times – application loading, browser refresh times, etc. | not applicable
| Processing times – functions, calculations, imports, exports | not applicable
| Query and Reporting times – initial loads and subsequent loads, ETL times | not applicable
| Interoperbility | not applicable
Availability | Hours of operation | not applicable
(uptime) | holidays, maintenance times, etc | not applicable
| • Locations of operation – where should it be available from, what are the connection requirements? | not applicable
Reliability | The ability of a system to perform its required functions under stated conditions for a specific period of time. | not applicable
| Mean Time Between Failures – What is the acceptable threshold for down-time? | not applicable
| Mean Time To Recovery – if broken, how much time is available to get the system back up again? | not applicable
Recoverability | Recovery process | not applicable
(in the event of failure..) | Recovery Point Objectives (RPO) | not applicable
| Recovery Time Objectives (RTO) | not applicable
| Backup frequencies – how often is the transaction data, config data, code backed-up? | not applicable
Robustness | The ability of the system to resist change without adapting its initial stable configuration – operational characteristics with growth? | not applicable
| Fault trapping (I/O) , Application Hooks, SMNP – how to handle failures ? | not applicable
Integrity | Application Integrity | not applicable
(Consistency of events, values, methods, measures, expectations & outcomes) | Data integrity – referential integrity in database tables and interfaces | not applicable
| Information Integrity – during transformation | not applicable
not applicable
Maintainability | Conformance to Enterprise Architecture standards | not applicable
(The ease with which the system can be maintained) | Conformance to Technical design standards | not applicable
| Conformance to coding standards | not applicable
| Conformance to best practices. | not applicable
Usability | User Standards (Look / Feel) | not applicable
| Internationalization / localization requirements – languages, spellings, keyboards, etc | not applicable
Documentation | User Documentation | not applicable
| System Documentation (Production Acceptance?) | not applicable
| Help? | not applicable
| Training Material | not applicable
Mobile Optimisation | Mobile Responsiveness - ie mobile phones and tablets | yes
Browser Compatibility | Compatible with all supported browers and versions thereof | yes