## Versioning
Version | Comments | Author | Date
0.1 | Test Cases 1-17 and subcases created | Alin Radu, Catalin Fleancu | 11th August 2016
0.2 | Test Cases Run | Catalin Geani Fleancu | 12th August 2016

## Customer Service
Sabre 2.0 - Test Cases
Feature |  | Live URL |  |  | Test URL
Customer Service |  | tbc |  |  | eCommerce platform : https://sabdev.brandpath.net/ OMS platform: https://sabdevoms.brandpath.net/oms-web/
No | Content | No | Test case | Condition | Expected Result | Pass/Fail | Actual Result / Bugs | Comments | Date
1 | Customer Service | 1 | Create order
|  | 1.1 | Create order with Paypal
|  |  | Open eCommerce platform |  | Home page will be displayed | Passed |  |  | 2016-08-12
|  |  | Go to any category (example: Mobiles & wearables) |  | Listing page will be displayed | Passed |  |  | 2016-08-12
|  |  | Press "Add to basket" |  | Popup confirmation will be displayed | Passed |  |  | 2016-08-12
|  |  | Press "See basket" |  | Basket page will be displayed | Passed |  |  | 2016-08-12
|  |  | Select Paypal payment type, then select check box "I understand and agree to the Samsung Terms and Conditions" then press proceed to checkout |  | Login page will be displayed. | Passed |  | Note: PayPal credit not available for testing | 2016-08-12
|  |  | Press "continue as guest" |  | checkout page will be displayed | Passed |  |  | 2016-08-12
|  |  | Fill all fields and press checkout |  | Payment journey will start according to selection. Order confirmation received at email filled in Details page (please use your own email). | Passed |  | PayPal : bpc@pj-interactive.ro - S1nc1ty0 | 2016-08-12
|  |  | Note order reference number |  | After payment is complete, Thank you Page will be displayed. | Passed |  |  | 2016-08-12
|  | 1.2 | Create order with Worldpay
|  |  | Repeat previous steps and select Worldpay at basket as payment option |  | After payment is complete, Thank you Page will be displayed, confirmation email received - order moves to OMS | Passed |  | WorldPay : 4444333322221111 expire date in the future (not longer than 3 years) any name any CVV2 | 2016-08-12
|  | 1.3 | Create order with Bank Transfer
|  |  | Repeat previous steps and select Bank Transfer at basket as payment option |  | Thank you Page will be displayed, confirmation email received - order moves to OMS | Passed |  |  | 2016-08-12
|  | 2 | Check current status
|  | 2.1 | Search by Order Number
|  |  | Operator goes to "Advanced search" and select filter options, adding order reference |  | Orders list is updated based on filter selections | Passed |  |  | 2016-08-12
|  |  | Operator opens order summary and goes to order history tab |  | Order history operations is displayed. | Passed |  |  | 2016-08-12
|  | 2.2 | Search by Email/Name
|  |  | Operator goes to "Advanced search" and select filter options, adding email/Name , if customer does not remember Order Reference number |  | Orders list is updated based on filter selections | Passed |  |  | 2016-08-12
|  |  | Operator opens order summary and goes to order history tab |  | Order history operations is displayed. | Passed |  |  | 2016-08-12
|  | 3 | Order Validation
|  | 3.1 | Order approve - Complete fraud check
|  |  | PayPal, WorldPay and Bank transfer orders are checked automatically | Same Shipping and Billing address | PayPal, WorldPay and Bank transfer orders to be automatically approved or rejected by fraud check | Passed |  |  | 2016-08-12
|  |  | Operator goes to "Order Approval" and select filter options | Different Shipping and Billing address (Bank Transfer orders are skipping this step) | Orders list is updated based on filter selections | Passed |  |  | 2016-08-12
|  |  | Press quarantine button |  | Popup with textbox for quarantine message appears. Options to abort or continue approve are present. | Passed |  |  | 2016-08-12
|  |  | Press approve button |  | Popup with textbox for approval message appears. Options to abort or continue approve are present. | Passed |  |  | 2016-08-12
|  |  | Press reject button |  | Popup with textbox for reject message appears. Options to abort or continue approve are present. | Passed |  |  | 2016-08-12
|  | 4 | Order Validation
|  | 4.1 | Managing Bank Transfer Orders
|  |  | Place order on web |  | Order goes to status "Payment pending" | Passed |  |  | 2016-08-12
|  |  | Operator goes "Payment handling" inside OMS and search for the order reference and status "Payment Pending" |  | Order is displayed with option to cancel or approve | Passed |  |  | 2016-08-12
|  |  | Press "Payment failed" |  | Popup is displayed with option to abort or continue the operation. Text box is also displayed to leave comment for the operation. | Passed |  |  | 2016-08-12
|  |  | Press "Payment received" |  | Popup is displayed with option to abort or continue the operation. Text box is also displayed to leave comment for the operation. Order is picked up by automate processes | Passed |  |  | 2016-08-12
|  |  | Operator should upload payment confirmation |  | Operator opens order summary and goes to attachments tab and uploads payment confirmation. | Passed |  |  | 2016-08-12
|  |  | View/download payment confirmation from save screen |  | View/Download | Can not test |  | Bug already raised with technical team | 2016-08-12
|  | 5 | Order Validation
|  | 5.1 | Managing Orders without stock
|  |  | Operator goes to "backorder management" section of OMS |  | Option to search orders by different status is displayed (Awaiting stock, Pre Order, Awaiting stock ERP, Release back order). Orders with "Waiting stock ERP" can be managed inside ERP. Orders with "Release back order" are managed by automated tasks. | Passed |  |  | 2016-08-12
|  |  | Operator selects "Reject" | Order status "Awaiting stock" | Popup with option to continue or abort operation is displayed. Textbox to leave comment for the operation is displayed. | Passed |  |  | 2016-08-12
|  |  | Operator selects "Release back order" | Order status "Awaiting stock" | Popup with option to continue or abort operation is displayed. Textbox to leave comment for the operation is displayed. Order is sent to "Back order" automate tasks. | Passed |  |  | 2016-08-12
|  | 6 | Order Validation
|  | 6.1 | Managing exceptional order types (Pre-order & RE)
|  |  | Development in progress, please test in 2.1 version |  |  | Can not test |  |  | 2016-08-12
|  | 7 | Order details
|  | 7.1 | Manage a backorder / Awaiting stock
|  |  | Operator goes to "Backorders management" |  | Options to select filters and input order number is displayed | Passed |  |  | 2016-08-12
|  |  | Select "Awaiting stock" filter and input order number |  | Orders are displayed according to filter selected | Passed |  |  | 2016-08-12
|  |  | Press "release backorder" |  | Popup with textbox is displayed and option to continue or abort the operation. Orders are sent to automatic back order system processing | Passed |  |  | 2016-08-12
|  |  | Press reject |  | Popup with textbox is displayed and option to continue or abort the operation. Orders are canceled | Passed |  |  | 2016-08-12
|  | 8 | Cancel an order
|  | 8.1 | Bank transfer orders
|  |  | Operator goes to "Payment handling" inside OMS and search for the order reference |  | Order is displayed with option to cancel or approve | Passed |  |  | 2016-08-12
|  |  | Press "Payment failed" |  | Popup is displayed with option to abort or continue the operation. Text box is also displayed to leave comment for the operation. | Passed |  |  | 2016-08-12
|  | 8.2 | Orders without stock
|  |  | Operator goes to "backorder management" section of OMS |  | Option to search orders by different status is displayed (Awaiting stock, Pre Order, Awaiting stock ERP, Release back order). Orders with "Waiting stock ERP" can be managed inside ERP. Orders with "Release back order" are managed by automated tasks. | Passed |  |  | 2016-08-12
|  |  | Operator selects "Reject" | Order status "Awaiting stock" | Popup with option to continue or abort operation is displayed. Textbox to leave comment for the operation is displayed. | Passed |  |  | 2016-08-12
|  | 8.3 | Order Approval
|  |  | Operator goes to "Order Approval" tab and select filter options | Different Shipping and Billing address (Bank Transfer orders are skipping this step) | Orders list is updated based on filter selections | Passed |  |  | 2016-08-12
|  |  | Press reject button |  | Popup with textbox for reject message appears. Options to abort or continue approve are present. | Passed |  |  | 2016-08-12
|  | 9 | Order details
|  | 9.1 | Cancel/Swap an item in an order
|  |  | Operator should cancel old order |  | Old order is canceled, given it was not passed to ERP | Passed |  |  | 2016-08-12
|  |  | Create new order with the new details |  | New order should be created Reference the old order in the notes section of the order record | Passed |  |  | 2016-08-12
|  | 10 | Order details
|  | 10.1 | Edit address in an order
|  |  | Operator should cancel old order |  | Old order is canceled, given it was not passed to ERP | Passed |  |  | 2016-08-12
|  |  | Create new order with the new details |  | New order should be created Reference the old order in the notes section of the order record | Passed |  |  | 2016-08-12
|  | 11 | Order details
|  | 11.1 | Refund tracking
|  |  | Operator opens order summary and goes to Payment tab | Refund has been made | Refunds details and status is displayed. | Passed |  |  | 2016-08-12
|  | 12 | Order details
|  | 12.1 | Leave a note marking the customer's desire
|  |  | Operator opens order summary and goes to Comments tab |  | Previous comments are displayed and status updates. Option to add a new comment is displayed and they can be Customer/internal | Passed |  |  | 2016-08-12
|  | 13 | Order details
|  | 13.1 | Check return log
|  |  | Operator opens order summary and goes to Return tab |  | Return list is displayed with all relevant informations. | Passed |  |  | 2016-08-12
|  | 14 | Order details
|  | 14.1 | Check stock of a product
|  |  | 1.Check product on eCommerce |  | If product is out of stock, buy button will display "Out of stock" | Can not test |  | No feed from ERP | 2016-08-12
|  |  | 2.Operator goes to "Advanced search" and select filter options, adding order reference |  | Orders list is updated based on filter selections. If product is out of stock, the order will have status "Awaiting stock". | Passed |  |  | 2016-08-12
|  | 15 | Commercial Gestures
|  | 15.1 | Commercial Gestures - Discount and partial refund
|  |  | Operator goes to "Advanced search" and select filter options, adding order reference then opens order summary |  | Orders list is updated based on filter selections and order summary is displayed | Passed |  |  | 2016-08-12
|  |  | Operator opens order summary and goes to Payment tab |  | Payment and refunds details and status is displayed. | Passed |  |  | 2016-08-12
|  |  | Operator places "+" at Refund section in the Payment tab |  | Popup with refund details will be displayed | Can not test |  | Partial refund development in progress. Full refund is working. Refund needs to be approved to take place | 2016-08-12
|  | 16 | Manual orders
|  | 16.1 | Manual orders (made by phone)
|  |  | Phone orders will be done by operator through eCommerce interface |  | The order will act as an normal order. Phone orders should be Bank transfer only, but the system won't enforce this option. | Passed |  |  | 2016-08-12
|  | 17 | Check tracking information
|  | 17.1 | Check tracking information
|  |  | This can be done via web and link sent to customer on confirmation email. This can also be checked via OMS order status. |  |  | Passed |  |  | 2016-08-12

## Screenshots
Screenshots
ID | Screenshot

## Order Flow TestCases (hidden)
` |  | Sabre 2.0 - Offline Order Flow TestCases
No |  | Test case | Condition | Expected Result | Pass/Fail | Actual Result | Comments
Fraud Check = Rejected
1
| I | Fraud Check = rejected |  | Order cancel | Not Runned |  | N/A at this moment 13-07-2016
Fraud Check = Approved
PayPall
2
| I | Fraud Check = Approved |  | Go to stock check | Passed |  | SUK01LT-OSXR-RJUK / H771652
| II | Stock check = Awaiting stock |  | Go to Back order Processing | Failed | Stuck at "Awaitting stock | SUK01FC-TCMX-OAKI
| III | Stock check = Stock Available |  | Go to Payment capture | Passed |  | SUK01LT-OSXR-RJUK / H771652
| IV | Payment capture = rejected |  | Order cancel | Not Runned
| V | Payment capture = taken |  | Order dispatch (ERP) | Passed |  | SUK01LT-OSXR-RJUK / H771652
| VI | Order dispatch = Canceled, rejected |  | Order cancel | Passed |  | SUK01DR-AVPD-TTOE
| VII | Order dispatch = Accepted |  | Order Processing (EDI) | Passed |  | SUK01LT-OSXR-RJUK / H771652
| VIII | Order Processing (EDI) = completed |  | Order Completed | Passed |  | SUK01LT-OSXR-RJUK / H771652
WorldPay
3
| I | Fraud Check = Approved |  | Go to stock check | Passed |  | SUK01II-IOQA-GYOT
| II | Stock check = Awaiting stock |  | Go to Back order Processing | Failed | Stuck at "Awaitting stock | SUK01II-IOQA-GYOT
| III | Stock check = Stock Available |  | Go to Payment capture | Passed |  | SUK01SY-NTKE-PRBF
| IV | Payment capture = rejected |  | Order cancel | Not Runned
| V | Payment capture = taken |  | Order dispatch (ERP) | Failed | Payment capture failed | SUK01SY-NTKE-PRBF
| VI | Order dispatch = Canceled, rejected |  | Order cancel | Not Runned
| VII | Order dispatch = Accepted |  | Order Processing (EDI) | Not Runned
| VIII | Order Processing (EDI) = completed |  | Order Completed | Not Runned
Bank transfer
4
| I | Fraud Check = Approved |  | Go to stock check | Passed |  | SUK01XM-JOLP-SCHQ
| II | Stock check = Awaiting stock |  | Go to Back order Processing | Not Runned
| III | Stock check = Stock Available |  | Go to Payment capture | Failed | Stuck at "Payment capture" | SUK01XM-JOLP-SCHQ
| IV | Payment capture = rejected |  | Order cancel | Not Runned
| V | Payment capture = taken |  | Order dispatch (ERP) | Not Runned
| VI | Order dispatch = Canceled, rejected |  | Order cancel | Not Runned
| VII | Order dispatch = Accepted |  | Order Processing (EDI) | Not Runned
| VIII | Order Processing (EDI) = completed |  | Order Completed | Not Runned
Advance Test cases
5
| I | Bundle with one product out of stock |  | Order should start "Awaiting stock" flow | Not Runned
| II | Order with different delivery type |  | Order should behave normaly | Not Runned
| III | Order with voucher per order |  | Order should behave normaly | Not Runned
| IV | Order with voucher per product |  | Order should behave normaly | Passed |  | SUK01ZG-DHUT-PWVO / H771655
| V | Fraud check - uncheck "Same as shipping address" |  | Order should be approved manually | Passed
| VI | Select One payment option, go back and select other payment optiion |  | Order should behave normaly | Failed | Payment capture failed | SUK01SY-NTKE-PRBF
| VII |  |  |  | Not Runned
| VIII |  |  |  | Not Runned
DRAFT