## Plan
Sabre 2:0 Test Plan | [8 empty] | Nonimal Flow Testing |  |  |  | Operational Readiness Testing |  | Regression Testing
Categories | Subject | HLR Ref | HLR Page | HLD Ref | HDL Page | Owner | 2016-02-15 | 2016-02-22 | 2016-02-29 | 2016-03-07 | 2016-03-14 | 2016-03-21 | 2016-03-28 | 2016-04-04 | 2016-04-11 | Dependencies
Test Strategy | Overview of Test Method, Documents, etc. | n/a | n/a | n/a |  | David / Oz | 2016-03-28: Test Strategy review
Test cases Sign-Off | Test cases Review SignOff | n/a | n/a | n/a |  | David | 2016-02-29: David SignOff
Test cases Sign-Off | Test cases Review SignOff | n/a | n/a | n/a |  | BA | 2016-02-22: BA SignOff
Ecommerce Module | Website Customer Journey through to Payment and Fulfilment | 4.2 | 5 | tbc |  | Geani / Gary | 2016-02-15: Test Case; 2016-03-07: Nominal Testing; 2016-04-11: Regression Testing
| Home Page | 4.4 | 7 | tbc |  |  | 2016-02-15: Test Case; 2016-03-07: Nominal Testing
| Header, footer and menu navigation | 4.5 | 9 | tbc |  |  | 2016-02-15: Test Case; 2016-03-07: Nominal Testing
| Category, Product Listing and Filter Options | 4.6 | 10 | tbc |  |  | 2016-02-15: Test Case; 2016-03-07: Nominal Testing
| Product/Bundle Details | 4.7 | 17 | tbc |  |  | 2016-02-15: Test Case; 2016-03-07: Nominal Testing
| Mini Basket | 4.8 | 18 |  |  |  | 2016-02-15: Test Case; 2016-03-28: OR Testing
| Shopping Basket | 4.8 | 18 | tbc |  |  | 2016-02-15: Test Case; 2016-03-07: Nominal Testing
| Checkout | 4.9 | 21 | tbc |  |  | 2016-02-15: Test Case; 2016-03-07: Nominal Testing | Dummy/Tessting Credit Card/Bank account
| Payment Page | 4.1 | 23 | tbc |  |  | 2016-02-15: Test Case; 2016-03-07: Nominal Testing | Dummy/Tessting Credit Card/Bank account
| Order Confirmation Page | 4.11 | 25 | tbc |  |  | 2016-02-15: Test Case; 2016-03-07: Nominal Testing; 2016-03-28: OR Testing
| Static Content/Information Pages | 4.12 | 28 | tbc |  |  | 2016-02-15: Test Case; 2016-03-07: Nominal Testing
| FAQ | 4.13 | 28 | tbc |  |  | 2016-02-15: Test Case; 2016-03-07: Nominal Testing
| Site Map | 4.14 | 28 | tbc |  |  | 2016-02-15: Test Case; 2016-03-07: Nominal Testing
| Site Analytics Integration | 4.15 | 28 | tbc |  |  | 2016-02-15: Test Case; 2016-03-07: Nominal Testing
| Vouchers / Promotional Codes | 4.16 | 29 | tbc |  |  | 2016-02-15: Test Case; 2016-03-28: OR Testing
| Trade-Ins | 4.17 | 32 | tbc |  |  | 2016-02-15: Test Case; 2016-03-28: OR Testing
| Affiliate | 4.19 | 37 | tbc |  |  | 2016-02-15: Test Case; 2016-03-28: OR Testing
| Employee Partner Portal (EPP) | 4.19 | 37 | tbc |  |  | 2016-02-15: Test Case; 2016-03-28: OR Testing | EPP accounts
| Requirement Specifications: Generic | 5 | 42 | tbc |  |  | 2016-02-15: Test Case; 2016-03-07: Nominal Testing
SIT Testing | System integration | tbc | tbc | tbc |  | tbc | [9 empty] | Details tbc
PIM | UK Sales Channel | 5.1 | 5 | tbc |  | Geani / Alin | 2016-02-29: Test Case; 2016-03-21: Nominal Testing
| Product Catalogue | 5.2 | 5 | tbc |  |  | 2016-02-29: Test Case; 2016-03-21: Nominal Testing
| Prodcut Categories | 5.3 | 5 | tbc |  |  | 2016-02-29: Test Case; 2016-03-21: Nominal Testing
| Prodcut Properties | 5.4 | 5 | tbc |  |  | 2016-02-29: Test Case; 2016-03-21: Nominal Testing
| Product lifecycle | 5.5 | 5 | tbc |  |  | 2016-02-29: Test Case; 2016-03-21: Nominal Testing
| Search Prodcuts | 5.6 | 7 | tbc |  |  | 2016-02-29: Test Case; 2016-03-21: Nominal Testing
| Free of Charge Prodcuts | 5.7 | 7 | tbc |  |  | 2016-02-29: Test Case; 2016-03-21: Nominal Testing
| Prodcut Variants | 5.8 | 8 | tbc |  |  | 2016-02-29: Test Case; 2016-03-21: Nominal Testing
| Prodcut versions | 5.9 | 8 | tbc |  |  | 2016-02-29: Test Case; 2016-03-21: Nominal Testing
| Bundles | 5.1 | 9 | tbc |  |  | 2016-02-29: Test Case; 2016-03-21: Nominal Testing
| PDPs (Product description Page) | 5.11 | 10 | tbc |  |  | 2016-02-29: Test Case; 2016-03-21: Nominal Testing
| EPP - Partners and Staff Channel | 6.1 | 12 | tbc |  |  | 2016-02-29: Test Case; 2016-04-04: OR Testing
| Vouchers | 6.2 | 12 | tbc |  |  | 2016-02-29: Test Case; 2016-04-04: OR Testing
| Tagging Support | 6.3 | 13 | tbc |  |  | 2016-02-29: Test Case; 2016-04-04: OR Testing
| Ratings & Reviews | 6.4 | 13 | tbc |  |  | 2016-02-29: Test Case; 2016-04-04: OR Testing
| Product accessories | 6.5 | 13 | tbc |  |  | 2016-02-29: Test Case; 2016-04-04: OR Testing
| Scheduling | 6.6 | 15 | tbc |  |  | 2016-02-29: Test Case; 2016-04-04: OR Testing
| Cloning Products | 6.7 | 15 | tbc |  |  | 2016-02-29: Test Case; 2016-04-04: OR Testing
| Services | 6.8 | 16 | tbc |  |  | 2016-02-29: Test Case; 2016-04-04: OR Testing
| Trade-Ins |  |  | tbc |  |  | 2016-02-29: Test Case; 2016-04-04: OR Testing
| Audit | 6.9 | 16 | tbc |  |  | 2016-02-29: Test Case; 2016-04-04: OR Testing
| Requirement Specifications: Generic | 7 | 16 | tbc |  |  | 2016-02-29: Test Case; 2016-03-21: Nominal Testing
OMS / ESOM | Order Management Interfaces | 4 | 11 | tbc |  | Geani / Natalie | 2016-03-07: Test Case; 2016-03-21: Nominal Testing
| Customer Service Interface | 4.1 | 12 | tbc |  |  | 2016-03-07: Test Case; 2016-03-21: Nominal Testing
| User types (authorized, restricted view access, restricted actions) | 4.1.1 | 14 | tbc |  |  | 2016-03-07: Test Case; 2016-04-04: OR Testing
| Customer Service Administrator (Order limited actions - TBD) | 4.1.1 | 14 | tbc |  |  | 2016-03-07: Test Case; 2016-04-04: OR Testing
| Order Approval Access Customer Support Agent (restricted, access, actions, order approval) | 4.1.3 | 15 | tbc |  |  | 2016-03-07: Test Case; 2016-04-04: OR Testing
| System Administrator Interface | 4.1.1 | 14 | tbc |  |  | 2016-03-07: Test Case; 2016-04-04: OR Testing
| Create Regular order web site | 5.2.1, 9.5 | 17, 57 | tbc |  |  | 2016-03-07: Test Case; 2016-03-21: Nominal Testing
| Create regular order CS | 5.3, 9.6 | 17, | tbc |  |  | 2016-03-07: Test Case; 2016-04-04: OR Testing
| Create pre-order customer - web site | 9.7 |  | tbc |  |  | 2016-03-07: Test Case; 2016-04-04: OR Testing
| Create pre-order - CS | 5.2.2, 9.7 | 16, 61 | tbc |  |  | 2016-03-07: Test Case; 2016-04-04: OR Testing
| Create re-order - CS Agent | 5.2.4, 9.8 | 16, 61 | tbc |  |  | 2016-03-07: Test Case; 2016-04-04: OR Testing
| Create regular order 3rd party "sandbox interface" |  |  | tbc |  |  | 2016-03-07: Test Case; 2016-03-21: Nominal Testing
| Order Fields and Descriptions - same comprehensive list? | 5.5 | 23 | tbc |  |  | 2016-03-07: Test Case; 2016-03-21: Nominal Testing
| Order data Integrity check (required fields addressed, suntax, format, length, etc) | 6.2.1 |  | tbc |  |  | 2016-03-07: Test Case; 2016-03-21: Nominal Testing
| Bin check - ?soft allocation? | 10.6 | 64 | tbc |  |  | 2016-03-07: Test Case; 2016-03-21: Nominal Testing
| Payment Gateway Validation | 6 | 35 | tbc |  |  | 2016-03-07: Test Case; 2016-03-21: Nominal Testing
| Credit Card – WorldPay | 6.2.4 | 40 | tbc |  |  | 2016-03-07: Test Case; 2016-03-21: Nominal Testing
| PayPal | 6.2.5 | 40 | tbc |  |  | 2016-03-07: Test Case; 2016-03-21: Nominal Testing
| Bank Transfer | 6.2.6 | 40 | tbc |  |  | 2016-03-07: Test Case; 2016-04-04: OR Testing
| Risk Guardian Fraud Check | 7, 7.2.4 | 42 | tbc |  |  | 2016-03-07: Test Case; 2016-03-21: Nominal Testing
| Internal Fraud Check | 7, 7.2.5 | 42 | tbc |  |  | 2016-03-07: Test Case; 2016-03-21: Nominal Testing
| Order Status Change (automated) | 9 | 49 | tbc |  |  | 2016-03-07: Test Case; 2016-03-21: Nominal Testing
| Change Order Status (manual - CS Agent) | 9 | 49 | tbc |  |  | 2016-03-07: Test Case; 2016-04-04: OR Testing
| Customer change an order (add, subtract quantity, add item) before checkout | 9.9 | 61 | tbc |  |  | 2016-03-07: Test Case; 2016-04-04: OR Testing
| CS Agent change an order (add, subtract quantity, add item - CS Agent - pre-approved status) | 9.9 | 61 | tbc |  |  | 2016-03-07: Test Case; 2016-04-04: OR Testing
| Order Approval – Order Manager | 9.3.2 | 54 | tbc |  |  | 2016-03-07: Test Case; 2016-03-21: Nominal Testing
| Customer cancel an order - pre-approved status | 9.9 | 61 | tbc |  |  | 2016-03-07: Test Case; 2016-04-04: OR Testing
| CS - Cancel an order - pre-approved status | 9.9 | 61 | tbc |  |  | 2016-03-07: Test Case; 2016-04-04: OR Testing
| Customer cancel a line item on order - pre-approved status |  | 61 | tbc |  |  | 2016-03-07: Test Case; 2016-04-04: OR Testing
| CS cancel an order - pre-approved status | 9.9 | 61 | tbc |  |  | 2016-03-07: Test Case; 2016-04-04: OR Testing
| Send order to Dispatch | 9.10. | 63 | tbc |  |  | 2016-03-07: Test Case; 2016-03-21: Nominal Testing
| Interface to ESOM |  |  | tbc |  |  | 2016-03-07: Test Case; 2016-03-21: Nominal Testing
| Returned Merchandise Authorizations (RMA) | 12 | 68 | tbc |  |  | 2016-03-07: Test Case; 2016-04-04: OR Testing
| Re-order validation with original order, financial reconciliation interface | 12 | 68 | tbc |  |  | 2016-03-07: Test Case; 2016-04-04: OR Testing
| Refund validation with original order, financial reconciliation interface | 12 | 68 | tbc |  |  | 2016-03-07: Test Case; 2016-04-04: OR Testing
| Trade-Ins | 13 | 69 | tbc |  |  | 2016-03-07: Test Case; 2016-04-04: OR Testing
| Order History (search by email, customer #, etc.) | 10 | 63 | tbc |  |  | 2016-03-07: Test Case; 2016-04-04: OR Testing
| Customer blacklisting & whitelisting | 10.5 | 64 | tbc |  |  | 2016-03-07: Test Case; 2016-04-04: OR Testing
| Reporting | 11 | 64 | tbc |  |  | 2016-03-07: Test Case; 2016-04-04: OR Testing
| Preset Email Samples | 14 | 74 | tbc |  |  | 2016-03-07: Test Case; 2016-04-04: OR Testing
| Administration System Configuration | 15 | 74 | tbc |  |  | 2016-03-07: Test Case; 2016-04-04: OR Testing
Sage X3 (ERP) |  | tbc | tbc | tbc |  | tbc
Sabre 1 (Exp) Bugs & Fixes | Ensure they haven't been duplicated | tbc | tbc | tbc |  | Geani | 2016-03-21: Test Case; 2016-03-28: Nominal Testing; 2016-04-04: OR Testing
Change Requests |  | tbc | tbc | tbc |  | Geani | 2016-03-21: Test Case; 2016-03-28: Nominal Testing; 2016-04-04: OR Testing

## Questions
Testing Questions
1 | When is estimed that I will receive HLD documents?
2 | I have a list of HLD requirements but there are some requirements that I can’t find them on HLR document
3 | When is estimated that I will receive PIM/OMS and the other modules HLR/HLD documents?
4 | Need more details in order to make complete test cases for Payment page. Or a Dummy/Tessting Credit Card/Bank account
5 | How does Trade-In system tracking works? Because after I completed a trade in journey, I can't see any trace of the Trade In journey.