## HLP New
VFT Interim Project: Go-live Countdown & Deployment Plan (w/c) Revised 13th Jan
Owner | Activity | Status | 2016-01-09 | 2016-01-10 | 2016-01-11 | 2016-01-12 | 2016-01-13 | 2016-01-14 | 2016-01-15 | 2016-01-16 | 2016-01-17 | 2016-01-18 | 2016-01-19 | 2016-01-20 | 2016-01-21 | 2016-01-22 | 2016-01-23 | 2016-01-24 | 2016-01-25 | 2016-01-26 | 2016-01-27 | 2016-01-28 | 2016-01-29 | 2016-01-30 | 2016-01-31 | 2016-02-01 | 2016-02-02 | 2016-02-03 | 2016-02-04 | 2016-02-05 | 2016-02-06 | 2016-02-07 | 2016-02-08 | 2016-02-09 | 2016-02-10 | 2016-02-11 | 2016-02-12 | Post Go-live
PJM | Device Details | Implementaion | bar: 2016-01-11 to 2016-01-15; 2016-01-18 to 2016-01-20
PJM | Test | bar: 2016-01-21
VFT | Device Details Design Approval | Signed off | bar: 2016-01-13
VFT | Device Details Functional Test | bar: 2016-01-22
PJM | Home Page (incl. banner) | Implementation | bar: 2016-01-13 to 2016-01-14
PJM | Test | bar: 2016-01-15
VFT | Home Page Design Approval | Signed off | bar: 2016-01-13
VFT | Home Page Functional Test | bar: 2016-01-18
PJM | Device Listing | Implementaion | bar: 2016-01-11 to 2016-01-15; 2016-01-18 to 2016-01-20
PJM | Test | bar: 2016-01-21
VFT | Device Listing Design Approval | Signed off | bar: 2016-01-12
VFT | Device Listing Functional Test | bar: 2016-01-22
PJM | Tariff Listing | Design | bar: 2016-01-11 to 2016-01-15; 2016-01-18 to 2016-01-22; 2016-01-25 to 2016-01-27
PJM | Test | bar: 2016-01-28
VFT | Tariff Listing Design Approval | bar: 2016-01-15
VFT | Tariff Listing Functional Test | bar: 2016-01-29
PJM | Tariff Details | Design | bar: 2016-01-11 to 2016-01-15; 2016-01-18 to 2016-01-22; 2016-01-25 to 2016-01-27
PJM | Test | bar: 2016-01-28
VFT | Tariff Details Design Approval | bar: 2016-01-15
VFT | Tariff Details Functional Test | bar: 2016-01-29
PJM | Header & Footer | bar: 2016-01-18 to 2016-01-22; 2016-01-25 to 2016-01-27
PJM | Test | bar: 2016-01-28
VFT | Header & Footer Code Submission | Awaiting Code | bar: 2016-01-15
VFT | Header & Footer Functional Test | bar: 2016-01-29
PJM | Pagination
PJM | Tagging | bar: 2016-01-15; 2016-01-18 to 2016-01-20
PJM | Test | bar: 2016-01-21
VFT | Tagging Information | Awaiting Impl. Guide & Log-in | bar: 2016-01-14
VFT | Tagging Functional Test | bar: 2016-01-22
PJM | Load testing | bar: 2016-01-28
VFT | DNS Workshops & Confirmation | bar: 2016-01-18 to 2016-01-22; 2016-01-25 to 2016-01-29
VFT | Device, tariff, accessory, digital product data Loading | bar: 2016-02-01 to 2016-02-05
VFT | SIT & Security & Soasta testing | bar: 2016-02-01 to 2016-02-05
VFT | eShop sign-off | bar: 2016-02-08 to 2016-02-09
PJM | Deployment & PVT | bar: 2016-02-10 to 2016-02-11