## Requirements TraceabilityMatrix
| Vodafone Turkey Priorities | Vodafone Turkey - Interim and Regression Requirements Testing Status | TBA mm/dd/yyyy | TBA mm/dd/yyyy
Interim Phase Testing (Progression): |  | Progression Status
Setting up new accessible to purchase devices functionality (CMS) | High |  | Passed | Not run
Adding additional graphics functionality for phones that can be purchased (CMS) - rosette | High |  | Passed | Not run
Visible additional graphics functionality for phones that can be purchased (eShop) - rosette | High |  | Passed | Not run
Buy buttons (CTA) visible on front end store (eShop) | High |  | Passed | Not run
Setting up new devices properties - SKU code and tariff identifier (CMS) | High |  | Passed | Not run
New Filters and sorting mechanisms for devices (eShop) | High |  | Passed | Not run
Adding New device properties - color and memory size properties (CMS) | High |  | Passed | Not run
Adding ne property - top 5 devices (CMS) | High |  | Passed | Not run
Refferral functionality - any ICMP code to be passed to Vodafone My Account (eShop) | High |  | Passed | Not run
Out of stock functionality (CMS & eShop) | High |  | Passed | Not run
Responsive design (eShop) | High |  | Not run | Not run
Top phones functionality (CMS & eShop) | High |  | Passed | Not run
Remove tariff lead journeys (eShop) | High |  | Passed | Not run
Pre-sales to sales functionality (CMS & eShop) | High |  | Not run | Not run
New dedicated areas - Hearlines, techincal information (CMS & eShop) | High |  | Not run | Not run
Reporting (Omniture, Tealium) (eShop) | High |  | Not run | Not run
Functional Regression Testing
Functional Test purchase flows - Phone -> Plan - Check-out (see TestFlows Sheet) | High |  | Passed | Not run
Test Postpaid Tariff Preferences Filters: (NB:Buy now button on plans page will be disabled) | High |  | Passed | Not run
Test Postpaid Tariff Featured Filter: Popular | High |  | Passed | Not run
Test Postpaid Tariff Featured Filter: New releases | High |  | Passed | Not run
Test Postpaid Tariff Contract your choice Filter: Advantages of a 12-month contract Postpaid | High |  | Not run | Not run
Test Postpaid Tariff Contract your choice Filter: Device contracts Postpaid | High |  | Not run | Not run
Device contract period Filter: | High |  | Not run | Not run
Test 6 months option filter | High |  | Not run | Not run
Test 12 months option filter | High |  | Not run | Not run
Test 18 months option filter | High |  | Not run | Not run
Test 24 months option filter | High |  | Not run | Not run
Test Postpaid Tariff Contract your choice Filter: I prefer no contract | High |  | Not run | Not run
Test Postpaid Tariff Contract your choice Filter: How do you get your timetable? | High |  | Not run | Not run
Test Postpaid Tariff Just get me to talk Tariff Filter | High |  | Not run | Not run
Test Postpaid Tariff Speech + SMS and / or Internet to get together | High |  | Not run | Not run
Test Postpaid Tariff Do not pack out | High |  | Not run | Not run
Test Postpaid Tariff Whether talking with Vodafone'lu | High |  | Not run | Not run
Test Postpaid Our special offer Sort Option: I am under 26 years of age | High |  | Not run | Not run
Test Postpaid Our special offer Sort Option: Public employee | High |  | Not run | Not run
Test Postpaid Our special offer Sort Option: Red would like to benefit from the privileges | High |  | Not run | Not run
Test Postpaid Our special offer Sort Option: I want to come to Vodafone | High |  | Not run | Not run
Test Postpaid Our special offer Sort Option: I'm doing my own thing | High |  | Not run | Not run
Test Postpaid Our special offer Sort Option: I am a farmer | High |  | Not run | Not run
Test Postpaid Our special offer Sort Option: I'm disabled | High |  | Not run | Not run
Test Postpaid Our special offer Sort Option: I want to switch from prepaid to postpaid | High |  | Not run | Not run
Test Postpaid Our special offer Sort Option: Other | High |  | Not run | Not run
Test Postpaid Your monthly payment 0-25 TL Sort Option | High |  | Not run | Not run
Test Postpaid Your monthly payment 26-40 TL Sort Option | High |  | Not run | Not run
Test Postpaid Your monthly payment 41-60 TL Sort Option | High |  | Not run | Not run
Test Postpaid Your monthly payment 61 - 90TL Sort Option | High |  | Not run | Not run
Test Postpaid Your monthly payment 91TL and above Sort Option | High |  | Not run | Not run
Test Postpaid Show inactive plans Sort Option | High |  | Not run | Not run
Test Postpaid Show All link | High |  | Not run | Not run
Test Postpaid Monthly Fee Sort Tab | High |  | Not run | Not run
Test Postpaid Inclusive minutes Sort Menu Tab | High |  | Not run | Not run
Test Postpaid Inclusive SMSs Sort Menu Tab | High |  | Not run | Not run
Test Postpaid Inclusive Internet Sort Menu Tab | High |  | Not run | Not run
Test Postpaid Contract Duration | High |  | Not run | Not run
Test Tariff Preferences Filter: Prepaid (NB:Buy now button on plans page will be disabled) | High |  | Passed | Not run
Test Prepaid Test I got my money's worth from the beginning what I know Sort Option("How do you get your timetable?" sort section) | High |  | Not run | Not run
Test Prepaid Test I do my load, I'll just spend time talking Sort Option("How do you get your timetable?" sort section) | High |  | Not run | Not run
Test Prepaid Test You get to talk to all directions Tariff enough Sort Option("How do you get your timetable?" sort section) | High |  | Not run | Not run
Test Prepaid Test Speech + SMS + Internet get together Sort Option("How do you get your timetable?" sort section) | High |  | Not run | Not run
Test Prepaid Test I am under 26 years of age Sort Option ("Our special offer" sorting section) | High |  | Not run | Not run
Test Prepaid Test I think New Line Pickup Sort Option ("Our special offer" sorting section) | High |  | Not run | Not run
Test Prepaid Test I want to move my number to Vodafone Sort Option ("Our special offer" sorting section) | High |  | Not run | Not run
Test Prepaid Test I'm doing my own thing Sort Option ("Our special offer" sorting section) | High |  | Not run | Not run
Test form fileds - personal details & contact information | High |  | Not run | Not run
Test Sing up for Email | High |  | Not run | Not run
Non-functional / Cross browser testing:
Landing page - Home page | High |  | Passed | Not run
Landing page - Device Detail Page | High |  | Passed | Not run
Landing page - Plan Detail Page | High |  | Not run | Not run
Landing page - Phone Listing Page (PAYM) | High |  | Not run | Not run
Landing page - Plans Listing Page (PAYG) | High |  | Not run | Not run
Landing page - Plan Listing Page (PAYM) | High |  | Not run | Not run
Landing page - Plans Listing Page (PAYG) | High |  | Not run | Not run
New Media Integration (Facebook, Twitter, etc.) | High |  | Not run | Not run
Non-successful scenarios
TBA |  |  | N/A
TBA
TBA
TBA
TBA
TBA
TBA
TBA
TBA
TBA

## Eshop Portal Use Cases
Vodafone Turkey: Online Scope - Interim & Regression Testing
Test Suite
Test Case: New Buying process - set up phones that can be purchased (CMS) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
NB: Please note that this might change are some properties of the phone and such features as SKU might become mandatory in order to publish device as available. | Admin accesses CMS log in page. | Admin prompted with user and password. |  | Passed
| Admin enters valid user and password. | Admin redirected to admin panels. |  | Passed
| Admin accesses Online Shop area and selects to see products/phones admin panel | Admin redirected to phones area and sees all phones available on CMS. |  | Passed
| Admin selects one phone and chooses to modify it. It clicks on checkbox to make it a phone available for purchase. Then completes the actions and publishes the new phone. | Admin prompted by Complete message and device should now be visible on eShop. |  | Passed
Test Case: New Buying process - set up phones that can be purchased (CMS) - rosetta feature | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
NB: Please note that this might change are some properties of the phone and such features as SKU might become mandatory in order to publish device as available. | Admin accesses CMS log in page. | Admin prompted with user and password. |  | Passed
| Admin enters valid user and password. | Admin redirected to admin panels. |  | Passed
| Admin accesses Online Shop area and selects to see products/phones admin panel | Admin redirected to phones area and sees all phones available on CMS. |  | Passed
| Admin selects one phone and chooses to modify it. It clicks on checkbox to make it a phone available for purchase. | Admin should be able to go to insert the next feature for this psecific phone. |  | Passed
| In the newly created upload photo functionality for the rosetta admin can upload the new banner that will go together with phone graphics. Then completes the actions and publishes the new phone. | Admin prompted by Complete message and device should now be visible on eShop. Also rosetta should be visible. |  | Passed
Test Case: Set up phones that can be purchased (CMS) - color | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
NB: Please note that this might change are some properties of the phone and such features as SKU might become mandatory in order to publish device as available. | Admin accesses CMS log in page. | Admin prompted with user and password. |  | Passed
| Admin enters valid user and password. | Admin redirected to admin panels. |  | Passed
| Admin accesses Online Shop area and selects to see products/phones admin panel | Admin redirected to phones area and sees all phones available on CMS. |  | Passed
| Admin selects one phone and chooses to modify it by adding new color to the device. Then completes the actions and publishes the new phone. | Admin prompted by Complete message and device should now be visible on eShop. New color device should be visible on front end. |  | Passed
Test Case: Set up phones that can be purchased (CMS) - storage size | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
NB: Please note that this might change are some properties of the phone and such features as SKU might become mandatory in order to publish device as available. | Admin accesses CMS log in page. | Admin prompted with user and password. |  | Passed
| Admin enters valid user and password. | Admin redirected to admin panels. |  | Passed
| Admin accesses Online Shop area and selects to see products/phones admin panel | Admin redirected to phones area and sees all phones available on CMS. |  | Passed
| Admin selects one phone and chooses to modify it by adding new storage size to the device. Then completes the actions and publishes the new phone. | Admin prompted by Complete message and device should now be visible on eShop. New storage radio button for device should be visible on front end. |  | Passed
Test Case: Set up phones that can be purchased (CMS) - storage size | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
NB: Please note that this might change are some properties of the phone and such features as SKU might become mandatory in order to publish device as available. | Admin accesses CMS log in page. | Admin prompted with user and password. |  | Passed
| Admin enters valid user and password. | Admin redirected to admin panels. |  | Passed
| Admin accesses Online Shop area and selects to see products/phones admin panel | Admin redirected to phones area and sees all phones available on CMS. |  | Passed
| Admin selects one phone and chooses to modify it by adding new storage size to the device. Then completes the actions and publishes the new phone. | Admin prompted by Complete message and device should now be visible on eShop. New storage radio button for device should be visible on front end. |  | Passed
Test Case: Set up phones (CMS) - top 5 property | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
| Admin accesses CMS log in page. | Admin prompted with user and password. |  | Passed
| Admin enters valid user and password. | Admin redirected to admin panels. |  | Passed
| Admin accesses Online Shop area and selects to see products/phones admin panel | Admin redirected to phones area and sees all phones available on CMS. |  | Passed
| Admin selects one phone and chooses to modify it by adding it to the top 5 devices by activating property chech box. Then completes the actions and publishes the new phone. | Admin prompted by Complete message and device should now be visible on eShop. The new device should be amongst top five devices displayed on phones page. |  | Passed
Test Case: New Buying process - phones that can be purchased through Vodafone My Account | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
| Customer reaches view all phones page. | Phones that were set up for purchase in CMS should have Buy Now buttons. Verify layout ont broken. Verify layout is responsive. Color versions should be visible to each phone that can be purchased in more than one color. |  | Passed
| User clicks on one phone that can be purchased. | User is redirected to phone details page. Verify layout not broken. Verify layout is responsive. |  | Passed
| Customer selects one color variation and checks radio button for one memory size option, and clicks on Buy button. | Customer is redirected to Vodafone My Account page. Verify that SKU and tarrif identifier are passed to Vodafone. |  | Passed
Test Case: New Buying process - phones that can be purchased through Vodafone My Account - ICMP use case | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
| Customer reaches view all phones page after accessing an ICMP referral link | Phones that were set up for purchase in CMS should have Buy Now buttons. Verify layout not broken. Verify layout is responsive. Color versions should be visible to each phone that can be purchased in more than one color. Verify ICMP code is captured and stored in browser. |  | Passed
| User clicks on one phone that can be purchased. | User is redirected to phone details page. Verify layout not broken. Verify layout is responsive. |  | Passed
| Customer selects one color variation and checks radio button for one memory size option, and clicks on Buy button. | Customer is redirected to Vodafone My Account page. Verify that SKU, tarrif identifier, and ICMP code are passed to Vodafone. |  | Passed
| TBA | TBA |  | To Be filled with Pass, Fail, Not Run or In Progress
| TBA | TBA |  | To Be filled with Pass, Fail, Not Run or In Progress
| TBA | TBA |  | To Be filled with Pass, Fail, Not Run or In Progress
Test Case: New phones filter - Handset type | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
| Customer reaches view all phones page. | Phones are visible no filter is set. Verify layout is responsive. Color versions should be visible to each phone that can be purchased in more than one color. |  | Passed
| Customer clicks on drop down Phone Filters and selects 4G ready feature under Handset type list, and clicks Apply filters button. | Only phones with 4G should be visible. Visible items number should be the same as shown next to filter option. |  | Passed
| Customer clicks on drop down Phone Filters and deselects 4G and selects Touchscreen filter check box, and clicks Apply filters button. | Only phones with touchscreen should be visible. Visible items number should be the same as shown next to filter option. |  | Passed
| Customer clicks on drop down goes and clicks Clear filters buttons. | All phones are now visible as no filter is active. |  | Passed
Test Case: New phones filter - Price | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
| Customer reaches view all phones page. | Phones are visible no filter is set. Verify layout is responsive. Color versions should be visible to each phone that can be purchased in more than one color. |  | Passed
| Customer clicks on drop down Phone Filters and selects Up to 20 turkish lira a month, and clicks Apply filters button. | Only phones up to that price should be visible. Visible items number should be the same as shown next to filter option. |  | Passed
| Customer clicks on drop down Phone Filters and deselects up to 20 turkish lire and selects Up to 40 a month filter check box, and clicks Apply filters button. | List with phones visible expands up to the new filter price Visible items number should be the same as shown next to filter option. |  | Passed
| Customer clicks on drop down goes and clicks Clear filters buttons. | All phones are now visible as no filter is active. |  | Passed
| TBA | TBA |  | To Be filled with Pass, Fail, Not Run or In Progress
| TBA | TBA |  | To Be filled with Pass, Fail, Not Run or In Progress
Test Case: New phones filter - other filters | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
| Customer reaches view all phones page. | Phones are visible no filter is set. Verify layout is responsive. Color versions should be visible to each phone that can be purchased in more than one color. |  | Passed
| Test all other filters using actions logic previously used on Handset type and Price filters. | Only phones that are matching that filter should be visible. Device items number should be the same as shown next to filter option. |  | Passed
Test Case: Buying process - Plan PAYG + Phone (Regression) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
| See that Plan first purchase journey in no longer valid. | See that this purchase journey in no longer valid |  | N/A
Test Case: Buying process - Plan PAYG + Phone - incomplete purchase (Regression) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
| See that Plan first purchase journey in no longer valid. | See that this purchase journey in no longer valid |  | N/A
Test Case: Buying process - Plan PAYM + Phone (Regression) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
| See that Plan first purchase journey in no longer valid. | See that this purchase journey in no longer valid |  | N/A
Test Case: Buying process - Plan PAYM + Phone - incomplete purchase (Regression) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
| See that Plan first purchase journey in no longer valid. | See that this purchase journey in no longer valid |  | N/A
Test Case: Buying process - Plan PAYG + Phone (Quickview select button) (Regression) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
| See that Plan first purchase journey in no longer valid. | See that this purchase journey in no longer valid |  | N/A
Test Case: Buying process - Plan PAYG + Phone (Quickview select button) - incomplete purchase (Regression) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
| See that Plan first purchase journey in no longer valid. | See that this purchase journey in no longer valid |  | N/A
Test Case: Buying process - Plan PAYM + Phone (Quickview select button) (Regression) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
| See that Plan first purchase journey in no longer valid. | See that this purchase journey in no longer valid |  | N/A
Test Case: Buying process - Plan PAYM + Phone (Quickview select button) - incomplete purchase (Regression) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
| See that Plan first purchase journey in no longer valid. | See that this purchase journey in no longer valid |  | N/A
Test Case: Buying process - Phone + Plan PAYG (Regression) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
| user enters site, on home page, and clicks on Phones page link. | user is prompted with all Device Catalog offers. Page layout and functionality are checked before test goes further. |  | Passed
| user selects one phone offer | user is taken to all plans - pay as you go page. age layout and functionality are checked before test goes further. |  | Passed
| user selects one plan offer | user reaches basket with all purchased goods reflecting his previous actions. Page layout and functionality are checked before test goes further. |  | Passed
| user checks basket products, clicks button and moves to complete the purchase | user is taken to personal and contact details page. Page layout and functionality are checked before test goes further. |  | N/A
| user fills in all mandatory fields and clicks to place order | user is prompted with purchase successful message. Page layout and functionality are checked before test ends. Check also if Order Acknowledgement email is received. |  | N/A
Test Case: Buying process - Phone + Plan PAYM (Regression) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
| user enters site, on home page, and clicks on Phones page link. | user is prompted with all phones offers. Page layout and functionality are checked before test goes further. |  | Passed
| user selects one phone offer | user is taken to all pay monthly plans page. age layout and functionality are checked before test goes further. |  | Passed
| user selects one plan offer | user reaches basket with all purchased goods reflecting his previous actions. Page layout and functionality are checked before test goes further. |  | Passed
| user checks basket products, clicks button and moves to complete the purchase | user is taken to personal and contact details page. Page layout and functionality are checked before test goes further. |  | N/A
| user fills in all mandatory fields and clicks to place order | user is prompted with purchase successful message. Page layout and functionality are checked before test ends. Check also if Order Acknowledgement email is received. |  | N/A
Test Case: Buying process - Phone + Plan PAYG - incomplete purchase (Regression) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
| user enters site, on home page, and clicks on Phones page link. | user is prompted with all Device Catalog offers. Page layout and functionality are checked before test goes further. |  | Passed
| user selects one phone offer | user is taken to all plans - pay as you go page. age layout and functionality are checked before test goes further. |  | Passed
| user selects one plan offer | user reaches basket with all purchased goods reflecting his previous actions. Page layout and functionality are checked before test goes further. |  | Passed
| user checks basket products, clicks button and moves to complete the purchase | user is taken to personal and contact details page. Page layout and functionality are checked before test goes further. |  | N/A
| user clicks button and removes all purchased goods | Basket pages reloads with each removed product action and page reflects that action by not showing removed goods and their prices. Page layout and functionality are checked before test ends. |  | N/A
Test Case: Buying process - Phone + Plan PAYM - incomplete purchase (Regression) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
| user enters site, on home page, and clicks on Phones page link. | user is prompted with all phones offers. Page layout and functionality are checked before test goes further. |  | Passed
| user selects one phone offer | user is taken to all pay monthly plans page. age layout and functionality are checked before test goes further. |  | Passed
| user selects one plan offer | user reaches basket with all purchased goods reflecting his previous actions. Page layout and functionality are checked before test goes further. |  | Passed
| user checks basket products, clicks button and moves to complete the purchase | user is taken to personal and contact details page. Page layout and functionality are checked before test goes further. |  | N/A
| user clicks button and removes all purchased goods | Basket pages reloads with each removed product action and page reflects that action by not showing removed goods and their prices. Page layout and functionality are checked before test ends. |  | N/A
Test Case: Buying process - Phone + PAYM Plan (select both on phone details page) - incomplete purchase (Regression) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
| user enters site, on home page, and clicks on Phones page link. | user is prompted with all phones offers. Page layout and functionality are checked before test goes further. |  | Passed
| user clicks on one phone Full details link | user is taken phone details page. Page layout and functionality are checked before test goes further. |  | Passed
| user clicks on Chose a plan tab selects one PAYM plan offer | user reaches basket with all purchased goods reflecting his previous actions. Page layout and functionality are checked before test goes further. |  | Passed
| user checks basket products, clicks button and moves to complete the purchase | user is taken to personal and contact details page. Page layout and functionality are checked before test goes further. |  | N/A
| user clicks button and removes all purchased goods | Basket pages reloads with each removed product action and page reflects that action by not showing removed goods and their prices. Page layout and functionality are checked before test ends. |  | N/A
Test Case: Buying process - Phone + PAYG Plan (select both on phone details page) - incomplete purchase (Regression) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
| user enters site, on home page, and clicks on Phones page link. | user is prompted with all phones offers. Page layout and functionality are checked before test goes further. |  | Passed
| user clicks on one phone Full details link | user is taken phone details page. Page layout and functionality are checked before test goes further. |  | Passed
| user clicks on Chose a plan tab selects one PAYG plan offer | user reaches basket with all purchased goods reflecting his previous actions. Page layout and functionality are checked before test goes further. |  | Passed
| user checks basket products, clicks button and moves to complete the purchase | user is taken to personal and contact details page. Page layout and functionality are checked before test goes further. |  | N/A
| user clicks button and removes all purchased goods | Basket pages reloads with each removed product action and page reflects that action by not showing removed goods and their prices. Page layout and functionality are checked before test ends. |  | N/A
Test Case: Buying process - Phone + PAYM Plan (select both on phone details page) (Regression) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
| user enters site, on home page, and clicks on Phones page link. | user is prompted with all phones offers. Page layout and functionality are checked before test goes further. |  | Passed
| user clicks on one phone Full details link | user is taken phone details page. Page layout and functionality are checked before test goes further. |  | Passed
| user clicks on Chose a plan tab selects one PAYM plan offer | user reaches basket with all purchased goods reflecting his previous actions. Page layout and functionality are checked before test goes further. |  | Passed
| user checks basket products, clicks button and moves to complete the purchase | user is taken to personal and contact details page. Page layout and functionality are checked before test goes further. |  | N/A
| user fills in all mandatory fields and clicks to place order | user is prompted with purchase successful message. Page layout and functionality are checked before test ends. Check also if Order Acknowledgement email is received. |  | N/A
Test Case: Buying process - Phone + PAYG Plan (select both on phone details page) (Regression) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
| user enters site, on home page, and clicks on Phones page link. | user is prompted with all phones offers. Page layout and functionality are checked before test goes further. |  | Passed
| user clicks on one phone Full details link | user is taken phone details page. Page layout and functionality are checked before test goes further. |  | Passed
| user clicks on Chose a plan tab selects one PAYG plan offer | user reaches basket with all purchased goods reflecting his previous actions. Page layout and functionality are checked before test goes further. |  | Passed
| user checks basket products, clicks button and moves to complete the purchase | user is taken to personal and contact details page. Page layout and functionality are checked before test goes further. |  | N/A
| user fills in all mandatory fields and clicks to place order | user is prompted with purchase successful message. Page layout and functionality are checked before test ends. Check also if Order Acknowledgement email is received. |  | N/A
Test Case: Test all forms fileds on Personal and Contact details page (Regression) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
| TBA | TBA |  | To Be filled with Pass, Fail, Not Run or In Progress
| TBA | TBA |  | To Be filled with Pass, Fail, Not Run or In Progress
| TBA | TBA |  | To Be filled with Pass, Fail, Not Run or In Progress
| TBA | TBA |  | To Be filled with Pass, Fail, Not Run or In Progress
| TBA | TBA |  | To Be filled with Pass, Fail, Not Run or In Progress
| TBA | TBA |  | To Be filled with Pass, Fail, Not Run or In Progress
| TBA | TBA |  | To Be filled with Pass, Fail, Not Run or In Progress
Test Case: PAYM Plans Seach Filters (Regression) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
| user enters site, on home page and clicks on Pay Monthly plans page link. | user is prompted with all plans offers. Page layout and functionality are checked before test goes further. |  | Passed
| user clicks and tests functionality on all search filters. | plans are dispalyed in accordance with filter selected/clicked. Page layout and functionality are checked before test goes further. |  | Passed
Test Case: PAYG Plans Search Filters (Regression) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
| user enters site, on home page and clicks on Pay As You Go plans page link. | user is prompted with all plans offers. Page layout and functionality are checked before test goes further. |  | Passed
| user clicks and tests functionality on all search filters. | plans are dispalyed in accordance with filter selected/clicked. Page layout and functionality are checked before test goes further. |  | Passed
Test Case: Phones Search filters (Regression) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
| user enters site, on home page and clicks on All Phones page link. | user is prompted with all phones offers. Page layout and functionality are checked before test goes further. |  | Passed
| user clicks and tests functionality on all search filters. | plans are dispalyed in accordance with filter selected/clicked. Page layout and functionality are checked before test goes further. |  | Passed
Test Case: Test plan details pages (Regression) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
| test layout and content |  |  | Failed |  | Bug 9
Test Case: Test phone details pages (Regression) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
| test layout and content |  |  | Failed |  | bug 27, 28
Test Case: Test Menu and Footer links and landing pages (Regression) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
| test layout and content |  |  | Passed
Test Case: Test New Media Integration (Facebook buttons) (Regression) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
Test Case: Test sign up for email functionality (Regression) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
Test Case: Buying process (Regression) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
Test Case: Buying process (Regression) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
Test Case: Buying process (Regression) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
Test Case: Buying process (Regression) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
Test Case: Buying process (Regression) | Test Steps | Operation to be used
Test Step | Test Detail | Expected Result | Actual Result | Status | Time Taken | Comment
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress
To Be filled with Pass, Fail, Not Run or In Progress

## Errors
BugID | Date and Time Found | Assigned TO | Date and Time Fixed | Flow | Test Comments | Test Fixed Comments | Legend
1 | 2015-12-06 |  | NAB | Press shopping cart icon; Create an phone->plan->basket flow | Shopping cart can't be accesed from any flow methods | Not a bug. Shopping cart flow not aplicable. |  | =NAB
2 | 2015-12-06 |  | NAB | Reach Phone details page | Pressing "Buy Now" or "Fiyatlari Gor" redirects to vodafone live page, braking the "Buy Flow" | Not a bug. |  | =In progress
3 | 2015-12-06 |  | 2015-12-07 | home page -> press Cihazlar button-> press Tariff listing link | Tariff listing page not working | Trafiff listing page working |  | =Fixed
4 | 2015-12-06 |  | NAB | Press the vodafone logo on stage page | Pressing the Vodafone logo on stage page will redirect to live page | Not a bug. |  | =Open Bug
5 | 2015-12-06 |  | NAB | Reach Phone details page | Phone images are not shown | Not a bug. It is CMS amanged.
6 | 2015-12-06 |  |  | Reach Phone details page | Some text are in english some are in TK
7 | 2015-12-06 |  | NAB | Reach Phone details page | "Neden vodafone.com.tr'den Almalym " dropdown is emply Screen shot 1 | Not a bug. Parametters not set in CMS. Setting CMS parametters will fix this issue.
8 | 2015-12-06 |  | NAB | Reach Phone details page - Ne Kadar Oderim? Drop down | "Tariffe Grupu" - Selecting any option except "Tumu" will remove every tariffe option Screenshot 2 and 3 | Not a bug. It is CMS amanged.
9 | 2015-12-06 |  | Page in progress | Reach plan detail page example : http://vodafonetr-stage.pjmedia.co.uk/priceplans/red-small1/OfferingID/B14D82A0-4392-11E3-A65F0022195BA3CC | Lots of issues on plan detail page Screenshot 4 | Page in progress
10 | 2015-12-06 |  | NAB | Reach Phone details page | "Compatible devices…" dropdown is empty Screenshot 5 | Not a bug. Parametters not set in CMS. Setting CMS parametters will fix this issue.
11 | 2015-12-06 |  | NAB | Reach Phone details page | All phones have only one color available "Purple" Screenshot 6 | Not a bug. Parametters not set in CMS. Setting CMS parametters will fix this issue.
12 | 2015-12-06 |  | NAB | Reach all phone filter | Additional filters "Stock" and "Staff Picked" display all phones | Not a bug. Parametters not set in CMS. Setting CMS parametters will fix this issue.
13 | 2015-12-06 |  | NAB | - Reach all phone filter - Select two different but related filters | Combining filters don't display all phones. For example selecting only android will display around 20 samsung phones. If selecting android and samsung filters will display only 7 phones | Not a bug. It is CMS amanged.
14 | 2015-12-06 |  | NAB | Reach all phone page | Tablet is present on phone page. Vodafone Smart Tab 6 | Not a bug. It is CMS amanged.
15 | 2015-12-06 |  | NAB | Reach all phone page | Phones withou price or "ÜCRETSİZ" tag appear. Some phones that don't have price displayed (example iPhone 4s 16GB) while opening will diplay a price "From 34TL/month". This phone was showing while the filter "under 24TL/moth" was active. Screenshots 7, 8, 9 | Not a bug. It is CMS amanged.
16 | 2015-12-06 |  | NAB | Reach BlackBery z10 128GB Phone details page | Missing specifications. Screenshot 10 | Not a bug. Parametters not set in CMS. Setting CMS parametters will fix this issue.
17 | 2015-12-06 |  | NAB | Reach all phone page | "Esnaf Tarifeleri ile" is missing the left "Sirala" Filter Screenshot 11, 12 | Not a bug. It is design.
18 | 2015-12-06 |  | NAB | Reach all phone filter | Item number is not visible near filter Screenshot 13 | Not a bug. It is design.
19 | 2015-12-06 |  | NAB | - Homepage - Cihazlar | Pressing on "Mobile", "Tablet", "Accessories", "Tariff" will do nothing. Pressing on listing redirects to the needed page. | Not a bug. It is design.
20 | 2015-12-06 |  | NAB | - Homepage - Cihazlar - Tablet listing | Mobile phones and accessories appear on tablet listing page Screenshot 14 | Not a bug. It is CMS amanged.
21 | 2015-12-06 |  | Page on hold. | - Reach accessories page - Reach accessorry produc page | "Buy now" button does nothing | Page on hold.
22 | 2015-12-06 |  | NAB | Click "Online Self-Service" link from the upper left corner on any page | "Online Self-Service" redirects to live web page | Not a bug.
23 | 2015-12-06 |  | NAB | Reach "http://vodafonetr-stage.pjmedia.co.uk/cok-satanlar-masasi" | Pressing "Satin Al" button from mouse over display redirects to live product details | Not a bug.
24 | 2015-12-06 |  | NAB | Reach any tablet product details | No plan is displayed in the "Ne Kadar Oderim?" drop down table Screenshot 15 | Not a bug. It is CMS amanged.
25 | 2015-12-08 |  | Page in progress | 1. Reach Tariff list page 2. Select Vodafone’luyum and Pre to Post | Ret Text is missaligen for arife İnternet Her Yöne Konuşma Her Yöne SMS Aylık Ücre Screenshot 16 | Page in progress
26 | 2015-12-08 |  | Page in progress | 1. Reach Tariff listing 2. Use sorting filter (example A-Z / Z-A) | Sorting filter displays only a few plans | Page in progress
27 | 2015-12-08 |  |  | 1. Reach Produc detail page 2. Choose plan filter 3. Notice that package selection doesn’t work as intended. | After selecting an plan filter, the package selection doesn't add to price and doesn't generate SKU code. Also all packages can be selected
28 | 2015-12-08 |  |  | 1. Open Product detail page 2. Open recommended devices and or compatible devices 3. notice some images are not shown 4. scrool up or down for the images to appear | On product detail page some images are not shown untill the user scrolls up or down once. Please see video

## Scheenshots
Screenshot 1
Screenshot 2
Screenshot 3
Screenshot 4
Screenshot 5
Screenshot 6
Screenshot 7 | Screenshot 8 | Screenshot 9
Screenshot 10
Screenshot 11
Screenshot 12
Screenshot 13
Screenshot 14
Screenshot 15
Screenshot 16

## Test Report
Test cases Number | Not run | Failed | Completed | N/A
35 | 2 | 2 | 23 | 8
Requirements TraceabilityMatrix | Not run | Failed | Completed | N/A
72 | 53 | 0 | 19 | 0
Bugs | In Progress \ On hold | Open | Fixed \ Not A Bug
28 | 4 | 3 | 21